## Annex I
Decentralized Capital Budget Programme - 2019
Division wise Physical and Financial Weekly Progress as of 03.09.2019
Division:-
No. | GN Division | Name of the Project | Projects | [12 empty] | Allocation | [12 empty] | ** Physical Progress (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  | No. of Projects Approved |  |  | Total categorized by Sectors * | [9 empty] | Allocation Made (Rs.Mn) |  |  | Total Allocation Categorized by Sectors * | [9 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | Construction | Goods / Services Purchase | Total | WS | EL | RA | RE | MI | CD | VL | CP | OI | FE | Construction | Goods / Services Purchase | Total | WS | EL | RA | RE | MI | CD | VL | CP | OI | FE |  | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4)
1 | Maligawila | Providing chairs for Maligawila minipuragama Yasodara kantha Awamanglyadara society |  | 1 | [12 empty] | 35000 | 35000 | [9 empty] | 35000 | [9 empty] | 1 | 34999.52 | bar: Total; Total categorized by Sectors * FE
2 | Division | Helding Vocational Trainnings for Women to improve Self industries |  | 1 | [12 empty] | 100000 | 100000 | [6 empty] | 100000 | [5 empty] | 1 | bar: Total to Total categorized by Sectors * FE
3 | Division | Providing Sports equipments for Registered Youth and Sports Clubs |  | 1 | [12 empty] | 50000 | 50000 | [9 empty] | 50000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
4 | Division | Providing chairs for Registered welfare societies |  | 1 | [12 empty] | 100000 | 100000 | [9 empty] | 100000 | [9 empty] | 1 | 99871.63 | bar: Total; Total categorized by Sectors * FE
5 | Mahagodayaya | Providing Roofing Sheets for Mahagodayaya Farmers society |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
6 | Udagama | Providing chairs for 11th mile post Samadi Awamangalyadara societies |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 | [9 empty] | 1 | 40000 | bar: Total; Total categorized by Sectors * FE
7 | Maligawila | Providing two Gas cooker set for Dilena Tharu Govi kantha societies |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
8 | Gonaganara | Finish the rest of works of Raja Mawatha Walliammara awamanglyadara Society | 1 | [12 empty] | 100000 |  | 100000 | [9 empty] | 100000 | [9 empty] | 1 | 100000 | bar: Total; Total categorized by Sectors * FE
9 | Dicyaya | Repairing the Buttala Adunkulupawwa Aranya senasana Road | 1 | [12 empty] | 300000 |  | 300000 |  |  | 300000 | [11 empty] | 1 | bar: Total to Total categorized by Sectors * FE
10 | Maligawila | Finish the rest of works of Ratthrewewa junction Yasa Isuru welfare Society hall. | 1 | [12 empty] | 200000 |  | 200000 | [9 empty] | 200000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
11 | Koonketiya | Repairing the roof of Rajamawatha 17 th mile post Rosa Kusum Pre chlidhood Development center. | 1 | [12 empty] | 100000 |  | 100000 | [9 empty] | 100000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
12 | Medagama | Finish the rest of works of Medagama Karavilakotuwa Ekamuthu Awamanglyadara Society Building. | 1 | [12 empty] | 200000 |  | 200000 | [9 empty] | 200000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
13 | Kukurampola | Mesh Covering of Kukurampola, Kovilpalessa commiunity center | 1 | [12 empty] | 100000 |  | 100000 | [9 empty] | 100000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
14 | Rahatahangama | Consructing the play ground of Block 9-11 | 1 | [12 empty] | 200000 |  | 200000 | [9 empty] | 200000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
15 | Mahgodayaya | Finish the rest of works of mahagodayaya Samagi Maranadara Society Building | 1 | [12 empty] | 200000 |  | 200000 | [9 empty] | 200000 |  |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
16 | Kumaragama | Providing a buffet set for Uva Pelwatta Kumaragama Block04 Ekasath Awamanglyadara society |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 | [9 empty] | 1 | 40000 | bar: Total; Total categorized by Sectors * FE
17 | Goonaganara | Providing a Loud Speeker for Gonaganara Dimuthu Maranadara society |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
18 | Goonaganara | Constrution Sri Wimalananda Dhamma School Building of Goonaganara 21th mile post |  | 1 | [12 empty] | 50000 | 50000 | [9 empty] | 50000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
19 | Minipuragama | Providing a Steel hut for Minipuragama Yasodara kantha Awamanglyadara society |  | 1 | [12 empty] | 65000 | 65000 | [9 empty] | 65000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
20 | Pettagamwela | Developing the Sri Rahathankanda Arannya senasanaya |  | 1 | [12 empty] | 100000 | 100000 | [9 empty] | 100000 | [9 empty] | 1 | 98350 | bar: Total; Total categorized by Sectors * FE
21 | Pelwatta | Providing a Steel hut for Acala Maranadara society Pimburalanda, 7th mile post |  | 1 | [12 empty] | 65000 | 65000 | [9 empty] | 65000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
22 | Kumaragama | Providing a Steel hut for Kumaragama Block 4 Maranadara Society |  | 1 | [12 empty] | 65000 | 65000 | [9 empty] | 65000 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
23 | Yudaganawa | Providing Chairs for Peellawela Maranadara Society |  | 1 | [12 empty] | 25000 | 25000 | [9 empty] | 25000 | [9 empty] | 1 | 24785.66 | bar: Total; Total categorized by Sectors * FE
24 | Pettagamwela | Providing a Steel hut for Samadhi Awamangalyadara Society, 11th mile post. |  | 1 | [12 empty] | 65000 | 65000 | [9 empty] | 65000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
25 | Galtammandiya | Providing Chairs for Galtammandiya, Samagipura Annyonnyadara Society |  | 1 | [12 empty] | 25000 | 25000 | [9 empty] | 25000 | [9 empty] | 1 | 24785.66 | bar: Total; Total categorized by Sectors * FE
26 | Pettagamwela | Constrution Gamudawa Sri Sudharshanarama Building |  | 1 | [12 empty] | 100000 | 100000 | [9 empty] | 100000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
27 | Waguruwela | Providing equipments for Dhamma Schcool of Waguruwela Sri Poyamalu Temple. |  | 1 | [12 empty] | 100000 | 100000 | [9 empty] | 100000 | [9 empty] | 1 | 99711 | bar: Total; Total categorized by Sectors * FE
28 | Mahasenpura | Providing equipments for Kalayathanaya, pahalawela, pelwatta. |  | 1 | [12 empty] | 100000 | 100000 | [9 empty] | 100000 | [9 empty] | 1 | 87379 | bar: Total; Total categorized by Sectors * FE
29 | Buruthagolla | Providing Water tanks for Gemishakthi Kantha Society, Buruthagolla |  | 1 | [12 empty] | 50000 | 50000 | [9 empty] | 50000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
30 | Rahatahangama | Providing a Generater for Ekamuthu Maranadara Society, Block 15-16, Rahathangama |  | 1 | [12 empty] | 35000 | 35000 | [9 empty] | 35000 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
31 | Ulugala | Providing chairs for Awamanglyadara Welfare society, Janapadaya, Okkampitiya. |  | 1 | [12 empty] | 25000 | 25000 | [9 empty] | 25000 | [9 empty] | 1 | 24785.66 | bar: Total; Total categorized by Sectors * FE
32 | Koonketiya | Constrution Youn Wijaya Awamanglyadara Society Building, 18 mile post, Rajamawatha |  | 1 | [12 empty] | 65000 | 65000 | [9 empty] | 65000 | [8 empty] | 1 |  | 33500 | bar: Total; Total categorized by Sectors * FE
33 | Maligawila | Providing a Buffet set for Jana Shakthi Kantha Society, Upper Dambegoda |  | 1 | [12 empty] | 40000 | 40000 | [9 empty] | 40000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * FE
34 | Medagama | Concrete the​ by road near the Rajapaksha kadaya , in Badalkumbura road, | 1 | [12 empty] | 485000 |  | 485000 |  |  | 485000 | [11 empty] | 1 | bar: Total to Total categorized by Sectors * FE
35 | Goonaganara | Providing equipments for Walagamba Vihara Dhamma School 19th mile post Rajamawatha. |  | 1 | [12 empty] | 34650 | 34650 | [9 empty] | 34650 | [9 empty] | 1 | 34650 | bar: Total; Total categorized by Sectors * FE
36 | Udagama | Providing equipments for Rahathankanda Arannya Dhamma School |  | 1 | [12 empty] | 29700 | 29700 | [9 empty] | 29700 | [9 empty] | 1 | 25350 | bar: Total; Total categorized by Sectors * FE
37 | Unawatuna | Providing equipments for Unawatuna Purana Vihara Dhamma School |  | 1 | [12 empty] | 34650 | 34650 | [9 empty] | 34650 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
38 | Medagama | Providing serpina for Dhameesha Ranagakalayathanaya |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
39 | Udagama | Providing a Nest café machine and a Fax machine for Dutugemunu Old boys 94 Batch |  | 1 | [12 empty] | 59400 | 59400 | [9 empty] | 59400 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
40 | Ulugala | Providing a Seelin fans for Building of Eksath Awamanglyadara society |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 | [9 empty] | 1 | 24750 | bar: Total; Total categorized by Sectors * FE
41 | Pettagamwela | Providing equipments for pla aera of Kids world pre school and day care center |  | 1 | [12 empty] | 39600 | 39600 | [9 empty] | 39600 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
42 | Medagama | Providing Asbastos Sheet for Garadibakina Farmers Society Building |  | 1 | [12 empty] | 39600 | 39600 | [9 empty] | 39600 | [9 empty] | 1 | 39340 | bar: Total; Total categorized by Sectors * FE
43 | Mahagodayaya | Providing chairs for Nelum Kantha society |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 | [9 empty] | 1 | 19682.73 | bar: Total; Total categorized by Sectors * FE
44 | Okkampitiya | Providing chairs for Social development center |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 | [9 empty] | 1 | 19682.73 | bar: Total; Total categorized by Sectors * FE
45 | Udagama | Providing equipments for Mo/ Dutugemunu Primary Collage open stage |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
46 | Yatiyallathota | Providing a Genareter for Wellassa sahayogitha padanama, Munkotuwa |  | 1 | [12 empty] | 44550 | 44550 | [9 empty] | 44550 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
47 | Puhulkotuwa | Providing Plastic chairs and Saspan set for Vijaya Maranadara Society |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 | [9 empty] | 1 | 24785.66 | bar: Total; Total categorized by Sectors * FE
48 | Unawatuna | Providing Plastic chairs for Sri Mahanaga Maranadara Society |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 | [9 empty] | 1 | 24785.66 | bar: Total; Total categorized by Sectors * FE
49 | Pettagamwela | Finishing the works of Udara Maranadara Society Building | 1 | [12 empty] | 19800 |  | 19800 | [9 empty] | 19800 | [9 empty] | 1 | 19799 | bar: Total; Total categorized by Sectors * FE
50 | Mahasenpura | Providing Music Instruments for Arunodaya Pre School |  | 1 | [12 empty] | 11880 | 11880 | [9 empty] | 11880 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
51 | Yatiyallathota | Building the rest of Isuru pre childhood center building | 1 | [12 empty] | 14850 |  | 14850 | [9 empty] | 14850 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
52 | Maligawila | Providing gage 28 sheet for Sanasuma Awamangalyadara Society, Raththriwewa |  | 1 | [12 empty] | 34650 | 34650 | [9 empty] | 34650 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
53 | Udagama | Providing Nescafe machine for Wijaya welfare Society, 11th Maile post. |  | 1 | [12 empty] | 49500 | 49500 | [9 empty] | 49500 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
54 | Yatiyallathota | Building the Burutha Road Youth welfare Sahana Awamanglayadara Society building | 1 | [12 empty] | 39600 |  | 39600 | [9 empty] | 39600 | [9 empty] | 1 | 39346 | bar: Total; Total categorized by Sectors * FE
55 | Unawatuna | Providing Plastic chairs for Eka hitha Maranadara Society |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 | [9 empty] | 1 | 24750 | bar: Total; Total categorized by Sectors * FE
56 | Waguruwela | Providing a Genarater for Deyyannewela Wijaya Awamangalyadara Society, |  | 1 | [12 empty] | 44550 | 44550 | [9 empty] | 44550 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
57 | Koonketiya | Providing a Genarater for Rashmi WishwaKawaya |  | 1 | [12 empty] | 39600 | 39600 | [9 empty] | 39600 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
58 | Koonketiya | Providing Plastic chairs for Koonketiya Samuradhi Society |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 | [9 empty] | 1 | 19682.73 | bar: Total; Total categorized by Sectors * FE
59 | Weheragala | Providing chairs and a cupboard for Lahiru Paropakara Society |  | 1 | [12 empty] | 29700 | 29700 | [9 empty] | 29700 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
60 | Goonaganara | Providing Music Instruments for Nruththyanjali Kalayathanaya |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
61 | Pahalagama | Providing a Printer for Dambeyaya Primary School |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
62 | Okkampitiya | Providing Books for Library of Wijayabahu Primary School |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
63 | Horabokka | Providing a Genarater for Waliaralanda Ekasath Maranadara Society, |  | 1 | [12 empty] | 39600 | 39600 | [9 empty] | 39600 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
64 | Minipuragama | Providing Music Instruments for Sri Lakmal Kalayathanaya |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
65 | Minipuragama | Providing chairs for Wemens Rural Development Society |  | 1 | [12 empty] | 19800 | 19800 | [9 empty] | 19800 | [9 empty] | 1 | 19682.73 | bar: Total; Total categorized by Sectors * FE
66 | Puhulkotuwa | Building the Bubudu Eksath Welfare Society Building | 1 | [12 empty] | 194000 |  | 194000 | [9 empty] | 194000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
67 | Udagama | Finishing rest works of Samagi Awamanglyadara Society Building | 1 | [12 empty] | 194000 |  | 194000 | [9 empty] | 194000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
68 | Koonketiya | Providing equipments for tiling of Walliammara Awamangalyadara Soceity Building |  | 1 | [12 empty] | 11880 | 11880 | [9 empty] | 11880 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
69 | Yatiyallathota | Providing chairs for Samurdhi village Society, old Burutha road, Puwakpitiya. |  | 1 | [12 empty] | 24750 | 24750 | [9 empty] | 24750 |  |  |  | 1 | bar: Total; Total categorized by Sectors * FE
70 | Unawatuna | Gravaling Unawatuna Palugaswewa by road in Buttala Division | 1 | [12 empty] | 242500 |  | 242500 |  |  | 242500 | [9 empty] | 1 | bar: Total to Total categorized by Sectors * FE
71 | Yudaganawa | Providing Steel hut for Peellawela Eksath Maranadara Society |  | 1 | [12 empty] | 99000 | 99000 | [9 empty] | 99000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
72 |  | Providing GI pips for Ekasitha Maranadara Society in Buttala Division |  | 1 | [12 empty] | 49500 | 49500 | [9 empty] | 49500 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
73 |  | Sraring a revoling fund pragramme inLiyaPaula Kantha Society in Buttala Division |  | 1 | [12 empty] | 99000 | 99000 | [9 empty] | 99000 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
74 | Udaarwa | Building Weherayaya temples Danashalawa in Buttala Division |  | 1 | [12 empty] | 49500 | 49500 | [9 empty] | 49500 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
75 | Maligawila | Providing desks and Plastic chairs for Maligawila Siri Sumanajothi Dhamma School in Buttala Division |  | 1 | [12 empty] | 49500 | 49500 | [9 empty] | 49500 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
76 | Kukurampola | Providing equipments for Kukuluwa vihara Library building |  | 1 | [12 empty] | 49500 | 49500 | [9 empty] | 49500 |  |  | 1 | bar: Total; Total categorized by Sectors * FE
Total |  |  | 15 | 61 | 76 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 72 | 2589750 | 2726210 | 5315960 |  |  | 1027500 | 0 | 0 | 0 | 100000 | 0 | 0 | 4188460 | 0 | 0 | 19 | 23 | 8 | 1 | 0 | 0 | 1 | 24 | 1044455.37
76
|  | * Projects should be categorized for following sectors |  |  | Total categorized by Sectors * CD: ** Physical progress |  | 5315960 | [7 empty] | 5315960 | [11 empty] | 76
|  | Sector Name |  |  | Total: Circular code
|  | WS- Rural Water Supply |  |  | Total: 1.1; Total categorized by Sectors * CD: A - Estimates are being / to be prepared
|  | EL- Rural Electricity |  |  | Total: 1.2; Total categorized by Sectors * CD: B - For Constructions : B-1 = Estimates Approved & Bid Documents Prepared, B-2 = Quotation / Bid called, B-3= Quotation / Bid Received , B-4= Contract Awarded
|  | RA - Rural Access |  |  | Total: 1.3; Total categorized by Sectors * CD: Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
|  | RE- Rural Economy |  |  | Total: 1.4; Total categorized by Sectors * CD: C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
|  | MI - Minor Irrigation |  |  | Total: 1.7; Total categorized by Sectors * CD: D - For Constructions : 60% completed Other : Received goods /instruments as per the order
|  | CD - Community Development |  |  | Total: 1.6; Total categorized by Sectors * CD: E - For Constructions 80% completed Other : Received goods /instruments as per the order
|  | VL- Vocational and Livelihood |  |  | Total: 1.11; Total categorized by Sectors * CD: F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
|  | CP - Community Protection |  |  | Total: 1.1; Total categorized by Sectors * CD: G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
|  | OI - Other Infrastructure |  |  | Total: 1.12
|  | FE - Supply of facilities and Equipment |  |  | Total: 1.5 , 1.8 , 1.9

## Annex II
Annexure/ DCB/ 02
Decentralized Capital Budget Programme - 2019 Monaragala District
Physical and Financial Progress of the Month of 03.09.2019
Divisional Secretariat Division (a) |  | Name: Buttala
No:1243
SN | Name of MP | Name of Project | අංශය | G.N. Division (b) |  | Type of Project (Construction / Goods & Services) | Sector | Total Estimate Cost (Rs.) |  | Allocation (Rs.) | sector | Expenditure (Rs.) | Unit of Measure | Physical Progress (c) | [9 empty] | No of Beneficiaries | Remarks
|  |  |  | Name | No |  |  | With VAT | Without VAT |  |  |  |  | A | B |  |  |  | C | D | E | F | G
[15 empty] | B1 | B2 | B3 | B4
1 | R.M Ranjith Maddumabandara | Providing chairs for Maligawila minipuragama Yasodara kantha Awamanglyadara society |  | Maligawila | 12595 | Goods & Services | FE |  |  | 35000 |  | 34999.52 | [10 empty] | 1
2 | R.M Ranjith Maddumabandara | Helding Vocational Trainnings for Women to improve Self industries |  | Division |  | Goods & Services | VL |  |  | 100000 | [5 empty] | 1
3 | R.M Ranjith Maddumabandara | Providing Sports equipments for Registered Youth and Sports Clubs |  | Division |  | Goods & Services | FE |  |  | 50000 | [5 empty] | 1
4 | R.M Ranjith Maddumabandara | Providing chairs for Registered welfare societies |  | Division |  | Goods & Services | FE |  |  | 100000 |  | 99871.63 | [10 empty] | 1
5 | R.M Ranjith Maddumabandara | Providing Roofing Sheets for Mahagodayaya Farmers society |  | Mahagodayaya | 12590 | Goods & Services | FE |  |  | 40000 | [6 empty] | 1
6 | R.M Ranjith Maddumabandara | Providing chairs for 11th mile post Samadi Awamangalyadara societies |  | Udagama | 12589 | Goods & Services | FE |  |  | 40000 |  | 40000 | [10 empty] | 1
7 | R.M Ranjith Maddumabandara | Providing two Gas cooker set for Dilena Tharu Govi kantha societies |  | Maligawila | 12595 | Goods & Services | FE |  |  | 40000 | [5 empty] | 1
8 | J.M Ananda Kumarasiri | Finish the rest of works of Raja Mawatha Walliammara awamanglyadara Society |  | Gonaganara | 12611 | Construction | FE |  |  | 100000 |  | 100000 | [10 empty] | 1
9 | J.M Ananda Kumarasiri | Repairing the Buttala Adunkulupawwa Aranya senasana Road |  | Dicyaya | 12588 | Construction | RA |  |  | 300000 | [7 empty] | 1
10 | J.M Ananda Kumarasiri | Finish the rest of works of Ratthrewewa junction Yasa Isuru welfare Society hall. |  | Maligawila | 12595 | Construction | FE |  |  | 200000 | [7 empty] | 1
11 | J.M Ananda Kumarasiri | Repairing the roof of Rajamawatha 17 th mile post Rosa Kusum Pre chlidhood Development center. |  | Koonketiya | 12599 | Construction | FE |  |  | 100000 | [7 empty] | 1
12 | J.M Ananda Kumarasiri | Finish the rest of works of Medagama Karavilakotuwa Ekamuthu Awamanglyadara Society Building. |  | Medagama | 12600 | Construction | FE |  |  | 200000 | [7 empty] | 1
13 | J.M Ananda Kumarasiri | Mesh Covering of Kukurampola, Kovilpalessa commiunity center |  | Kukurampola | 12607 | Construction | FE |  |  | 100000 | [7 empty] | 1
14 | J.M Ananda Kumarasiri | Consructing the play ground of Block 9-11 |  | Rahatahangama | 12612 | Construction | FE |  |  | 200000 | [7 empty] | 1
15 | J.M Ananda Kumarasiri | Finish the rest of works of mahagodayaya Samagi Maranadara Society Building |  | Mahgodayaya | 12590 | Construction | FE |  |  | 200000 | [7 empty] | 1
16 | J.M Ananda Kumarasiri | Providing a buffet set for Uva Pelwatta Kumaragama Block04 Ekasath Awamanglyadara society |  | Kumaragama | 12606 | Goods & Services | FE |  |  | 40000 |  | 40000 | [10 empty] | 1
17 | J.M Ananda Kumarasiri | Providing a Loud Speeker for Gonaganara Dimuthu Maranadara society |  | Goonaganara | 12611 | Goods & Services | FE |  |  | 40000 | [6 empty] | 1
18 | J.M Ananda Kumarasiri | Constrution Sri Wimalananda Dhamma School Building of Goonaganara 21th mile post |  | Goonaganara | 12611 | Goods & Services | FE |  |  | 50000 | [5 empty] | 1
19 | J.M Ananda Kumarasiri | Providing a Steel hut for Minipuragama Yasodara kantha Awamanglyadara society |  | Minipuragama | 12596 | Goods & Services | FE |  |  | 65000 | [5 empty] | 1
20 | J.M Ananda Kumarasiri | Developing the Sri Rahathankanda Arannya senasanaya |  | Pettagamwela | 12601 | Goods & Services | FE |  |  | 100000 |  | 98350 | [10 empty] | 1
21 | J.M Ananda Kumarasiri | Providing a Steel hut for Acala Maranadara society Pimburalanda, 7th mile post |  | Pelwatta | 12604 | Goods & Services | FE |  |  | 65000 | [5 empty] | 1
22 | J.M Ananda Kumarasiri | Providing a Steel hut for Kumaragama Block 4 Maranadara Society |  | Kumaragama | 12606 | Goods & Services | FE |  |  | 65000 | [6 empty] | 1
23 | J.M Ananda Kumarasiri | Providing Chairs for Peellawela Maranadara Society |  | Yudaganawa | 12587 | Goods & Services | FE |  |  | 25000 |  | 24785.66 | [10 empty] | 1
24 | J.M Ananda Kumarasiri | Providing a Steel hut for Samadhi Awamangalyadara Society, 11th mile post. |  | Pettagamwela | 12601 | Goods & Services | FE |  |  | 65000 | [5 empty] | 1
25 | J.M Ananda Kumarasiri | Providing Chairs for Galtammandiya, Samagipura Annyonnyadara Society |  | Galtammandiya | 12593 | Goods & Services | FE |  |  | 25000 |  | 24785.66 | [10 empty] | 1
26 | J.M Ananda Kumarasiri | Constrution Gamudawa Sri Sudharshanarama Building |  | Pettagamwela | 12601 | Goods & Services | FE |  |  | 100000 | [5 empty] | 1
27 | J.M Ananda Kumarasiri | Providing equipments for Dhamma Schcool of Waguruwela Sri Poyamalu Temple. |  | Waguruwela | 12610 | Goods & Services | FE |  |  | 100000 |  | 99711 | [10 empty] | 1
28 | J.M Ananda Kumarasiri | Providing equipments for Kalayathanaya, pahalawela, pelwatta. |  | Mahasenpura | 12605 | Goods & Services | FE |  |  | 100000 |  | 87379 | [10 empty] | 1
29 | J.M Ananda Kumarasiri | Providing Water tanks for Gemishakthi Kantha Society, Buruthagolla |  | Buruthagolla | 12597 | Goods & Services | FE |  |  | 50000 | [5 empty] | 1
30 | J.M Ananda Kumarasiri | Providing a Generater for Ekamuthu Maranadara Society, Block 15-16, Rahathangama |  | Rahatahangama | 12612 | Goods & Services | FE |  |  | 35000 | [6 empty] | 1
31 | J.M Ananda Kumarasiri | Providing chairs for Awamanglyadara Welfare society, Janapadaya, Okkampitiya. |  | Ulugala | 12594 | Goods & Services | FE |  |  | 25000 |  | 24785.66 | [10 empty] | 1
32 | J.M Ananda Kumarasiri | Constrution Youn Wijaya Awamanglyadara Society Building, 18 mile post, Rajamawatha |  | Koonketiya | 12599 | Goods & Services | FE |  |  | 65000 |  | 33500 | [9 empty] | 1
33 | J.M Ananda Kumarasiri | Providing a Buffet set for Jana Shakthi Kantha Society, Upper Dambegoda |  | Maligawila | 12595 | Goods & Services | FE |  |  | 40000 | [8 empty] | 1
34 | Sumedha G Jayasena | Concrete the​ by road near the Rajapaksha kadaya , in Badalkumbura road, |  | Dicyaya | 12588 | Construction | RA |  |  | 485000 | [7 empty] | 1
35 | Sumedha G Jayasena | Providing equipments for Walagamba Vihara Dhamma School 19th mile post Rajamawatha. |  | Goonaganara | 12611 | Goods & Services | FE |  |  | 34650 |  | 34650 | [10 empty] | 1
36 | Sumedha G Jayasena | Providing equipments for Rahathankanda Arannya Dhamma School |  | Udagama | 12589 | Goods & Services | FE |  |  | 29700 |  | 25350 | [10 empty] | 1
37 | Sumedha G Jayasena | Providing equipments for Unawatuna Purana Vihara Dhamma School |  | Unawatuna | 12586 | Goods & Services | FE |  |  | 34650 | [6 empty] | 1
38 | Sumedha G Jayasena | Providing serpina for Dhameesha Ranagakalayathanaya |  | Medagama | 12600 | Goods & Services | FE |  |  | 24750 | [6 empty] | 1
39 | Sumedha G Jayasena | Providing a Nest café machine and a Fax machine for Dutugemunu Old boys 94 Batch |  | Udagama | 12589 | Goods & Services | FE |  |  | 59400 | [6 empty] | 1
40 | Sumedha G Jayasena | Providing a Seelin fans for Building of Eksath Awamanglyadara society |  | Ulugala | 12594 | Goods & Services | FE |  |  | 24750 |  | 24750 | [10 empty] | 1
41 | Sumedha G Jayasena | Providing equipments for pla aera of Kids world pre school and day care center |  | Pettagamwela | 12601 | Goods & Services | FE |  |  | 39600 | [6 empty] | 1
42 | Sumedha G Jayasena | Providing Asbastos Sheet for Garadibakina Farmers Society Building |  | Medagama | 12600 | Goods & Services | FE |  |  | 39600 |  | 39340 | [10 empty] | 1
43 | Vijitha Berugoda | Providing chairs for Nelum Kantha society |  | Mahagodayaya | 12590 | Goods & Services | FE |  |  | 19800 |  | 19682.73 | [10 empty] | 1
44 | Vijitha Berugoda | Providing chairs for Social development center |  | Okkampitiya | 12592 | Goods & Services | FE |  |  | 19800 |  | 19682.73 | [10 empty] | 1
45 | Vijitha Berugoda | Providing equipments for Mo/ Dutugemunu Primary Collage open stage |  | Udagama | 12589 | Goods & Services | FE |  |  | 19800 | [6 empty] | 1
46 | Vijitha Berugoda | Providing a Genareter for Wellassa sahayogitha padanama, Munkotuwa |  | Yatiyallathota | 12609 | Goods & Services | FE |  |  | 44550 | [6 empty] | 1
47 | Vijitha Berugoda | Providing Plastic chairs and Saspan set for Vijaya Maranadara Society |  | Puhulkotuwa | 12602 | Goods & Services | FE |  |  | 24750 |  | 24785.66 | [10 empty] | 1
48 | Vijitha Berugoda | Providing Plastic chairs for Sri Mahanaga Maranadara Society |  | Unawatuna | 12586 | Goods & Services | FE |  |  | 24750 |  | 24785.66 | [10 empty] | 1
49 | Vijitha Berugoda | Finishing the works of Udara Maranadara Society Building |  | Pettagamwela | 12601 | Construction | FE |  |  | 19800 |  | 19799 | [10 empty] | 1
50 | Vijitha Berugoda | Providing Music Instruments for Arunodaya Pre School |  | Mahasenpura | 12605 | Goods & Services | FE |  |  | 11880 | [6 empty] | 1
51 | Vijitha Berugoda | Building the rest of Isuru pre childhood center building |  | Yatiyallathota | 12609 | Construction | FE |  |  | 14850 | [6 empty] | 1
52 | Vijitha Berugoda | Providing gage 28 sheet for Sanasuma Awamangalyadara Society, Raththriwewa |  | Maligawila | 12595 | Goods & Services | FE |  |  | 34650 | [6 empty] | 1
53 | Vijitha Berugoda | Providing Nescafe machine for Wijaya welfare Society, 11th Maile post. |  | Udagama | 12589 | Goods & Services | FE |  |  | 49500 | [6 empty] | 1
54 | Vijitha Berugoda | Building the Burutha Road Youth welfare Sahana Awamanglayadara Society building |  | Yatiyallathota | 12609 | Construction | FE |  |  | 39600 |  | 39346 | [10 empty] | 1
55 | Vijitha Berugoda | Providing Plastic chairs for Eka hitha Maranadara Society |  | Unawatuna | 12586 | Goods & Services | FE |  |  | 24750 |  | 24750 | [10 empty] | 1
56 | Vijitha Berugoda | Providing a Genarater for Deyyannewela Wijaya Awamangalyadara Society, |  | Waguruwela | 12610 | Goods & Services | FE |  |  | 44550 | [6 empty] | 1
57 | Vijitha Berugoda | Providing a Genarater for Rashmi WishwaKawaya |  | Koonketiya | 12599 | Goods & Services | FE |  |  | 39600 | [6 empty] | 1
58 | Vijitha Berugoda | Providing Plastic chairs for Koonketiya Samuradhi Society |  | Koonketiya | 12599 | Goods & Services | FE |  |  | 19800 |  | 19682.73 | [10 empty] | 1
59 | Vijitha Berugoda | Providing chairs and a cupboard for Lahiru Paropakara Society |  | Weheragala | 12603 | Goods & Services | FE |  |  | 29700 | [6 empty] | 1
60 | Vijitha Berugoda | Providing Music Instruments for Nruththyanjali Kalayathanaya |  | Goonaganara | 12611 | Goods & Services | FE |  |  | 19800 | [6 empty] | 1
61 | Vijitha Berugoda | Providing a Printer for Dambeyaya Primary School |  | Pahalagama | 12598 | Goods & Services | FE |  |  | 19800 | [6 empty] | 1
62 | Vijitha Berugoda | Providing Books for Library of Wijayabahu Primary School |  | Okkampitiya | 12592 | Goods & Services | FE |  |  | 19800 | [6 empty] | 1
63 | Vijitha Berugoda | Providing a Genarater for Waliaralanda Ekasath Maranadara Society, |  | Horabokka | 12585 | Goods & Services | FE |  |  | 39600 | [6 empty] | 1
64 | Vijitha Berugoda | Providing Music Instruments for Sri Lakmal Kalayathanaya |  | Minipuragama | 12596 | Goods & Services | FE |  |  | 19800 | [6 empty] | 1
65 | Vijitha Berugoda | Providing chairs for Wemens Rural Development Society |  | Minipuragama | 12596 | Goods & Services | FE |  |  | 19800 |  | 19682.73 | [10 empty] | 1
66 | Vijitha Berugoda | Building the Bubudu Eksath Welfare Society Building |  | Puhulkotuwa | 12602 | Construction | FE |  |  | 194000 | [5 empty] | 1
67 | Vijitha Berugoda | Finishing rest works of Samagi Awamanglyadara Society Building |  | Udagama | 12589 | Construction | FE |  |  | 194000 | [5 empty] | 1
68 | Vijitha Berugoda | Providing equipments for tiling of Walliammara Awamangalyadara Soceity Building |  | Koonketiya | 12599 | Goods & Services | FE |  |  | 11880 | [5 empty] | 1
69 | Wijayamuni Soysa | Providing chairs for Samurdhi village Society, old Burutha road, Puwakpitiya. |  | Yatiyallathota | 12609 | Goods & Services | FE |  |  | 24750 | [6 empty] | 1
70 | Padma Udayashantha Gunsekara | Gravaling Unawatuna Palugaswewa by road in Buttala Division |  | Unawatuna | 12586 | Construction | RA |  |  | 242500 | [5 empty] | 1
71 | Padma Udayashantha Gunsekara | Providing Steel hut for Peellawela Eksath Maranadara Society |  | Yudaganawa | 12587 | Goods & Services | FE |  |  | 99000 | [5 empty] | 1
72 | Padma Udayashantha Gunsekara | Providing GI pips for Ekasitha Maranadara Society in Buttala Division |  |  |  | Goods & Services | FE |  |  | 49500 | [5 empty] | 1
73 | Padma Udayashantha Gunsekara | Sraring a revoling fund pragramme inLiyaPaula Kantha Society in Buttala Division |  |  |  | Goods & Services | FE |  |  | 99000 | [5 empty] | 1
74 | Padma Udayashantha Gunsekara | Building Weherayaya temples Danashalawa in Buttala Division |  | Udaarwa | 12584 | Goods & Services | FE |  |  | 49500 | [5 empty] | 1
75 | Padma Udayashantha Gunsekara | Providing desks and Plastic chairs for Maligawila Siri Sumanajothi Dhamma School in Buttala Division |  | Maligawila | 12595 | Goods & Services | FE |  |  | 49500 | [5 empty] | 1
76 | Padma Udayashantha Gunsekara | Providing equipments for Kukuluwa vihara Library building |  | Kukurampola | 12606 | Goods & Services | FE |  |  | 49500 | [5 empty] | 1
Total | [9 empty] | 5315960 |  | 1044455.37 |  | 0 | 0 | 19 | 23 | 8 | 1 | 0 | 0 | 1 | 24 | 0 | 0
76
* Projects should be categorized for following sectors
| Sector Name |  |  | Circular code
| WS- Rural Water Supply |  |  | 1.1
| EL- Rural Electricity |  |  | 1.2
| RA-Rural Access |  |  | 1.3
| RE- Rural Economy |  |  | 1.4
| MI- Minor Irrigation |  |  | 1.7
| CD- Community Development |  |  | 1.6
| VL- Vocational and Livelihood |  |  | 1.11
| CP- Community Protection |  |  | 1.1
| OI- Other Infrastructure |  |  | 1.12
| FE- Supply of facilities and Equipment |  |  | 1.5 , 1.8 , 1.9
Instructions to fill the Physical Progress
| Description for rating | [10 empty] | Rates | Percentage Ranges
| Estimate is being / to be prepared and initial works started | [10 empty] | A | (0 - 5)%
| Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared | [10 empty] | B | (6 - 25)%
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments | [10 empty] | C | (26 - 40)%
| Constructions : 60% Completed Other : Received goods / instruments as per the order | [10 empty] | D | (41 - 60)%
| Constructions : 80% Completed Other : Received goods / instruments as per the order | [10 empty] | E | (61 - 80)%
| Constructions : 99% Completed Other : Completed lists of goods to be given to beneficiaries | [10 empty] | F | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs | [10 empty] | G | 100%

## Sinhala
විමධ්‍යගත අයවැය සංවර්ධන වැඩසටහන - 2019 මොනරාගල දිස්ත්‍රික්කය
2019 09.03 දිනට භෞතික හා මූල්‍ය ප්‍රගතිය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | ක්ෂේත්‍රය | ව්‍යාපෘතිය අයත් ගරු මන්ත්‍රී තුමා | කේත අංකය | ව්‍යාපෘතිය | ග්‍රාම නිලධාරි වසම | වෙන්කළ මුදල (රු.ශ) | ඇස්තමේන්තු මුදල කර්මාන්ත ව්‍යාපෘති සඳහා (රු.ශ) | භෞතික ප්‍රගතිය | [9 empty] | වියදම රු. | ප්‍රතිලාභීන් සංඛ්‍යාව
[8 empty] | A | B | B | B | B | C - ආරම්භ කොට 25%ක් වැඩ අවසන් / මිලදීගැනීම් - මිල ගණන් කැඳවා ඇත. | D - 50%ක් වැඩ අවසන් / මිලදීගැනීම් - මිල ගණන්,ලැබී භාණ්ඩ/ද්‍රව්‍ය ඇනවුම් කර ඇත. | E - 75%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය මිලදිගෙන ඇත. | F -99%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය ලබාදීමට ප්‍රතිලාබී නාම ලේඛන සකසා ඇත. | G - 100%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය ප්‍රතිලාබීන්ට ලබාදී ඇත.
[8 empty] | මූලික කටයුතු අරඹා ඇත | ඇස්තමෙන්තු අනුමත කිරීම/ ලිපිගොනු සකසා ඇත | ටෙන්ඩර්/ මිල ගණන් කැඳවා ඇත. | ටෙන්ඩර්/ මිල ගණන් ලැබී ඇත. | කොන්ත්‍රාත් පිරිනමා ඇත.
1 | 1 | RMB | MD/BU/MP/01/047 | මාලිගාවිල මිනිපුරගම,යශෝධරා කාන්තා අවමංගල්‍යාධාර සමිතියට ප්ලාස්ටික් පුටු ලබාදීම | මාලිගාවිල | 35000 | [10 empty] | 1 | 34999.52
2 | 2 | RMB | MD/BU/MP/01/048 | ස්වයං රැකියා ජනනය කිරිමේ අරමුනින් කාන්තාවන් සදහා වෘත්තිය පුහුණු පාඨමාලා පැවැත්විම |  | 100000 |  |  |  | 1
3 | 3 | RMB | MD/BU/MP/01/049 | ප්‍රා.ලේ.කොට්ඨාසයේ ලියාපදිංචි යෞවන හා ක්‍රීඩා උපකරන ලබාදීම | ප්‍රා.ලේ.කොට්ඨාසය | 50000 |  |  |  | 1
4 | 4 | RMB | MD/BU/MP/01/050 | ප්‍රා.ලේ.කොට්ඨාසයේ ලියාපදිංචි ස්වේඡ්ඡා සංවිධාන සදහා ප්ලාස්ටික් පුටු ලබාදිම | ප්‍රා.ලේ.කොට්ඨාසය | 100000 | [10 empty] | 1 | 99871.63
5 | 5 | RMB |  | මහගොඩයාය ගොවි සංවිදානයේ සමිතිශාලාවට සෙවිලි තහඩු ලබාදීම | මහගොඩයාය | 40000 |  |  |  |  | 1
6 | 6 | RMB |  | 11 කණුව සමාධි අවමංග්‍යාධාර සමිතියට පුටු ලබා දීම | උඩගම | 40000 | [10 empty] | 1 | 40000
7 | 7 | RMB |  | මාලිගාවිල දිලෙනතරු ගොවිකාන්තා සමිතියට ගෑස් ලිප් කට්ටල 2ක් ලබාදීම | මාලිගාවිල | 40000 |  |  |  | 1
8 | 1 | AK | MD/BU/MP/02/166 | රජමාවත 19 කණූව වල්ලිඅම්මාර අවමංගල්‍යාධාර සමිතියේ ඉදිරි වැඩ නිම කිරිම | ගෝනගංආර | 100000 | [10 empty] | 1 | 100000
9 | 2 | AK | MD/BU/MP/02/167 | බුත්තල, දික්යාය අදුන්කුලුපව්ව ආරණ්‍ය සේනාසනයට යන මාර්ගය ප්‍රතිසංස්කරණය කිරිම | දික්යාය | 300000 | [5 empty] | 1 | [7 empty] | සංශෝධන
10 | 3 | AK | MD/BU/MP/02/168 | රාත්‍රීවැව හන්දිය යස ඉසුරු සුභ සාධක සමිති ශාලාවේ ඉතිරි වැඩ නිම කිරීම. | මාලිගාවිල | 200000 | [5 empty] | 1
11 | 4 | AK | MD/BU/MP/02/169 | රජ මාවත 17 කණූව රෝස කුසුම් පූර්ව ළමා මධ්‍යස්ථානයේ වහලය ප්‍රතිසංස්කරණය කිරීම. | කෝන්කැටිය | 100000 | [5 empty] | 1
12 | 5 | AK | MD/BU/MP/02/170 | මැදගම කරවිල කොටුව එකමුතු අවමංගල්‍යාධාර සමිති ගොඩනැගිල්ල ඉතිරි වැඩ නිම කිරීම. | මැදගම | 200000 | [5 empty] | 1
13 | 6 | AK | MD/BU/MP/02/171 | කුකුරම්පොල ,කෝවිල්පැලැස්ස ප්‍රජා ශාලාවේ දැල් ආවරණය කිරීම | කුකුරම්පොල | 100000 | [5 empty] | 1
14 | 7 | AK | MD/BU/MP/02/172 | ජනාවාස 9-11 ක්‍රීඩාපිටිය ඉදිකිරීම | රහතන්ගම | 200000 | [5 empty] | 1
15 | 8 | AK | MD/BU/MP/02/173 | මහගොඩයාය සමගි මරණාධාර සමිති නව ගොඩනැගිල්ලේ ඉතිරි වැඩ නිම කිරීම | මහගොඩයාය | 200000 | [5 empty] | 1
16 | 9 | AK | MD/BU/MP/02/174 | ඌව පැල්වත්ත, කුමාරගම ජනාවාස 04 දේවාල කොටස එක්සත් අවමංගල්‍යාධාර සමිතියට බුෆේ කට්ටලයක් ලබාදීම | කුමාරගම | 40000 | [10 empty] | 1 | 40000
17 | 10 | AK | MD/BU/MP/02/175 | ගෝණගංආර දිමුතු මරණාධාර සමිතියට ශබ්ද විකාශන යන්ත්‍රක් ලබාදීම | ගෝනගංආර | 40000 |  |  |  |  | 1
18 | 11 | AK | MD/BU/MP/02/176 | ගෝණගංආර 21 කණුව ශ්‍රී විමලානන්ද දහම් පාසල් ගොඩනැගිල්ල ඉදිකිරිම | ගෝනගංආර | 50000 |  |  |  | 1
19 | 12 | AK | MD/BU/MP/02/177 | මිණිපුරගම යශෝධරා කාන්තා අවමංගළ්‍යාධාර සමිතියට තහඩු මඩුවක් ලබාදීම | මිණිපුරගම | 65000 |  |  |  | 1
20 | 13 | AK | MD/BU/MP/02/178 | ඓතිහාසික ශ්‍රී රහතන්කන්ද ආරණ්‍ය සේනාසනයේ සංවර්ධන කටයුතු කිරිම | පෙට්ටගම්වෙල | 100000 | [10 empty] | 1 | 98350
21 | 14 | AK | MD/BU/MP/02/179 | පිඹුරාලන්ද 7 කණූව අචල මරණාධාර සමිතියට තහඩු මඩුවක් ලබාදිම | පැල්වත්ත | 65000 |  |  |  | 1
22 | 15 | AK | MD/BU/MP/02/180 | කුමාරගම ජනාවස 04 මරණාධාර සමිතියට තහඩු මඩුවක් ලබාදීම | කුමාරගම | 65000 |  |  |  |  | 1
23 | 16 | AK | MD/BU/MP/02/181 | පීල්ලෙවෙල මරණාධාර සමිතියට පුටු ලබා දීම | යුදගනාව | 25000 | [10 empty] | 1 | 24785.66
24 | 17 | AK | MD/BU/MP/02/182 | 11 කණුව සමාධි අවමංගල්‍යාධාර සමිතියට තහඩු මඩුවක් ලබාදීම | පෙට්ටගම්වෙල | 65000 |  |  |  | 1
25 | 18 | AK | MD/BU/MP/02/183 | ගල්ටැම්මණ්ඩිය සමගිපුර සමඟි අන්‍යෝ‍යධාර සමිතියට පුටු ලබා දිම | ගල්ටැම්මණිඩිය | 25000 | [10 empty] | 1 | 24785.66
26 | 19 | AK | MD/BU/MP/02/184 | ගම්උදාව ශ්‍රී සුදර්ශනාරාම අරාමයේ සංඝාවාස ගොඩනැගිල්ල ඉදි කිරිම | පෙට්ටගම්වෙල | 100000 |  |  |  | 1
27 | 20 | AK | MD/BU/MP/02/185 | වගුරුවෙල ශ්‍රී පෝයමළු විහාරස්ථානයේ දහම් පාසල සඳහා උපකරණ ලබාදිම | වගුරුවෙල | 100000 | [10 empty] | 1 | 99711
28 | 21 | AK | MD/BU/MP/02/186 | පහලවෙල පැල්වත්ත කලායතනයට භාණ්ඩ ලබාදීම | මහසෙන්පුර | 100000 | [10 empty] | 1 | 87379
29 | 22 | AK | MD/BU/MP/02/187 | බුරුතගොල්ල ගැමි ශක්ති ගොවි කාන්තා සමිතියට ජල ටැංකි ලබාදීම | බුරුතගොල්ල | 50000 |  |  |  | 1
30 | 23 | AK | MD/BU/MP/02/188 | රහතන්ගම ජනාවාස 15/16 එකමුතු මරණාධාර සමිතියට ජෙනරේටරයක් ලබාදිම | රහතන්ගම | 35000 |  |  |  |  | 1
31 | 24 | AK | MD/BU/MP/02/189 | ඔක්කම්පිටිය ජනපද සහන අවමංගල්‍යාධාර සුභ සාධක සමිතියට පුටු ලබාදීම | උළුගල | 25000 | [10 empty] | 1 | 24785.66
32 | 25 | AK | MD/BU/MP/02/190 | රජ මාවත 18 කණූව යොවුන් වජය අවමංගල්‍යාධාර සමිතියේ ගොඩනැගිල්ල ඉදි කිරිම | කෝන්කැටිය | 65000 | [9 empty] | 1 |  | 33500
33 | 26 | AK | MD/BU/MP/02/191 | දඹේගොඩ ඉහල ජන ශක්ති කාන්තා සමිතියට බුෆේ කට්ටලයක් ලබාදිම | මාලිගාවිල | 40000 | [6 empty] | 1
34 | 1 | SGJ | MD/BU/MP/03/415 | බුත්තල,බඩල්කුඹුර ප්‍රධාන මාර්ගයේ රාජපක්ෂ යකඩ කඩය අසලින් ඇති අතුරු මාර්ගය කොන්ක්‍රීට් කිරිම | දික්යාය | 485000 | [5 empty] | 1
35 | 2 | SGJ | MD/BU/MP/03/416 | රජමාවත, 19 කණුව, වළගම්බා පුුරාණ විහාරයේ දහම් පාසල සදහා උපකරණ ලබා දිම | ගෝනගංආර | 34650 | [10 empty] | 1 | 34650
36 | 3 | SGJ | MD/BU/MP/03/417 | රහතන්කන්ද ආරන්‍ය සේනාසනයේ දහම් පාසල සදහා උපකරණ ලබා දීම | උඩගම | 29700 | [10 empty] | 1 | 25350
37 | 4 | SGJ | MD/BU/MP/03/418 | උනාවටුන පුරාණ විහාරයේ දහම් පාසල සදහා උපකරණ ලබා දීම | උනාවටුන | 34650 |  |  |  |  | 1
38 | 5 | SGJ | MD/BU/MP/03/419 | ධමීෂ රංගකලායතනය සදහා සර්පිනාවක් ලබා දිම | මැදගම | 24750 |  |  |  |  | 1
39 | 6 | SGJ | MD/BU/MP/03/420 | දුටුගැමුණු ආදි ශිෂ්‍ය 94 කණ්ඩායම සදහා නෙස්කැෆේ යන්ත්‍රයක් හා ෆැක්ස් යන්ත්‍රයක් ලබා දිම |  | 59400 |  |  |  |  | 1
40 | 7 | SGJ | MD/BU/MP/03/421 | 6 ඇළ එක්සත් අවමංගල්‍යාධාර සමිතියේ අභිනව ගොඩනැගිල්ල සඳහා සීලිං ෆෑන් ලබා දිම | උළුගල | 24750 | [10 empty] | 1 | 24750
41 | 8 | SGJ | MD/BU/MP/03/422 | කිඩ්ස් වර්ල්ඩ් පෙර පාසල හා දිවා සුරුකුම් මධ්‍යස්ථානයටසෙල්ලම් මිදුල සදහා අවශ්‍ය උපකරණ ලබා දීම | පෙට්ටගම්වෙල | 39600 |  |  |  |  | 1
42 | 9 | SGJ | MD/BU/MP/03/423 | ගැරඩි බකිණ ගොව් සංවිධාන ගොඩනැගිල්ල සදහාඇස්බැස්ටෝස් ෂීට් ලබා දීම | මැදගම | 39600 | [10 empty] | 1 | 39340
43 | 1 | VB | MD/BU/MP/04/550 | නෙළුම් කාන්තා සමිතියට ප්ලාස්ට්ක් පුටු ලබා දීම | මහගොඩයාය | 19800 | [10 empty] | 1 | 19682.73
44 | 2 | VB | MD/BU/MP/04/551 | සමාජ සංවර්ධන කේන්ද්‍රයට ප්ලාස්ට්ක් පුටු ලබා දීම | ඔක්කම්පිටිය | 19800 | [10 empty] | 1 | 19682.73
45 | 3 | VB | MD/BU/MP/04/552 | මො/දුටුගැමුණු ප්‍රාථමිතක විදුහලේ එළිමහන් වේදිකාව ඉදිකිරීමට ද්‍රව්‍යාධාර ලබා දීම | උඩගම | 19800 |  |  |  |  | 1
46 | 5 | VB | MD/BU/MP/04/554 | මුංකොටුව වෙල්ලස්ස සහයෝගතා පදනමට ජෙනරේටරයක් ලබා දීම | යටියල්ලාතොට | 44550 |  |  |  |  | 1
47 | 6 | VB | MD/BU/MP/04/555 | විජය මරණාධාර සමිතියට ප්ලාස්ටික් පුටු සහ සාස්පාන් කට්ටලයක් ලබා දිම | පුහුල්කොටුව | 24750 | [10 empty] | 1 | 24785.66
48 | 7 | VB | MD/BU/MP/04/556 | ශ්‍රි මහානාග මරණාධාර සමිතියට ප්ලාස්ටික් පුටු ලබා දීම | උනාවටුන | 24750 | [10 empty] | 1 | 24785.66
49 | 8 | VB | MD/BU/MP/04/557 | උදාර මරණාධාර සමිතියේ ගොඩනැගිල්ලේ ඉතිරි වැඩ නිම කිරිම | පෙට්ටගම්වෙල | 19800 | [10 empty] | 1 | 19799
50 | 9 | VB | MD/BU/MP/04/558 | අරුණෝදය පෙර පාසලට සංගීත උපකරණ ලබා දීම | මහසෙන්පුර | 11880 |  |  |  |  | 1
51 | 10 | VB | MD/BU/MP/04/559 | ඉසුරු මුල් ළමා විය මධ්‍යස්ථානයේ ඉදි කරගෙන යන ගොඩනැගිල්ලේ ඉදිකිරීම් කටයුතු කිරීම | යටියල්ලාතොට | 14850 |  |  |  |  | 1
52 | 11 | VB | MD/BU/MP/04/560 | රාත්‍රීවැව සැනසුම අවමංගල්‍යාධාර සමිතියට ගේජ් 28 ටකරං තහඩු ලබාදීම | මාලිගාවිල | 34650 |  |  |  |  | 1
53 | 12 | VB | MD/BU/MP/04/561 | 11 කණුව, විජය සුබසාධක සමිතියට නෙස්කැෆේ යන්ත්‍රයක් ලබාදීම | උඩගම | 49500 |  |  |  |  | 1
54 | 13 | VB | MD/BU/MP/04/562 | බුරුතපාර තරුණ සුබසාධක සහන අවමංගල්‍යාධාර සමිතියේ ගොඩනැගිල්ල ඉදිකිරිම | යටියල්ලාතොට | 39600 | [10 empty] | 1 | 39346
55 | 14 | VB | MD/BU/MP/04/563 | එකහිත මරණාධාර සමිතියට ප්ලාස්ටික් පුටු ලබාදීම | උනාවටුන | 24750 | [10 empty] | 1 | 24750
56 | 16 | VB | MD/BU/MP/04/565 | දෙයියන්වෙල විජය අවමංගල්‍යාධාර සමිතියට ජෙනරේටරයක් ලබාදීම | වගුරුවෙල | 44550 |  |  |  |  | 1
57 | 17 | VB | MD/BU/MP/04/533 | රශ්මි විශ්ව කවයට ජෙනරේටරයක් ලබාදීම | කෝන්කැටිය | 39600 |  |  |  |  | 1
58 | 18 | VB | MD/BU/MP/04/567 | කෝන්කැටිය සමෘද්ධි සමිතියට ප්ලාස්ටික් පුටු ලබාදීම | කෝන්කැටිය | 19800 | [10 empty] | 1 | 19682.73
59 | 19 | VB | MD/BU/MP/04/568 | ලහිරු පරෝපකාර සමිතියට පුටු සහ කබඩ් එකක් ලබාදීම | වෙහෙරගල | 29700 |  |  |  |  | 1
60 | 20 | VB | MD/BU/MP/04/569 | නෘත්‍යාංජලි කලායතනයට සංගීත උපකරණ ලබාදීම | ගෝනගංආර | 19800 |  |  |  |  | 1
61 | 21 | VB | MD/BU/MP/04/570 | දඹේයාය ප්‍රාථමික විදුහලට ප්‍රින්ටර් යන්ත්‍රයක් ලබාදීම | පහලගම | 19800 |  |  |  |  | 1
62 | 22 | VB | MD/BU/MP/04/571 | විජයබාහු ප්‍රාථමික විදුහලේ ළමා පුස්තකාලයට පොත් ලබාදිම | ඔක්කම්පිටිය | 19800 |  |  |  |  | 1
63 | 23 | VB | MD/BU/MP/04/572 | වැලිආරලන්ද එක්සත් මරණාධාර සමිතියට විදුලිජනක යන්ත්‍රයක් ලබාදීම | හොරබොක්ක | 39600 |  |  |  |  | 1
64 | 24 | VB | MD/BU/MP/04/573 | ශ්‍රී ලක්මාල් කලායතනයට සංගිත උපකරණ ලබාදිම | මිනිපුරගම | 19800 |  |  |  |  | 1
65 | 25 | VB | MD/BU/MP/04/574 | කාන්තා ග්‍රාම සංවර්ධන සමිතියට ප්ලාස්ටික් පුටු ලබාදීම | මිනිපුරගම | 19800 | [10 empty] | 1 | 19682.73
66 |  | VB | MD/BU/MP/04/1049 | පුබුදු එත්සත් සුබසාධක සමිති ගොඩනැගිල්ල ඉදිකිරීම | පුහුල්කොටුව | 194000 |  |  |  | 1
67 |  | VB | MD/BU/MP/04/1050 | සමගි අවමංගල්‍යාධාර සමිතියේ ඉතිරි වැඩ නිම කිරීම | උඩලම | 194000 |  |  |  | 1
68 |  | VB | MD/BU/MP/04/1008 | වල්ලිඅම්මාර අවමංග්‍යාධාර සමිතිශාලාවේ බිමට ටයිල් ඇල්ලීමට ද්‍රව්‍යාධාර ලබාදීම | කෝන්කැටිය | 11880 |  |  |  | 1
69 | 2 | WS | MD/BU/NL/06/788 | පුවක්පිටිය ගම, පරණ බුරුතපාර, බුත්තල සමෘද්ධි ගම්මාන සමිතියට පුටු ලබාදීම | යටියල්ලාතොට | 24750 |  |  |  |  | 1 | [9 empty] | 76
70 | 1 | PUG | MO/BU/MP/05/634 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ උනාවටුන පලුගස් වැව අතුරැ මාර්ගය ඩෝසර් කර ග්‍රෙවල් කිරීම | උනාවටුන | 242500 |  |  |  | 1
71 | 2 | PUG | MO/BU/MP/05/635 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ පීල්ලවල එක්සත් සුබසාධන මරණාධාර සම්තිය සදහා තහඩු ආවරණයක් ලබා දීම. | යුදගනාව | 99000 |  |  |  | 1
72 | 3 | PUG | MO/BU/MP/05/636 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ එකසිත මරණාධාර සමිතිය සදහා GI වර්ගයේ යකඩ බට ලබා දීම. |  | 49500 |  |  |  | 1
73 | 4 | PUG | MO/BU/MP/05/637 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ ලියපවුර කාන්තා සුබසාධක සමිතියේ ස්වයංරැකියා චක්‍රීය ණය වැඩසටහනක් ආරම්භ කිරීම. |  | 99000 |  |  |  | 1
74 | 5 | PUG | MO/BU/MP/05/638 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ වෙහෙර යාය පන්සලේ ඉදිකෙඓමින් පවතින දාන ශාලාවේ වැඩ සිදු කිරීම. | උඩඅරාව | 49500 |  |  |  | 1
75 | 6 | PUG | MO/BU/MP/05/639 | බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාශයේ මාළිගාවිල සිරි සුමන ජෝති දහම් පාසල සදහා ඩෙස් හා ප්ලාස්ටීක් පුටු ලබා දීම. | මාළිගාවිල | 49500 |  |  |  | 1
76 | 7 | PUG | MO/BU/MP/05/675 | කුකුරම්පොල කකුලුවා රජමහ විහාරයේ පුස්තකාල ගොඩනැගිල්ල සදහා ද්‍රව්‍යාධාර ලබා දීම. | කුකුරම්පොල | 49500 |  |  |  | 1
මුළු එකතුව | [5 empty] | 5315960 | 0 | 0 | 0 | 19 | 23 | 8 | 1 | 0 | 0 | 1 | 24 | 1044455.37 | 0
76
C = ඉදිකිරීම් - ආරම්භ කොට 25%ක් වැඩ අවසන් / මිලදීගැනීම් - මිල ගණන් කැඳවා ඇත.
D = ඉදිකිරීම් - 50%ක් වැඩ අවසන් / මිලදීගැනීම් - මිල ගණන්,ලැබී භාණ්ඩ/ද්‍රව්‍ය ඇනවුම් කර ඇත.
E = ඉදිකිරීම් - 75%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය මිලදිගෙන ඇත.
F= ඉදිකිරීම් - 99%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය ලබාදීමට ප්‍රතිලාබී නාම ලේඛන සකසා ඇත.
G = ඉදිකිරීම් - 100%ක් වැඩ අවසන් / මිලදීගැනීම් - භාණ්ඩ/ද්‍රව්‍ය ප්‍රතිලාබීන්ට ලබාදී ඇත.
ව්‍යාපෘතිය ඉදිරිපත් කරන ලද ගරු මන්ත්‍රීතුමන්ලාගේ නම් හා කෙටි යෙදුම් ලබාදී ඇති ප්‍රතිපාදන ප්‍රමාණයන්
අනු අංකය | ව්‍යාපෘතිය ඉදිරිපත් කරන ලද ගරු මන්ත්‍රීතුමන්ලාගේ නම් හා කෙටි යෙදුම් | [6 empty] | ව්‍යාපෘති ගණන |  | ප්‍රතිපාදන ප්‍රමාණයන්
1 | ගරු අමාත්‍ය ආර්.එම්. රංජිත් මද්දුම බණ්ඩාර මැතිතුමා - RMB | [6 empty] | 7 |  | 405000
2 | ගරු නියෝජ්‍ය කථානායක ආනන්ද කුමාරසිරි මැතිතුමා - AK | [6 empty] | 26 |  | 2455000
4 | මොනරාගල දිස්ත්‍රික් ගරු පාර්ලිමේන්තු මන්ත්‍රිනි සුමේධා ජී ජයසේන මැතිනිය - SGJ | [6 empty] | 9 |  | 772500
5 | මොනරාගල දිස්ත්‍රික් ගරු පාර්ලිමේන්තු මන්ත්‍රි විජිත බේරුගොඩ මැතිතුමා - VB | [6 empty] | 25 |  | 1008730
6 | මොනරාගල දිස්ත්‍රික් ගරු පාර්ලිමේන්තු මන්ත්‍රි පද්ම උදය ශාන්ත ගුණසේකර මැතිතුමා - PUG | [6 empty] | 7 |  | 638500
7 | ජාතික ලැයිස්තු ගරු පාර්ලිමේන්තු මන්ත්‍රි ගාමිණී විජිත් විජයමුණි සොයිසා මැතිතුමා - WS | [6 empty] | 2 |  | 321750
එකතුව | [7 empty] | 76 |  | 5601480