## Weekly Progress
Gampereliya - Rapid Rural Development Programme (RRDP) - 2019
Divisional wise Physical and Financial Weekly Progress as of 03.09. 2019
Divisional Secretariat :- Buttala
No. | Project name | GN Divition | No. of Eligible GN Divisions | Projects * | [14 empty] | Allocation | [14 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  |  | No. of Projects Approved |  |  | Total categorized by Sectors * | [11 empty] | Allocation Made (Rs. Mn) |  |  | Total Allocation Categorized by Sectors * | [11 empty] | A | B |  |  |  | C (40%) | D (60%) | E (80%) | F (99%) | G (100%)
|  |  |  | Construction | Goods / Services Purchase | Total | RA | EL | SF | PG | MI | RE | LCD | EP | TD | RC | HD | SW | Construction | Goods / Services Purchase | Total | RA | EL | SF | PG | MI | RE | LCD | EP | TD | RC | HD | SW |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Devolopping Doowa Perakatiya Road With Small Culvart | Udaarawa | 12584 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 600 | bar: Total to Total categorized by Sectors * RA
2 | Developping Unawatuna Horabokka Road | Horabokka | 12585 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 780 | bar: Total to Total categorized by Sectors * RA
3 | Developping The Wewewela Mada Road From Passara Road | Pelwatta | 12604 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 1400 | bar: Total to Total categorized by Sectors * RA
4 | Developping Kukuluwawa Viharaya Road | Kukurampola | 12607 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 2500 | bar: Total to Total categorized by Sectors * RA
5 | Developping Biock 4 Devala Kotasa School Road | Kumaragama | 12606 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 560 | bar: Total to Total categorized by Sectors * RA
6 | Reparing Block 9/11 Pola Pitiya Road | Rahathangama | 12612 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 480 | bar: Total to Total categorized by Sectors * RA
7 | Developping Walimadayaya Village Kudaoya Nersury Road | Kumarapura | 12608 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 530 | bar: Total to Total categorized by Sectors * RA
8 | Reparing From Batalakotuwa To Munkotuwa Road | Yatiyallathota | 12609 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 650 | bar: Total to Total categorized by Sectors * RA
9 | Developping Galgodayaya Road | Mahasenpura | 12605 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 350 | bar: Total to Total categorized by Sectors * RA
10 | Reparing Gamunugama Road From Sugar Co-Operating Name Board | Weheragala | 12603 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 963709.48 | 850 | bar: Total to Total categorized by Sectors * RA
11 | Reparing Unawatuna Ambakolawewa By Road | Unawatuna | 12586 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 900 | bar: Total to Total categorized by Sectors * RA
12 | Reparing Ellawala Road | Puhulkotuwa | 12602 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 250 | bar: Total to Total categorized by Sectors * RA
13 | Developping Rest Of Pubudu Mawatha | Puhulkotuwa | 12602 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 150 | bar: Total to Total categorized by Sectors * RA
14 | Reparing The Road From Yudaganawa Peelewela Bridge To Cannal | Yudaganawa | 12587 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 970000 | 1500 | bar: Total to Total categorized by Sectors * RA
15 | Developping Andampahuwa Road With Interlok Block | Dicyaya | 12588 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 970000 | 400 | bar: Total to Total categorized by Sectors * RA
16 | Developping Udagama Tempel Road Bridge | Udagama | 12589 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 480000 | 5000 | bar: Total to Total categorized by Sectors * RA
17 | Reparing Malgasyaya Cementery Road | Udagama | 12589 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 484410.47 | 450 | bar: Total to Total categorized by Sectors * RA
18 | Reparing Perahara Mawatha | Pettagamwela | 12601 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 969387.8 | 1500 | bar: Total to Total categorized by Sectors * RA
19 | Reparing Karawilakotuwa Tank Road From Okkampitiya Road | Medagama | 12600 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 380 | bar: Total to Total categorized by Sectors * RA
20 | Reparing Karawilakotuwa Nelumgama Road | Medagama | 12600 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 800 | bar: Total to Total categorized by Sectors * RA
21 | Reparing Menadena Cemetary Road | Waguruwela | 12610 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 970000 | 450 | bar: Total to Total categorized by Sectors * RA
22 | Developping 15 th Mile Post Madama Road | Koonketiya | 12599 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 484910 | 600 | bar: Total to Total categorized by Sectors * RA
23 | Developping Udara Tank Road | Koonketiya | 12599 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 520 | bar: Total to Total categorized by Sectors * RA
24 | Developping 19 th Mile Post Tempel Road | Goonaganara | 12611 | 1 | [14 empty] | 970000 | 0 | 970000 | 970000 | [20 empty] | 1 | 970000 | 650 | bar: Total to Total categorized by Sectors * RA
25 | Developping Akkara 100 Road | Mahagodayaya | 12590 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 480 | bar: Total to Total categorized by Sectors * RA
26 | Developping Hospital Road From Weeragas Janction ( mr. Robert"s House By Road ) | Okkampitiya | 12592 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 562222.54 | 350 | bar: Total to Total categorized by Sectors * RA
27 | Reparing The Road From Gurumadayaya To Rathwatte Mawatha | Gaminipura | 12591 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 459647.48 | 380 | bar: Total to Total categorized by Sectors * RA
28 | Reparing Rathwatte Mawatha kiula road | Gaminipura | 12591 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 482637 | 250 | bar: Total to Total categorized by Sectors * RA
29 | Reparing the road from maha Ela to Buruthagolla cemetary | Buruthagolla | 12597 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 350 | bar: Total to Total categorized by Sectors * RA
30 | Repearing the by road from Puruwatta road to delgaswatta road | Pahalagama | 12598 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 569694.18 | 230 | bar: Total to Total categorized by Sectors * RA
31 | Repearing tempel road galpeella road | Galtammandiya | 12593 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 250 | bar: Total to Total categorized by Sectors * RA
32 | Repearing sooriyagaswatta road | Galtammandiya | 12593 | 1 | [14 empty] | 388000 | 0 | 388000 | 388000 | [20 empty] | 1 | 388000 | 450 | bar: Total to Total categorized by Sectors * RA
33 | Repering cannal road from 80 land | Ulugala | 12594 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 474986 | 650 | bar: Total to Total categorized by Sectors * RA
34 | Repearing 7 th cannal road | Ulugala | 12594 | 1 | [14 empty] | 485000 | 0 | 485000 | 485000 | [20 empty] | 1 | 485000 | 430 | bar: Total to Total categorized by Sectors * RA
35 | Repearing ulugala minipuragama combine road | Minipuragama | 12596 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 965040.72 | 240 | bar: Total to Total categorized by Sectors * RA
36 | Repearing sama mawatha | Maligavila | 12595 | 1 | [14 empty] | 582000 | 0 | 582000 | 582000 | [20 empty] | 1 | 582000 | 650 | bar: Total to Total categorized by Sectors * RA
37 | Developping chandramadurarama temple | Yatiyallathota | 12609 | 1 | [14 empty] | 194000 | 0 | 194000 | [9 empty] | 194000 | [11 empty] | 1 | 194000 | 800 | bar: Total; Total categorized by Sectors * RC
38 | Developping block 15/16 rajamaha viharaya | Rahathangama | 12612 | 1 | [14 empty] | 194000 | 0 | 194000 | [9 empty] | 194000 | [11 empty] | 1 | 194000 | 600 | bar: Total; Total categorized by Sectors * RC
39 | Developping dambeyaya temple | Buruthagolla | 12597 | 1 | [14 empty] | 194000 | 0 | 194000 | [9 empty] | 194000 | [11 empty] | 1 | 194000 | 700 | bar: Total; Total categorized by Sectors * RC
40 | Developping Peraketiya Bubula Aranya road | Udaarawa | 12584 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 550 | bar: Total to Total categorized by Sectors * RA
41 | Developping Amunalanda Block 2 Road | Horabokka | 12585 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [18 empty] | 1 |  |  |  | 480 | bar: Total to Total categorized by Sectors * RA
42 | Developping The Pelwatta Passara Road near the 16th maile post Kudaoya 7th maile post road Road | Pelwatta | 12604 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 |  | 1500 | bar: Total to Total categorized by Sectors * RA
43 | Developping Elakandiya Road | Kukurampola | 12607 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [17 empty] | 1 |  |  |  |  | 800 | bar: Total to Total categorized by Sectors * RA
44 | Developping Biock 6 Thalakolawewa Road | Kumaragama | 12606 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 450 | bar: Total to Total categorized by Sectors * RA
45 | Developping Biock 12/14 Cemetary Road | Rahathangama | 12612 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 550 | bar: Total to Total categorized by Sectors * RA
46 | Developping rest of Walimadayaya Village Kudaoya Nersury Road | Kumarapura | 12608 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 700 | bar: Total to Total categorized by Sectors * RA
47 | Developping Walugolla mada Road | Yatiyallathota | 12609 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 771684.48 | 600 | bar: Total to Total categorized by Sectors * RA
48 | Developping rest of Galgodayaya Road | Mahasenpura | 12605 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [18 empty] | 1 |  |  |  | 250 | bar: Total to Total categorized by Sectors * RA
49 | Developping the by road inf ront of the Wasantha Service center of Burutha road Road | Weheragala | 12603 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 150 | bar: Total to Total categorized by Sectors * RA
50 | Developping the Harigalagama Road | Unawatuna | 12586 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 700 | bar: Total to Total categorized by Sectors * RA
51 | Developping the Yudaganawa Janapada Mahanaga Road | Puhulkotuwa | 12602 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 |  | 600 | bar: Total to Total categorized by Sectors * RA
52 | Developping the Samuradhi Mawatha from Halmillaara Sunils house to Yudagana Road | Yudaganawa | 12587 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 |  | 250 | bar: Total to Total categorized by Sectors * RA
53 | Developping the road near the Rajakandiya Mr M.L karunarathanas Coceat Work Shop | Dicyaya | 12588 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 774972.5 | 300 | bar: Total to Total categorized by Sectors * RA
54 | Developping Bandaranayaka Road | Udagama | 12589 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [15 empty] | 1 | [6 empty] | 1500 | bar: Total to Total categorized by Sectors * RA
55 | Developping rest of Perahara Mawatha | Pettagamwela | 12601 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 1000 | bar: Total to Total categorized by Sectors * RA
56 | Concreating Happoruwa temple road | Medagama | 12600 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 768060.61 | 800 | bar: Total to Total categorized by Sectors * RA
57 | Developping Deyyanewela road | Waguruwela | 12610 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 600 | bar: Total to Total categorized by Sectors * RA
58 | Developping near the 19 th Mile Post Mathara Traders Menik River Road | Koonketiya | 12599 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [17 empty] | 1 |  |  |  |  | 540 | bar: Total to Total categorized by Sectors * RA
59 | Developping 19 th Mile Post Cemetary Road | Goonaganara | 12611 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 480 | bar: Total to Total categorized by Sectors * RA
60 | Developping Gangeyaya tank road (Akkara100 road) D.M Sisilas house road | Mahagodayaya | 12590 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 320 | bar: Total to Total categorized by Sectors * RA
61 | Developping the Kaduruwelena and Weeragashandiya Connecting Road | Okkampitiya | 12592 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 500 | bar: Total to Total categorized by Sectors * RA
62 | Developping the road from Batukotuwa main road to Galkanda Arannya senasanaya | Gaminipura | 12591 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 747648.19 | 360 | bar: Total to Total categorized by Sectors * RA
63 | Developping the road from cemerary to Dammbeyaya mada raod | Buruthagolla | 12597 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 774296.06 | 600 | bar: Total to Total categorized by Sectors * RA
64 | Developping the road from Pinthaliya Junction to Athwel palama raod | Pahalagama | 12598 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 500 | bar: Total to Total categorized by Sectors * RA
65 | Developping the road from 17 th junction to Samagipura raod | Galtammandiya | 12593 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 470 | bar: Total to Total categorized by Sectors * RA
66 | Developping Sadahatissa Mawataha Mr Jayatissas house to Pre School road | Ulugala | 12594 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [17 empty] | 1 |  |  |  |  | 500 | bar: Total to Total categorized by Sectors * RA
67 | Developping the road from Boo tree to main raod 87 kadaya | Minipuragama | 12596 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 776000 | 450 | bar: Total to Total categorized by Sectors * RA
68 | Repairing the road from Dammepitiya to Niyadella | Maligawila | 12595 | 1 | [14 empty] | 776000 | 0 | 776000 | 776000 | [20 empty] | 1 | 774142.5 | 900 | bar: Total to Total categorized by Sectors * RA
69 | W.M CHAMARA WEERASINGHA | Udaarawa | 12584 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
70 | R.M NANDAWATHI | Horabokka | 12585 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 | bar: Total; Total categorized by Sectors * HD
71 | D.M ARUNA SAMPATH | Pelwatta | 12604 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
72 | S.G.JAYATHISSA | Kukurampola | 12607 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
73 | W.M.P.D.SUDEERA LAKSMAN | Kumaragama | 12606 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
74 | R.M.CHANDRANI NISHSHANKA | Rahathangama | 12612 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
75 | R.M.RAJARATHNA | Kumarapura | 12608 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
76 | D.M.CHAMINDA PUSHPA KUMARA | Yatiyallathota | 12609 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
77 | W.M. DHARMASENA | Mahasenpura | 12605 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
78 | H.M ARIYAWANSA | Weheragala | 12603 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
79 | K.D PRIYANTHA KUMARAGE | Unawatuna | 12586 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
80 | R.L CHANDARKANTHI | Puhulkotuwa | 12602 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
81 | U.G KAMANI PADMALATHA | Yudaganawa | 12587 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
82 | J.M .P NILANI JYASINGHA | Dicyaya | 12588 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
83 | W.A.K CHAMINDA | Udagama | 12589 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [10 empty] | 1 | 300000 | bar: Total; Total categorized by Sectors * HD
84 | P.K RANJITH | Pettagamwela | 12601 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
85 | W.A SUMITH JANAKA | Medagama | 12600 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
86 | R.M.HEENBANDA | Waguruwela | 12610 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
87 | W.T.R GAMINI ABESIGHA | Koonketiya | 12599 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
88 | L.SEELAWATHI | Goonaganara | 12611 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
89 | K.B.R DINGIRIBANDA | Mahagodayaya | 12590 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
90 | B.M AJITH KUMARA | Okkampitiya | 12592 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
91 | R.M BANDARA MENIKA | Gaminipura | 12591 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
92 | R.M TITUS SOORIYABANDARA | Buruthagolla | 12597 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
93 | R.M NANDAWATHI | Pahalagama | 12598 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
94 | R.M KALUM PADMASIRI | Galtammandiya | 12593 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
95 | R.M SUNIL RATHNAYAKA | Ulugala | 12594 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
96 | E.M SENAVIRATHNA | Minipuragama | 12596 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
97 | I.G PIYASENA | Maligawila | 12595 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
98 | K.M GUNATHILAKA | Udaarawa | 12584 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 | bar: Total; Total categorized by Sectors * HD
99 | R.M.NANDAWATHI | Horabokka | 12585 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
100 | PEMAWATHI MATHAGAWEERA | Pelwatta | 12604 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
101 | T.M.SURANGA | Kukurampola | 12607 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
102 | T.M.NISHANTHA | Kumaragama | 12606 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
103 | W.T.R SAMAN | Rahathangama | 12612 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
104 | W.M DHARMADASA | Kumarapura | 12608 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
105 | R.M.PIYADASA | Yatiyallathota | 12609 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
106 | EBRAHIM MAIMOONACHCHI | Mahasenpura | 12605 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
107 | R.M.KUSUMAWATHI | Weheragala | 12603 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
108 | S.D.CHANDRIKA | Unawatuna | 12586 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
109 | M.G.MIHIDUPALA | Puhulkotuwa | 12602 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
110 | S.A.SAJITH SALINDA | Yudaganawa | 12587 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
111 | K.M PEMAWATHI | Dicyaya | 12588 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
112 | H.A.SAMAN THILAKAPALA | Udagama | 12589 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
113 | S.A.DAMMIKA | Pettagamwela | 12601 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
114 | M.A.SAMANTH KUMARA | Medagama | 12600 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | [5 empty] | 50000 | bar: Total; Total categorized by Sectors * HD
115 | K.W.ABESINHA | Waguruwela | 12610 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
116 | R.M.SIRSWARDANA | Koonketiya | 12599 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
117 | B.M PUSHPAKUMARA | Goonaganara | 12611 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [6 empty] | 1 | bar: Total; Total categorized by Sectors * HD
118 | W.D SUJITH KUMARA | Mahagodayaya | 12590 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [6 empty] | 1 | bar: Total; Total categorized by Sectors * HD
119 | D.M.SUJEEWA BANDARA | Okkampitiya | 12592 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
120 | R.M.RATHNAYAKA | Gaminipura | 12591 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
121 | R.M.SUDUBANDARA | Buruthagolla | 12597 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
122 | R.M.APPUHAMI | Pahalagama | 12598 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [10 empty] | 1 | 300000 | bar: Total; Total categorized by Sectors * HD
123 | R.M.GUNAPALA | Galtammandiya | 12593 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [9 empty] | 1 |  | 220000 | bar: Total; Total categorized by Sectors * HD
124 | R.M.SUNIL RATHNAYAKE | Ulugala | 12594 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
125 | T.M.JAYANTHA SRINATH | Minipuragama | 12596 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
126 | S.VIJITHA KUMARA | Maligawila | 12595 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
127 | Divelopping Peraketiya Budugala Arannya Road | Udaarawa | 12584 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
128 | DiveloppingMurungawatta Block 02 Road | Horabokka | 12585 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
129 | Divelopping Wijaya Road in Buttala Wellawaya Road Starting near the 7th mile post | Pelwatta | 12604 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
130 | Divelopping Udawewa Road Up to Devala kotasa | Kukurampola | 12607 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
131 | Divelopping Miniyanagala road with Culvert | Kumaragama | 12606 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
132 | Divelopping nera R.G Jaysenas house to 20 Village Boodiya road | Rahathangama | 12612 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
133 | Divelopping near the Manumsewa Janapda irrigation cannal road with culvert | Kumarapura | 12608 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
134 | Divelopping the road from Burutha road to Burathapara Gama | Yatiyallathota | 12609 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
135 | Divelopping the Katagalara by road in Mullekumbura 6th mila post | Mahasenpura | 12605 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
136 | Divelopping rest of Weheragala gammana road with spreaddig interlock blocls | Weheragala | 12603 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
137 | Divelopping left road near the Unawatuna Ambakolawewa road Mr Elaberts kadaya | Unawatuna | 12586 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
138 | Divelopping the road near the Puhulkotuwa Pahala Mr W.M Wijesiris house | Puhulkotuwa | 12602 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
139 | Divelopping the Boodiya road by road from Uydaganawa Temple road near Samithi Shalawa | Yudaganawa | 12587 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
140 | Divelopping the rest of Andampahuwa road | Dicyaya | 12588 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
141 | Divelopping the road spreaddig interlock blocls from Udagama temple road to Pasal Mawatha Cannal road. | Udagama | 12589 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
142 | Divelopping the Buttala Pettagamweala Wimalathunga mawatha spreaddig interlock blocls | Pettagamwela | 12601 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
143 | DiveloppingOkkampitiya road Karawilakotuwa wewa road spreaddig interlock blocls | Medagama | 12600 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
144 | Divelopping 16th mile Sagini Circle Road | Koonketiya | 12599 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
145 | Divelopping Kumbukgasara wewa Road | Goonaganara | 12611 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
146 | Divelopping from Moramandiya to Waliara Road | Mahagodayaya | 12590 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
147 | Divelopping Okkampitiya Kaduruwalena(Katugaha house) Road | Okkampitiya | 12592 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
148 | Divelopping Katuwamada By road near Mr W.M Somapalas house road with culvert | Gaminipura | 12591 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
149 | Divelopping the road near the Boogas Handiya Habassa road Dharmasenas house up to Small cemetary road R.M Gunawardhanas house | Buruthagolla | 12597 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
150 | Divelopping from Buttala Gedara to Gadolbamma road | Pahalagama | 12598 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
151 | Divelopping Galtammndiya pahala Aparekka rice mill road | Galtammandiya | 12593 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
152 | Divelopping Maligavila mada road near 92 Mr. Kiriwanthes hous | Ulugala | 12594 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
153 | Divelopping from Minipuragama Karuwalagasdowa ara Mr. Samanthas house Road to Mr Siripalas house road | Minipuragama | 12596 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
154 | Divelopping from71 Mr Jayas land to Palukapitiya tank road | Maligawila | 12595 | 1 | [14 empty] | 776000 |  | 776000 | 776000 | [12 empty] | 1 | bar: Total to Total categorized by Sectors * RA
155 | K.M Sumithra Kumari ,Duwa ,Udaarawa, Uva Palwaththa. | Udaarawa | 12584 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
156 | H.M Sampath Kumara,Manampitiya,Uva Palwaththa. | Horabokka | 12585 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
157 | W.G Nishantha Lakshman,Wawewela pahala ,6 mile post, Uva Palwaththa. | Pelwatta | 12604 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
158 | B.V.Vjayathilaka,Edurugalayaya,Kukurampola, Uva Palwaththa. | Kukurampola | 12607 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
159 | A.A.Duleka Lakmali, Janawasa 04, Dewale kotasa, Kumaragama. | Kumaragama | 12606 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
160 | K.H Jagath, Block 9, Pelwatta Suger Com., Buttala | Rahathangama | 12612 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
161 | H.M Karunarathna, Walimadayaya, Kukurampola,Uva Palwaththa. | Kumarapura | 12608 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
162 | R.M Nadeeka Sadamali,Bathalakothuwa Handiya,Buttala | Yatiyallathota | 12609 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
163 | H.M Ghanawathi, Mullekubura,6 mile post,Uva Palwaththa. | Mahasenpura | 12605 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
164 | S.M Darmapala,Burutha road,Buttala. | Weheragala | 12603 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [8 empty] | 1 |  |  | 130000 | bar: Total; Total categorized by Sectors * HD
165 | R.D Piyal SamaraKoon, 94 /B,Priwena Road, Palugasmada, Unawatuna, Buttala. | Unawatuna | 12586 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
166 | H.M Dayani Herath, Wel widana niwasa,Puhulkotuwa, Buttala | Puhulkotuwa | 12602 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
167 | S.A Chandralatha, Pellewela,Udaganawa,Buttala | Yudaganawa | 12587 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
168 | K.M Upali Chandrasena, Bandaranayak Mawataha, Malgasyaya, Buttala. | Dicyaya | 12588 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
169 | R.W.V Upul Priyankara; 11 mile post, Monaragala Road, Buttala. | Udagama | 12589 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
170 | G.W.Ruwinika Madushani, 1/7, Okkampitiya Road, Buttala | Pettagamwela | 12601 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
171 | R.M PEMATHILAKA | Medagama | 12600 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
172 | D.M. Gunapala, Kandeyaya, Samddi Mawatha, Waguruwela, Buttala. | Waguruwela | 12610 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
173 | A.D. Danushka Sandaruwan, 18 mile post, Raja Mawatha, Buttala. | Koonketiya | 12599 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
174 | D.M. Heenmanika, 19 mile post, Raja Mawatha, Buttala. | Goonaganara | 12611 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
175 | D.M. Kusumawathi, Gageyaya road, Mahagodayaya, Kukurampola. | Mahagodayaya | 12590 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
176 | D.M. Dilan Laksiri, Kandiyaya, Okkampitiya. | Okkampitiya | 12592 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
177 | B.K. Janakasena, Gaminipura, 3 mile post, Okkampitiya. | Gaminipura | 12591 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
178 | H.G.P UPUL LAKMAL | Buruthagolla | 12597 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
179 | W.M. Gunathilaka, Siyabalagas waththa, Pahala gama, Okkampitiya. | Pahalagama | 12598 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
180 | T.R. Anura Srathchandrea, Gal peella, Okkampitiya. | Galtammandiya | 12593 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
181 | H.B.M.Gunarathna, No 7/3, Siya mawatha, Maligawila. | Ulugala | 12594 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
182 | R.M. Karunarathna, No 57, Minipuragama, Maligawila. | Minipuragama | 12596 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [5 empty] | 1 | bar: Total; Total categorized by Sectors * HD
183 | D.M. Suriyasena, Ransili wawa, Rathriwawa, Maligawila. | Maligawila | 12595 |  | 1 | [14 empty] | 300000 | 300000 | [10 empty] | 300000 | [7 empty] | 1 |  |  |  | 50000 | bar: Total; Total categorized by Sectors * HD
Total |  |  |  | 96 | 87 | 183 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 87 | 0 | 66445000 | 26100000 | 92545000 | 65863000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 582000 | 26100000 | 0 | 0 | 28 | 0 | 0 | 31 | 2 | 40 | 9 | 9 | 64 | 43278450.01 | 46460
[6 empty] | Total: 183; Total categorized by Sectors * RA: 0; Total categorized by Sectors * EL: 183 |  | 92545000
|  | * Projects should be categorized for following sectors | [19 empty] | ** Physical progress | [15 empty] | 183
|  | RA- Rural Access | [19 empty] | A - Estimates are being / to be prepared
|  | EL- Rural Electricity | [19 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
|  | SF- Sanitory Facility | [19 empty] | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
|  | PG- Play Ground | [19 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
|  | MI- Minor Irrigation | [19 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
|  | RE- Rural Economy | [19 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
|  | LCD - Livelihood and Capacity Development | [19 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
|  | EP- Environmental Programme | [19 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
TD- Tourism Development
RC- Religious Center Development
HD- Housing Development
SW- Social Welfare

## Monthly Progress
Annexure - 3
Gamperaliya- Rapid Rural Development Programme (RRDP) - 2019
Physical and Financial Progress of the Month of September 2019
Divisional Secretariat :-
No | Name of the Project | GN Division | Sector * | Name of Minister / Member of Parliament/ Officer who proposed the project | Length (k.m/m. )/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress 2019.09.03 | [11 empty] | No. of Beneficiaries | Remarks
[9 empty] | Financial |  | Physical **
[9 empty] | Expenditure (Rs. Mn.) | % | A | B1 | B2 | B3 | B4 | C | D | E | F | G
[12 empty] | B1 | B2 | B3 | B4
1 | Devolopping Doowa Perakatiya Road With Small Culvart | Udaarawa | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 600
2 | Developping Unawatuna Horabokka Road | Horabokka | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 780
3 | Developping The Wewewela Mada Road From Passara Road | Pelwatta | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 1400
4 | Developping Kukuluwawa Viharaya Road | Kukurampola | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 2500
5 | Developping Biock 4 Devala Kotasa School Road | Kumaragama | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 560
6 | Reparing Block 9/11 Pola Pitiya Road | Rahathangama | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 480
7 | Developping Walimadayaya Village Kudaoya Nersury Road | Kumarapura | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 530
8 | Reparing From Batalakotuwa To Munkotuwa Road | Yatiyallathota | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 650
9 | Developping Galgodayaya Road | Mahasenpura | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 350
10 | Reparing Gamunugama Road From Sugar Co-Operating Name Board | Weheragala | RA |  |  | 970000 | DS -Buttala |  | 963709.48 | [10 empty] | 1 | 850
11 | Reparing Unawatuna Ambakolawewa By Road | Unawatuna | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 900
12 | Reparing Ellawala Road | Puhulkotuwa | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 250
13 | Developping Rest Of Pubudu Mawatha | Puhulkotuwa | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 150
14 | Reparing The Road From Yudaganawa Peelewela Bridge To Cannal | Yudaganawa | RA |  |  | 970000 | DS -Buttala |  | 970000 | [10 empty] | 1 | 1500
15 | Developping Andampahuwa Road With Interlok Block | Dicyaya | RA |  |  | 970000 | DS -Buttala |  | 970000 | [10 empty] | 1 | 400
16 | Developping Udagama Tempel Road Bridge | Udagama | RA |  |  | 485000 | DS -Buttala |  | 480000 | [10 empty] | 1 | 5000
17 | Reparing Malgasyaya Cementery Road | Udagama | RA |  |  | 485000 | DS -Buttala |  | 484410.47 | [10 empty] | 1 | 450
18 | Reparing Perahara Mawatha | Pettagamwela | RA |  |  | 970000 | DS -Buttala |  | 969387.8 | [10 empty] | 1 | 1500
19 | Reparing Karawilakotuwa Tank Road From Okkampitiya Road | Medagama | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 380
20 | Reparing Karawilakotuwa Nelumgama Road | Medagama | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 800
21 | Reparing Menadena Cemetary Road | Waguruwela | RA |  |  | 970000 | DS -Buttala |  | 970000 | [10 empty] | 1 | 450
22 | Developping 15 th Mile Post Madama Road | Koonketiya | RA |  |  | 485000 | DS -Buttala |  | 484910 | [10 empty] | 1 | 600
23 | Developping Udara Tank Road | Koonketiya | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 520
24 | Developping 19 th Mile Post Tempel Road | Goonaganara | RA |  |  | 970000 | DS -Buttala |  | 970000 | [10 empty] | 1 | 650
25 | Developping Akkara 100 Road | Mahagodayaya | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 480
26 | Developping Hospital Road From Weeragas Janction ( mr. Robert"s House By Road ) | Okkampitiya | RA |  |  | 582000 | DS -Buttala |  | 562222.54 | [10 empty] | 1 | 350
27 | Reparing The Road From Gurumadayaya To Rathwatte Mawatha | Gaminipura | RA |  |  | 485000 | DS -Buttala |  | 459647.48 | [10 empty] | 1 | 380
28 | Reparing Rathwatte Mawatha kiula road | Gaminipura | RA |  |  | 485000 | DS -Buttala |  | 482637 | [10 empty] | 1 | 250
29 | Reparing the road from maha Ela to Buruthagolla cemetary | Buruthagolla | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 350
30 | Repearing the by road from Puruwatta road to delgaswatta road | Pahalagama | RA |  |  | 582000 | DS -Buttala |  | 569694.18 | [10 empty] | 1 | 230
31 | Repearing tempel road galpeella road | Galtammandiya | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 250
32 | Repearing sooriyagaswatta road | Galtammandiya | RA |  |  | 388000 | DS -Buttala |  | 388000 | [10 empty] | 1 | 450
33 | Repering cannal road from 80 land | Ulugala | RA |  |  | 485000 | DS -Buttala |  | 474986 | [10 empty] | 1 | 650
34 | Repearing 7 th cannal road | Ulugala | RA |  |  | 485000 | DS -Buttala |  | 485000 | [10 empty] | 1 | 430
35 | Repearing ulugala minipuragama combine road | Minipuragama | RA |  |  | 582000 | DS -Buttala |  | 965040.72 | [10 empty] | 1 | 240
36 | Repearing sama mawatha | Maligavila | RA |  |  | 582000 | DS -Buttala |  | 582000 | [10 empty] | 1 | 650
37 | Developping chandramadurarama temple | Yatiyallathota | RC |  |  | 194000 | DS -Buttala |  | 194000 | [10 empty] | 1 | 800
38 | Developping block 15/16 rajamaha viharaya | Rahathangama | RC |  |  | 194000 | DS -Buttala |  | 194000 | [10 empty] | 1 | 600
39 | Developping dambeyaya temple | Buruthagolla | RC |  |  | 194000 | DS -Buttala |  | 194000 | [10 empty] | 1 | 700
40 | Developping Peraketiya Bubula Aranya road | Udaarawa | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 550
41 | Developping Amunalanda Block 2 Road | Horabokka | RA |  |  | 776000 | DS -Buttala | [10 empty] | 1 |  |  | 480
42 | Developping The Pelwatta Passara Road near the 16th maile post Kudaoya 7th maile post road Road | Pelwatta | RA |  |  | 776000 | DS -Buttala | [12 empty] | 1 | 1500
43 | Developping Elakandiya Road | Kukurampola | RA |  |  | 776000 | DS -Buttala | [9 empty] | 1 |  |  |  | 800
44 | Developping Biock 6 Thalakolawewa Road | Kumaragama | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 450
45 | Developping Biock 12/14 Cemetary Road | Rahathangama | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 550
46 | Developping rest of Walimadayaya Village Kudaoya Nersury Road | Kumarapura | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 700
47 | Developping Walugolla mada Road | Yatiyallathota | RA |  |  | 776000 | DS -Buttala |  | 771684.48 | [10 empty] | 1 | 600
48 | Developping rest of Galgodayaya Road | Mahasenpura | RA |  |  | 776000 | DS -Buttala | [10 empty] | 1 |  |  | 250
49 | Developping the by road inf ront of the Wasantha Service center of Burutha road Road | Weheragala | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 150
50 | Developping the Harigalagama Road | Unawatuna | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 700
51 | Developping the Yudaganawa Janapada Mahanaga Road | Puhulkotuwa | RA |  |  | 776000 | DS -Buttala | [12 empty] | 1 | 600
52 | Developping the Samuradhi Mawatha from Halmillaara Sunils house to Yudagana Road | Yudaganawa | RA |  |  | 776000 | DS -Buttala | [12 empty] | 1 | 250
53 | Developping the road near the Rajakandiya Mr M.L karunarathanas Coceat Work Shop | Dicyaya | RA |  |  | 776000 | DS -Buttala |  | 774972.5 | [10 empty] | 1 | 300
54 | Developping Bandaranayaka Road | Udagama | RA |  |  | 776000 | DS -Buttala | [7 empty] | 1 | [5 empty] | 1500
55 | Developping rest of Perahara Mawatha | Pettagamwela | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 1000
56 | Concreating Happoruwa temple road | Medagama | RA |  |  | 776000 | DS -Buttala |  | 768060.61 | [10 empty] | 1 | 800
57 | Developping Deyyanewela road | Waguruwela | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 600
58 | Developping near the 19 th Mile Post Mathara Traders Menik River Road | Koonketiya | RA |  |  | 776000 | DS -Buttala | [9 empty] | 1 |  |  |  | 540
59 | Developping 19 th Mile Post Cemetary Road | Goonaganara | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 480
60 | Developping Gangeyaya tank road (Akkara100 road) D.M Sisilas house road | Mahagodayaya | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 320
61 | Developping the Kaduruwelena and Weeragashandiya Connecting Road | Okkampitiya | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 500
62 | Developping the road from Batukotuwa main road to Galkanda Arannya senasanaya | Gaminipura | RA |  |  | 776000 | DS -Buttala |  | 747648.19 | [10 empty] | 1 | 360
63 | Developping the road from cemerary to Dammbeyaya mada raod | Buruthagolla | RA |  |  | 776000 | DS -Buttala |  | 774296.06 | [10 empty] | 1 | 600
64 | Developping the road from Pinthaliya Junction to Athwel palama raod | Pahalagama | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 500
65 | Developping the road from 17 th junction to Samagipura raod | Galtammandiya | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 470
66 | Developping Sadahatissa Mawataha Mr Jayatissas house to Pre School road | Ulugala | RA |  |  | 776000 | DS -Buttala | [9 empty] | 1 |  |  |  | 500
67 | Developping the road from Boo tree to main raod 87 kadaya | Minipuragama | RA |  |  | 776000 | DS -Buttala |  | 776000 | [10 empty] | 1 | 450
68 | Repairing the road from Dammepitiya to Niyadella | Maligawila | RA |  |  | 776000 | DS -Buttala |  | 774142.5 | [10 empty] | 1 | 900
69 | W.M CHAMARA WEERASINGHA | Udaarawa | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
70 | R.M NANDAWATHI | Horabokka | HD |  |  | 300000 | DS -Buttala | [9 empty] | 1
71 | D.M ARUNA SAMPATH | Pelwatta | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
72 | S.G.JAYATHISSA | Kukurampola | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
73 | W.M.P.D.SUDEERA LAKSMAN | Kumaragama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
74 | R.M.CHANDRANI NISHSHANKA | Rahathangama | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
75 | R.M.RAJARATHNA | Kumarapura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
76 | D.M.CHAMINDA PUSHPA KUMARA | Yatiyallathota | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
77 | W.M. DHARMASENA | Mahasenpura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
78 | H.M ARIYAWANSA | Weheragala | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
79 | K.D PRIYANTHA KUMARAGE | Unawatuna | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
80 | R.L CHANDARKANTHI | Puhulkotuwa | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
81 | U.G KAMANI PADMALATHA | Yudaganawa | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
82 | J.M .P NILANI JYASINGHA | Dicyaya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
83 | W.A.K CHAMINDA | Udagama | HD |  |  | 300000 | DS -Buttala |  | 300000 | [10 empty] | 1
84 | P.K RANJITH | Pettagamwela | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
85 | W.A SUMITH JANAKA | Medagama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
86 | R.M.HEENBANDA | Waguruwela | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
87 | W.T.R GAMINI ABESIGHA | Koonketiya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
88 | L.SEELAWATHI | Goonaganara | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
89 | K.B.R DINGIRIBANDA | Mahagodayaya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
90 | B.M AJITH KUMARA | Okkampitiya | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
91 | R.M BANDARA MENIKA | Gaminipura | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
92 | R.M TITUS SOORIYABANDARA | Buruthagolla | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
93 | R.M NANDAWATHI | Pahalagama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
94 | R.M KALUM PADMASIRI | Galtammandiya | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
95 | R.M SUNIL RATHNAYAKA | Ulugala | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
96 | E.M SENAVIRATHNA | Minipuragama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
97 | I.G PIYASENA | Maligawila | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
98 | K.M GUNATHILAKA | Udaarawa | HD |  |  | 300000 | DS -Buttala | [9 empty] | 1
99 | R.M.NANDAWATHI | Horabokka | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
100 | PEMAWATHI MATHAGAWEERA | Pelwatta | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
101 | T.M.SURANGA | Kukurampola | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
102 | T.M.NISHANTHA | Kumaragama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
103 | W.T.R SAMAN | Rahathangama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
104 | W.M DHARMADASA | Kumarapura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
105 | R.M.PIYADASA | Yatiyallathota | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
106 | EBRAHIM MAIMOONACHCHI | Mahasenpura | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
107 | R.M.KUSUMAWATHI | Weheragala | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
108 | S.D.CHANDRIKA | Unawatuna | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
109 | M.G.MIHIDUPALA | Puhulkotuwa | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
110 | S.A.SAJITH SALINDA | Yudaganawa | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
111 | K.M PEMAWATHI | Dicyaya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
112 | H.A.SAMAN THILAKAPALA | Udagama | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
113 | S.A.DAMMIKA | Pettagamwela | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
114 | M.A.SAMANTH KUMARA | Medagama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [5 empty] | 1
115 | K.W.ABESINHA | Waguruwela | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
116 | R.M.SIRSWARDANA | Koonketiya | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
117 | B.M PUSHPAKUMARA | Goonaganara | HD |  |  | 300000 | DS -Buttala | [8 empty] | 1
118 | W.D SUJITH KUMARA | Mahagodayaya | HD |  |  | 300000 | DS -Buttala | [8 empty] | 1
119 | D.M.SUJEEWA BANDARA | Okkampitiya | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
120 | R.M.RATHNAYAKA | Gaminipura | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
121 | R.M.SUDUBANDARA | Buruthagolla | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
122 | R.M.APPUHAMI | Pahalagama | HD |  |  | 300000 | DS -Buttala |  | 300000 | [10 empty] | 1
123 | R.M.GUNAPALA | Galtammandiya | HD |  |  | 300000 | DS -Buttala |  | 220000 | [9 empty] | 1
124 | R.M.SUNIL RATHNAYAKE | Ulugala | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
125 | T.M.JAYANTHA SRINATH | Minipuragama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
126 | S.VIJITHA KUMARA | Maligawila | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
127 | Divelopping Peraketiya Budugala Arannya Road | Udaarawa | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
128 | DiveloppingMurungawatta Block 02 Road | Horabokka | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
129 | Divelopping Wijaya Road in Buttala Wellawaya Road Starting near the 7th mile post | Pelwatta | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
130 | Divelopping Udawewa Road Up to Devala kotasa | Kukurampola | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
131 | Divelopping Miniyanagala road with Culvert | Kumaragama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
132 | Divelopping nera R.G Jaysenas house to 20 Village Boodiya road | Rahathangama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
133 | Divelopping near the Manumsewa Janapda irrigation cannal road with culvert | Kumarapura | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
134 | Divelopping the road from Burutha road to Burathapara Gama | Yatiyallathota | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
135 | Divelopping the Katagalara by road in Mullekumbura 6th mila post | Mahasenpura | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
136 | Divelopping rest of Weheragala gammana road with spreaddig interlock blocls | Weheragala | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
137 | Divelopping left road near the Unawatuna Ambakolawewa road Mr Elaberts kadaya | Unawatuna | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
138 | Divelopping the road near the Puhulkotuwa Pahala Mr W.M Wijesiris house | Puhulkotuwa | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
139 | Divelopping the Boodiya road by road from Uydaganawa Temple road near Samithi Shalawa | Yudaganawa | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
140 | Divelopping the rest of Andampahuwa road | Dicyaya | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
141 | Divelopping the road spreaddig interlock blocls from Udagama temple road to Pasal Mawatha Cannal road. | Udagama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
142 | Divelopping the Buttala Pettagamweala Wimalathunga mawatha spreaddig interlock blocls | Pettagamwela | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
143 | DiveloppingOkkampitiya road Karawilakotuwa wewa road spreaddig interlock blocls | Medagama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
144 | Divelopping 16th mile Sagini Circle Road | Koonketiya | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
145 | Divelopping Kumbukgasara wewa Road | Goonaganara | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
146 | Divelopping from Moramandiya to Waliara Road | Mahagodayaya | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
147 | Divelopping Okkampitiya Kaduruwalena(Katugaha house) Road | Okkampitiya | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
148 | Divelopping Katuwamada By road near Mr W.M Somapalas house road with culvert | Gaminipura | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
149 | Divelopping the road near the Boogas Handiya Habassa road Dharmasenas house up to Small cemetary road R.M Gunawardhanas house | Buruthagolla | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
150 | Divelopping from Buttala Gedara to Gadolbamma road | Pahalagama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
151 | Divelopping Galtammndiya pahala Aparekka rice mill road | Galtammandiya | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
152 | Divelopping Maligavila mada road near 92 Mr. Kiriwanthes hous | Ulugala | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
153 | Divelopping from Minipuragama Karuwalagasdowa ara Mr. Samanthas house Road to Mr Siripalas house road | Minipuragama | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
154 | Divelopping from71 Mr Jayas land to Palukapitiya tank road | Maligawila | RA |  |  | 776000 | DS -Buttala |  |  |  |  | 1
155 | K.M Sumithra Kumari ,Duwa ,Udaarawa, Uva Palwaththa. | Udaarawa | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
156 | H.M Sampath Kumara,Manampitiya,Uva Palwaththa. | Horabokka | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
157 | W.G Nishantha Lakshman,Wawewela pahala ,6 mile post, Uva Palwaththa. | Pelwatta | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
158 | B.V.Vjayathilaka,Edurugalayaya,Kukurampola, Uva Palwaththa. | Kukurampola | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
159 | A.A.Duleka Lakmali, Janawasa 04, Dewale kotasa, Kumaragama. | Kumaragama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
160 | K.H Jagath, Block 9, Pelwatta Suger Com., Buttala | Rahathangama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
161 | H.M Karunarathna, Walimadayaya, Kukurampola,Uva Palwaththa. | Kumarapura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
162 | R.M Nadeeka Sadamali,Bathalakothuwa Handiya,Buttala | Yatiyallathota | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
163 | H.M Ghanawathi, Mullekubura,6 mile post,Uva Palwaththa. | Mahasenpura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
164 | S.M Darmapala,Burutha road,Buttala. | Weheragala | HD |  |  | 300000 | DS -Buttala |  | 130000 | [8 empty] | 1
165 | R.D Piyal SamaraKoon, 94 /B,Priwena Road, Palugasmada, Unawatuna, Buttala. | Unawatuna | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
166 | H.M Dayani Herath, Wel widana niwasa,Puhulkotuwa, Buttala | Puhulkotuwa | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
167 | S.A Chandralatha, Pellewela,Udaganawa,Buttala | Yudaganawa | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
168 | K.M Upali Chandrasena, Bandaranayak Mawataha, Malgasyaya, Buttala. | Dicyaya | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
169 | R.W.V Upul Priyankara; 11 mile post, Monaragala Road, Buttala. | Udagama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
170 | G.W.Ruwinika Madushani, 1/7, Okkampitiya Road, Buttala | Pettagamwela | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
171 | R.M PEMATHILAKA | Medagama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
172 | D.M. Gunapala, Kandeyaya, Samddi Mawatha, Waguruwela, Buttala. | Waguruwela | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
173 | A.D. Danushka Sandaruwan, 18 mile post, Raja Mawatha, Buttala. | Koonketiya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
174 | D.M. Heenmanika, 19 mile post, Raja Mawatha, Buttala. | Goonaganara | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
175 | D.M. Kusumawathi, Gageyaya road, Mahagodayaya, Kukurampola. | Mahagodayaya | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
176 | D.M. Dilan Laksiri, Kandiyaya, Okkampitiya. | Okkampitiya | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
177 | B.K. Janakasena, Gaminipura, 3 mile post, Okkampitiya. | Gaminipura | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
178 | H.G.P UPUL LAKMAL | Buruthagolla | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
179 | W.M. Gunathilaka, Siyabalagas waththa, Pahala gama, Okkampitiya. | Pahalagama | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
180 | T.R. Anura Srathchandrea, Gal peella, Okkampitiya. | Galtammandiya | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
181 | H.B.M.Gunarathna, No 7/3, Siya mawatha, Maligawila. | Ulugala | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
182 | R.M. Karunarathna, No 57, Minipuragama, Maligawila. | Minipuragama | HD |  |  | 300000 | DS -Buttala | [7 empty] | 1
183 | D.M. Suriyasena, Ransili wawa, Rathriwawa, Maligawila. | Maligawila | HD |  |  | 300000 | DS -Buttala |  | 50000 | [7 empty] | 1
Total | [5 empty] | 92545000 |  |  | 43278450.01 |  | 0 | 28 | 0 | 0 | 31 | 2 | 40 | 9 | 9 | 64 | 46460 | 0
* Projects should be categorized for following sectors |  |  | ** Physical progress | [17 empty] | 183
RA- Rural Access |  |  | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  | B - For Constructions : B-1- Estimates Approved & Bid Documents Prepared, B-2- Quotation / Bid called, B-3- Quotation / Bid Received , B-4- Contract Awarded
SF- Sanitory Facility |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimate prepared
PG- Play Ground |  |  | C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
LCD - Livelihood and Capacity Development |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
EP- Environmental Programme |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
TD- Tourism Development
RC- Religious Center Development
HD- Housing Development
SW- Social Welfare

## Sinhala
අමාත්‍යංශය :- ජාතික ප්‍රතිපත්ති හා ආර්ථික කටයුතු අමාත්‍යාංශය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | ක්ෂේත්‍රය | ව්‍යාපෘතිය | ග්‍රාම නිලධාරි වසම | වෙන්කළ මුදල (රු.ශ) | ඇස්තමේන්තු මුදල කර්මාන්ත ව්‍යාපෘති සඳහා (රු.ශ) | මාර්ග මීටර් | කොන්ත්‍රාත් කරු | භෞතික ප්‍රගතිය 2019.09.03 | [9 empty] | වියදම රු. | ප්‍රතිලාභීන් සංඛ්‍යාව
[8 empty] | A | B | B | B | B | 11%-25% | 26%-50% | 51%-75% | 76%-99% | 100%
[9 empty] | ඇස්තමෙන්තු අනුමත කිරීම/ ලිපිගොනු සකසා ඇත | ටෙන්ඩර්/ මිල ගණන් කැඳවා ඇත. | ටෙන්ඩර්/ මිල ගණන් ලැබී ඇත. | කොන්ත්‍රාත් පිරිනමා ඇත.
1 | ග්‍රාමීය මාර්ග | දුව හා පේරකැටිය සම්බන්ධ වන මාර්ගය (කුඩා පාලම සමඟ) සංවර්ධනය කිරිම | උඩඅරාව | 582000 | [12 empty] | 1 | 582000 | 600
2 | ග්‍රාමීය මාර්ග | උනාවටුන හොරබොක්ක මාර්ගය සංවර්ධනය කිරිම | හොරබොක්ක | 485000 | [12 empty] | 1 | 485000 | 780
3 | ග්‍රාමීය මාර්ග | පස්සර මාර්ගයේ සිට වැවේවෙල මැද මාර්ගය සංවර්ධනය කිරිම | පැල්වත්ත | 485000 | [12 empty] | 1 | 485000 | 1400
4 | ග්‍රාමීය මාර්ග | කුකුළුවා විහාරස්ථාන මාර්ගය සංවර්ධනය කිරීම | කුකුරම්පොළ | 582000 | [12 empty] | 1 | 582000 | 2500
5 | ග්‍රාමීය මාර්ග | ජනාවාස 4 දේවාල කොටස පාසල් මාර්ගය සංවර්ධනය කිරිම | කුමාරගම | 582000 | [12 empty] | 1 | 582000 | 560
6 | ග්‍රාමීය මාර්ග | පොල පිටිය මාර්ගය ජනාවාස 9/11 ප්‍රතිසංස්කරණය කිරීම | රහතන්ගම | 582000 | [12 empty] | 1 | 582000 | 480
7 | ග්‍රාමීය මාර්ග | වැලිමඩයාය ගම්මානයේ ප්‍රජාශාලාවේ සිට වැලිමඩයාය ගම්මානය අසලින් වැලිමඩයාය දේවාලය අසලින් කුඩාඔය තවාන අසලට යන මාර්ගය සංවර්ධනය කිරිම | කුමාරපුර | 582000 | [12 empty] | 1 | 582000 | 530
8 | ග්‍රාමීය මාර්ග | බතලකොටුව සිට මුංකොටුව මාර්ගය ප්‍රතිසංස්කරණය කිරිම | යටියල්ලාතොට | 582000 | [12 empty] | 1 | 582000 | 650
9 | ග්‍රාමීය මාර්ග | ගල්ගොඩයාය මාර්ගය සංවර්ධනය කිරිම | මහසෙන්පුර | 485000 | [12 empty] | 1 | 485000 | 350
10 | ග්‍රාමීය මාර්ග | සිනි සමාගමේ නාම පුවරුව අසල සිට ගැමුනුගම මාර්ගය ප්‍රතිසංස්කරණ්‍ය කිරිම | වෙහෙරගල | 970000 | [12 empty] | 1 | 963709.48 | 850
11 | ග්‍රාමීය මාර්ග | උනාවටුන අඹකොලවැව අතුරු මාර්ගය ප්‍රතිසංස්කරණය කිරිම | උනාවටුන | 582000 | [12 empty] | 1 | 582000 | 900
12 | ග්‍රාමීය මාර්ග | ඇල්ලවලට යන මාර්ගය ප්‍රතිසංස්කරණය කිරිම | පුහුල්කොටුව | 485000 | [12 empty] | 1 | 485000 | 250
13 | ග්‍රාමීය මාර්ග | පුබුදු මාවත ප්‍රධාන මාර්ගය ඉතිරි කොටස සංවර්ධනය කිරිම | පුහුල්කොටුව | 485000 | [12 empty] | 1 | 485000 | 150
14 | ග්‍රාමීය මාර්ග | යුදගනාව පිල්ලෙවෙල පාලම අසල සිට ඇල දක්වා මාර්ගය ප්‍රතිසංස්කරණය කිරිම | යුදගනාව | 970000 | [12 empty] | 1 | 970000 | 1500
15 | ග්‍රාමීය මාර්ග | අන්දම්පහුව මාර්ගය කැටගල් අල්ලා සංවර්ධණය කිරිම | දික්යාය | 970000 | [12 empty] | 1 | 970000 | 400
16 | ග්‍රාමීය මාර්ග | උඩගම විහාරස්ථානයට පිවිසෙන මාර්ගයේ පාලම පුළුල් කර සංවර්ධනය කිරිම | උඩගම | 485000 | [12 empty] | 1 | 480000 | 5000
17 | ග්‍රාමීය මාර්ග | මල්ගස්යාය සුසානභූමිය මාර්ගය ප්‍රතිසංස්කරණය කිරිම | උඩගම | 485000 | [12 empty] | 1 | 484410.47 | 450
18 | ග්‍රාමීය මාර්ග | පෙරහැර මාවත ප්‍රතිසංස්කරණය කිරීම | පෙට්ටගම්වෙල | 970000 | [12 empty] | 1 | 969387.8 | 1500
19 | ග්‍රාමීය මාර්ග | ඔක්කම්පිටිය මාර්ගයේ සිට කරවිල කොටුව වැව දක්වා මාර්ගය ප්‍රතිසංස්කරණය කිරීම | මැදගම | 485000 | [12 empty] | 1 | 485000 | 380
20 | ග්‍රාමීය මාර්ග | කරවිලකොටුව - නෙලුම්ගම මාර්ගය ප්‍රතිසංස්කරණය කිරිම | මැදගම | 485000 | [12 empty] | 1 | 485000 | 800
21 | ග්‍රාමීය මාර්ග | මේනාදන සුසානභුමිය පාර ප්‍රතිසංස්කරණය කිරීම | වගුරුවෙල | 970000 | [12 empty] | 1 | 970000 | 450
22 | ග්‍රාමීය මාර්ග | 15 කණුව මඩම පාර සංවර්ධනය කිරිම | කෝන්කැටිය | 485000 | [12 empty] | 1 | 484910 | 600
23 | ග්‍රාමීය මාර්ග | උදාර වැව පාර සංවර්ධනය කිරිම | කෝන්කැටිය | 485000 | [12 empty] | 1 | 485000 | 520
24 | ග්‍රාමීය මාර්ග | 19 කණුව වලගම්බා පන්සල පාර සංවර්ධණය කිරිම | ගෝනගංආර | 970000 | [12 empty] | 1 | 970000 | 650
25 | ග්‍රාමීය මාර්ග | අක්කර 100 මාර්ගය සංවර්ධනය කිරිම | මහගොඩයාය | 582000 | [12 empty] | 1 | 582000 | 480
26 | ග්‍රාමීය මාර්ග | වීරගස් හන්දියේ සිට රෝහල දක්වා මාර්ගයේ රොබට් මුදලාලිගේ නිවස පාර අතුරු මාර්ගය සංවර්ධනය කිරිම | ඔක්කම්පිටිය | 582000 | [12 empty] | 1 | 562222.54 | 350
27 | ග්‍රාමීය මාර්ග | ගුරුමඩයාය සිට රත්වත්ත මාවත දක්වා අතුරු මාර්ගය ප්‍රතිසංස්කරණය කිරිම | ගාමිණිපුර | 485000 | [12 empty] | 1 | 459647.48 | 380
28 | ග්‍රාමීය මාර්ග | රත්වත්ත මාවතේ කිවුල මාර්ගය ප්‍රතිසංස්කරණය | ගාමිණිපුර | 485000 | [12 empty] | 1 | 482637 | 250
29 | ග්‍රාමීය මාර්ග | මහඇල සිට බුරුතගොල්ල සුසානභුමිය දක්වා මාර්ගය ප්‍රතිසංස්කරණය කිරීම | බුරුතගොල්ල | 582000 | [12 empty] | 1 | 582000 | 350
30 | ග්‍රාමීය මාර්ග | පුරුවත්ත පාර සිට දෙල්ගස්වත්ත පාර සම්බන්ධ වන අතුරු මාර්ගය ප්‍රතිසංස්කරනය කිරිම. | පහලගම | 582000 | [12 empty] | 1 | 569694.18 | 230
31 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය පන්සල පාර ගල්පීල්ල මාර්ගය ප්‍රතිසංස්කරණය කිරිම | ගල්ටැම්මණ්ඩිය | 582000 | [12 empty] | 1 | 582000 | 250
32 | ග්‍රාමීය මාර්ග | සූරියගස්වත්ත මාර්ගය ප්‍රතිසංස්කරණය කිරිම | ගල්ටැම්මණ්ඩිය | 388000 | [12 empty] | 1 | 388000 | 450
33 | ග්‍රාමීය මාර්ග | 80 ඉඩම අසල සිට ඇල දක්වා මාර්ගය ප්‍රතිසංස්කරණය කිරිම | උළුගල | 485000 | [12 empty] | 1 | 474986 | 650
34 | ග්‍රාමීය මාර්ග | 7 ඇල, ඇල මාර්ගය ප්‍රතිසංස්කරණය කිරිම | උළුගල | 485000 | [12 empty] | 1 | 485000 | 430
35 | ග්‍රාමීය මාර්ග | උළුගල මිණිපුරගම සම්බන්ධ වන මාර්ගය ප්‍රතිසංස්කරණය කිරිම. | මිණිපුරගම | 582000 | [12 empty] | 1 | 965040.72 | 240
36 | ග්‍රාමීය මාර්ග | සාම මාවත ප්‍රතිසංස්කරණය කිරිම. | මාලිගාවිල | 582000 | [12 empty] | 1 | 582000 | 650
37 | විහාරස්ථාන සංවර්ධනය | චන්දුමදුරාරමය විහාරස්ථානයේ සංවර්ධන කටයුතු සඳහා | යටියල්ලාතොට | 194000 | [12 empty] | 1 | 194000 | 800
38 | විහාරස්ථාන සංවර්ධනය | ජනාවාස 15/16 රහතන්ගම රජමහ විහාරස්ථානයේ සංවර්ධන කටයුතු සඳහා | රහතන්ගම | 194000 | [12 empty] | 1 | 194000 | 600
39 | විහාරස්ථාන සංවර්ධනය | දඹේයාය විහාරස්ථානය සංවර්ධනය සඳහා | බුරුතගොල්ල | 194000 | [12 empty] | 1 | 194000 | 700
40 | ග්‍රාමීය මාර්ග | පේරකැටිය මාර්ගයේ බුබුල ආරණ්‍ය මාර්ගය සංවර්ධනය කිරිම. | උඩඅරාව | 776000 |  |  | එක්සත් ගැමුණු ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 550
41 | ග්‍රාමීය මාර්ග | අමුණලන්ද පාර ජනාවාස 02 මාර්ගය සංවර්ධනය කිරිම. | හොරබොක්ක | 776000 |  |  | හොරබොක්ක අමුණ ගොවි සංවිධානය | [7 empty] | 1 |  |  |  | 480
42 | ග්‍රාමීය මාර්ග | පැල්වත්ත පස්සර මාර්ගයේ 16 කනුව අසලින් දකුණු පසට ඇති කුඩාඔය 7 කනුව දක්වා ඇති මාර්ගය සංවර්ධනය කිරිම. | පැල්වත්ත | 776000 |  |  | පිඹුරාලන්ද ගොවි සංවිධානය | [9 empty] | 1 |  | 1500
43 | ග්‍රාමීය මාර්ග | ඇලකණ්ඩිය පාර සංවර්ධනය කිරිම. | කුකුරම්පොළ | 776000 |  |  | දඹේවැව ගොවි සංවිධානය | [6 empty] | 1 |  |  |  |  | 800
44 | ග්‍රාමීය මාර්ග | ජනාවාස 06 හරහා තලාකොළවැව මාර්ගය | කුමාරගම | 776000 |  |  | පැකුම් ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 450
45 | ග්‍රාමීය මාර්ග | ජනාවාස 12/14 සුසාන භූමිය දක්වා මාර්ගය සංවර්ධනය කිරීම | රහතන්ගම | 776000 | [12 empty] | 1 | 776000 | 550
46 | ග්‍රාමීය මාර්ග | වැලිමඩයාය ගම්මානයේ ප්‍රජාශාලාව අසල සිට වැලිමඩයාය දේවාලය අසලින් කුඩාඔය තවාන අසලට යන මාර්ගයේ ඉතිරි කොටස සංවර්ධනය කිරිම. | කුමාරපුර | 776000 |  |  | දඹේවැව ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 700
47 | ග්‍රාමීය මාර්ග | වලුගොල්ල මැද මාර්ගය සංවර්ධනය කිරීම | යටියල්ලාතොට | 776000 |  |  | යටියල්ලාතොට ගොවි සංවිධානය | [9 empty] | 1 | 771684.48 | 600
48 | ග්‍රාමීය මාර්ග | ගල්ගොඩයාය මාර්ගයේ ඉතිරි කොටස සංවර්ධනය කිරීම | මහසෙන්පුර | 776000 | [10 empty] | 1 |  |  |  | 250
49 | ග්‍රාමීය මාර්ග | බුරුත පාර වසන්ත සර්විස් ආයතනය ඉදිරියෙන් යන අතුරු මාර්ගය සංවර්ධනය කිරීම | වෙහෙරගල | 776000 |  |  | නිකවැව ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 150
50 | ග්‍රාමීය මාර්ග | උනාවටුන හරිගලගම මාර්ගය සංවර්ධනය කිරීම | උනාවටුන | 776000 | [12 empty] | 1 | 776000 | 700
51 | ග්‍රාමීය මාර්ග | යුදගනාව ජනපදය මහානාග මාවත සංවර්ධනය කිරීම | පුහුල්කොටුව | 776000 | [12 empty] | 1 |  | 600
52 | ග්‍රාමීය මාර්ග | හල්ම්ල්ලආර සුනිල් මයාගේ නිවස අසල සිට යුදගනාව මාර්ගය දක්වා සමෘද්ධි මාවත සංවර්ධනය කිරීම | යුදගනාව | 776000 |  |  | රන්තරු වැඩිහිටි සමිතිය | [9 empty] | 1 |  | 250
53 | ග්‍රාමීය මාර්ග | රාජකණ්ඩිය එම්.එල්.කරුණාරත්න මහතාගේ කොන්ක්‍රීට් වැඩපල අසල පාර සංවර්ධනය | දික්යාය | 776000 |  |  | රාජකණ්ඩිය ගොවි සංවිධානය | [9 empty] | 1 | 774972.5 | 300
54 | ග්‍රාමීය මාර්ග | වී ගබඩාව පාර ( බණ්ඩාරනායක මාවත) ප්‍රතිසංස්කරණය කිරීම | උඩගම | 776000 | [7 empty] | 1 | [6 empty] | 1500
55 | ග්‍රාමීය මාර්ග | පෙරහැර මාවත ඉතිරි කොටස සංවර්ධනය කිරීම | පෙට්ටගම්වෙල | 776000 |  |  | පැකුම් ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 1000
56 | ග්‍රාමීය මාර්ග | හත්පෝරුව පන්සල පාර කොන්ක්‍රීට් කිරීම | මැදගම | 776000 |  |  | මැදගම ඇල ගොවි සංවිධානය | [9 empty] | 1 | 768060.61 | 800
57 | ග්‍රාමීය මාර්ග | දෙයියන්නේවෙල මාර්ගය සංවර්ධනය කිරිම | වගුරුවෙල | 776000 | [12 empty] | 1 | 776000 | 600
58 | ග්‍රාමීය මාර්ග | 17 කණුව මාතර වෙළද සැල අසලින් මැණික් ගග දක්වා මාර්ගය සංවර්ණය කිරිම | කෝන්කැටිය | 776000 |  |  | තිඹිරිගස්ආරගම ගොවි සංවිධානය | [6 empty] | 1 |  |  |  |  | 540
59 | ග්‍රාමීය මාර්ග | 17 කණුව පොදු සුසාන භූමියට යන මාර්ගය සංවර්ධනය කිරීම | ගෝනගංආර | 776000 |  |  | කුඹුක්ගස්ආරගම ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 480
60 | ග්‍රාමීය මාර්ග | ගගේයාය වැව පාර (අක්කර 100 පාර) ඩි.එම්.සිසිල මහතාගේ නිවස අසල මාර්ගය සංවර්ධනය කිරිම. | මහගොඩයාය | 776000 | [12 empty] | 1 | 776000 | 320
61 | ග්‍රාමීය මාර්ග | කදුරුවැලැන සහ වීරගස්හන්දිය සම්බන්ධ වන මාර්ගය සංවර්ධනය කිරීම | ඔක්කම්පිටිය | 776000 |  |  | දාගොබඇල ගොවි සංවිධනාවය | [9 empty] | 1 | 776000 | 500
62 | ග්‍රාමීය මාර්ග | බටුකොටුව ප්‍රධාන මාර්ගයේ සිට ගල්කන්ද ආරණ්‍ය සේනාසනය දක්වා මාර්ගය සංවර්ධනය කිරිම | ගාමිණිපුර | 776000 |  |  | ගාමිණිපුර එක්සත් ගොවි සංවිධානය | [9 empty] | 1 | 747648.19 | 360
63 | ග්‍රාමීය මාර්ග | සුසාන භූමියේ සිට දඹේයාය මැද මාර්ගය සංවර්ධනය කිරීම | බුරුතගොල්ල | 776000 |  |  | ජන පුබුදු ග්‍රාම සංවර්ධන සමිතිය | [9 empty] | 1 | 774296.06 | 600
64 | ග්‍රාමීය මාර්ග | පිංතාලිය හන්දිය සිට අත්වැල් පාලම මාර්ගය දක්වා මාර්ගය සංවර්ධනය කිරිම | පහලගම | 776000 |  |  | පහලගම කාන්තා ග්‍රාම සංවර්ධන සමිතාය | [9 empty] | 1 | 776000 | 500
65 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය 17 හංදිය සිට සමගිපුර දක්වා මැද පාර සංවර්ධනය කිරිම | ගල්ටැම්මණ්ඩිය | 776000 |  |  | ශක්ති ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 470
66 | ග්‍රාමීය මාර්ග | සද්ධාතිස්ස මාවතේ ජයසිංහ මහතාගේ නිවස අසල සිට පෙර පාසල දක්වා මාර්ගය සංවර්ධනය කිරීස | උළුගල | 776000 | [9 empty] | 1 |  |  |  |  | 500
67 | ග්‍රාමීය මාර්ග | මිණිපුරගම බෝගහ අසල සිට ප්‍රධාන මාර්ගය 87 කඩය දක්වා මාර්ගය සංවර්ධනය කිරිම | මිණිපුරගම | 776000 |  |  | නැගෙනහිර ගොවි සංවිධානය | [9 empty] | 1 | 776000 | 450
68 | ග්‍රාමීය මාර්ග | මාලිගාවිල දඹේපිටිය සිට නියදැල්ල දක්වා මාර්ගය ප්‍රතිසංස්කරණය කිරීම | මාලිගාවිල | 776000 | [12 empty] | 1 | 774142.5 | 900
69 | නිවාස(අලුත්වැඩියා) | ඩබ්.එම්.චාමර වීරසිංහ මහතා, , උඩඅරාව,ඌව පැල්වත්ත | උඩඅරාව | 300000 | [7 empty] | 1
70 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.නන්දාවතී මිය, පාසල ඉදිරිපිට, හොරබොක්ක, ඌව පැල්වත්ත | හොරබොක්ක | 300000 | [9 empty] | 1
71 | නිවාස(අලුත්වැඩියා) | ඩී.එම්.අරුණ සම්පත් මහතා, බුබුල , ගොමආර,ඌව පැල්වත්ත | පැල්වත්ත | 300000 | [7 empty] | 1
72 | නිවාස(අලුත්වැඩියා) | එස්.ජී.ජයතිස්ස මහතා, කොවිල් පැලැස්ස,කුකුරම්පොල | කුකුරම්පොළ | 300000 | [10 empty] | 1 |  |  | 130000
73 | නිවාස(අලුත්වැඩියා) | ඩබ්.එම්.පී.ඩී. සුධීර ලක්ෂ්මන් මහතාජනාවාස 04, රජයේ.කොටස,කුමාරගම | කුමාරගම | 300000 | [9 empty] | 1 |  |  |  | 50000
74 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.චන්ද්‍රානි නිශ්ශංක මියඅංක 67,ජනාවාස 10, පැල්වත්ත සිනි සමාගම | රහතන්ගම | 300000 | [10 empty] | 1 |  |  | 130000
75 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.රාජරත්න මහතා, මිනුම්සේවා ජනපදය, කුකුරම්පොල | කුමාරපුර | 300000 | [9 empty] | 1 |  |  |  | 50000
76 | නිවාස(අලුත්වැඩියා) | ඩි.එම්.චමින්ද පුෂ්ප කුමාර මහතා, පරණ බුරුත පාර, බුත්තල | යටියල්ලාතොට | 300000 | [11 empty] | 1 |  | 220000
77 | නිවාස(අලුත්වැඩියා) | ඩබ්.එම්.ධර්මසේනන මහතා, ගෝනගොඩැල්ල පාර,ඌව පැල්වත්ත | මහසෙන්පුර | 300000 | [9 empty] | 1 |  |  |  | 50000
78 | නිවාස(අලුත්වැඩියා) | එච්.එම්.ආරියවංශ මහතා, ගැමුණුගම,බුරුතපාර,බුත්තල | වෙහෙරගල | 300000 | [9 empty] | 1 |  |  |  | 50000
79 | නිවාස(අලුත්වැඩියා) | කේ.ඩී.ප්‍රියන්ත කුමාරගේ මහතා, 68/1, හරලගම,උනාවටුන, බුත්තල | උනාවටුන | 300000 | [9 empty] | 1 |  |  |  | 50000
80 | නිවාස(අලුත්වැඩියා) | අආර්.එල්.චන්ද්‍රකාන්ති මිය, 31/ඒ, “ශ්‍රියාවාස, පුහුල්කොටුව, බුත්තල | පුහුල්කොටුව | 300000 | [7 empty] | 1
81 | නිවාස(අලුත්වැඩියා) | යූ.ජී.කමනි පද්මලතා මිය, අක්කර 100, යුදගනාව, බුත්තල | යුදගනාව | 300000 | [9 empty] | 1 |  |  |  | 50000
82 | නිවාස(අලුත්වැඩියා) | ජේ.එම්.ප්‍රියංකා නිලානි ජයසිංහ මිය, අන්දම්පහුව, දික්යාය, බුත්තල | දික්යාය | 300000 | [9 empty] | 1 |  |  |  | 50000
83 | නිවාස(අලුත්වැඩියා) | ඩබ්.ඒ.කේ.චමින්ද මහතා, අමුණපාර, උඩගම, බුත්තල | උඩගම | 300000 | [12 empty] | 1 | 300000
84 | නිවාස(අලුත්වැඩියා) | පීකේ රංජිත් මහතා, 7/1, ඔක්කම්පිටිය පාර, බුත්තල | පෙට්ටගම්වෙල | 300000 | [9 empty] | 1 |  |  |  | 50000
85 | නිවාස(අලුත්වැඩියා) | ඩබ්.ඒ.සුමිත් ජානක මහතා, කරවිලකොටුව, මැදගම, බුත්තල | මැදගම | 300000 | [9 empty] | 1 |  |  |  | 50000
86 | නිවාස(අලුත්වැඩියා) | ආර.එම් හීංබණ්ඩා මහතා, දඹගස්වත්ත, වගුරුවෙල, බුත්තල | වගුරුවෙල | 300000 | [11 empty] | 1 |  | 220000
87 | නිවාස(අලුත්වැඩියා) | ඩබ්.ටී.ආර්.ගාමිණි අබේසිංහ මහතා, 17 කනුව,රජමාවත,බුත්තල | කෝන්කැටිය | 300000 | [9 empty] | 1 |  |  |  | 50000
88 | නිවාස(අලුත්වැඩියා) | එල්.සීලවතී මිය, 21 කනුව, රජමාවත, බුත්තල | ගෝනගංආර | 300000 | [9 empty] | 1 |  |  |  | 50000
89 | නිවාස(අලුත්වැඩියා) | කේ.බී.ආර්.ඩිංගිරිබණ්ඩා මහතා, මහගොඩයාය, බුත්තල | මහගොඩයාය | 300000 | [9 empty] | 1 |  |  |  | 50000
90 | නිවාස(අලුත්වැඩියා) | බී.එම්.අජිත් කුමාර මහතා, ගල්කොටුව, කණ්ඩියාය, ඔක්කම්පිටිය | ඔක්කම්පිටිය | 300000 | [7 empty] | 1
91 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.බණ්ඩාර මැණිකා මිය, ගාමිණිපුර, ඔක්කම්පිටිය | ගාමිණිපුර | 300000 | [10 empty] | 1 |  |  | 130000
92 | නිවාස(අලුත්වැඩියා) | ආර්.ඩී සුපුන් උදයංග මහතා, වැව පෙදෙස, බුරුතගොල්ල, ඔක්කම්පිටිය | බුරුතගොල්ල | 300000 | [7 empty] | 1
93 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.නන්දාවති මිය, සියඹලාගස්වත්ත, පහලගම, ඔක්කම්පිටිය | පහලගම | 300000 | [7 empty] | 1
94 | නිවාස(අලුත්වැඩියා) | ආර්.එම්.කැළුම් පද්මසිරි මහතා, සමගිපුර,ගල්ටැම්මණ්ඩිය, ඔක්කම්පිටිය | ගල්ටැම්මණ්ඩිය | 300000 | [7 empty] | 1
95 | නිවාස(අලුත්වැඩියා) | කේ.එම්.ප්‍රියන්ත කෝණාර මහතා, නො.44, ජනපදය, ඔක්කම්පිටිය | උළුගල | 300000 | [11 empty] | 1 |  | 220000
96 | නිවාස(අලුත්වැඩියා) | ඊ.එම්.සෙනෙවිරත්න මහතා, අංක 64 බාරේ, මිණිපුරගම, මාලිගාවිල | මිණිපුරගම | 300000 | [9 empty] | 1 |  |  |  | 50000
97 | නිවාස(අලුත්වැඩියා) | අයි.පී.පියසේන මහතා, ඩී/26/1, සද්ධාතිස්ස මාවත, මාලිගාවිල. | මාලිගාවිල | 300000 | [7 empty] | 1
98 | නව නිවාස ඉදිකිරීම | කේ. එම් ගුණතිලක | උඩඅරාව | 300000 | [9 empty] | 1
99 | නව නිවාස ඉදිකිරීම | ජේ.කේ. එම් සුමේධ ඩයස්, හොරෙබාක්ක, ඌව පැල්වත්ත | හොරබොක්ක | 300000 | [7 empty] | 1
100 | නව නිවාස ඉදිකිරීම | පේමාවතී මතගවීර මිය, පස්සර පාර, ඌව පැල්වත්ත | පැල්වත්ත | 300000 | [7 empty] | 1
101 | නව නිවාස ඉදිකිරීම | ඩබ්.එම්.ධර්මදාස මහතා,ඇලබඩයාය, කුකරම්පොළ,උ්ව පැල්වත්ත | කුකුරම්පොළ | 300000 | [9 empty] | 1 |  |  |  | 50000
102 | නව නිවාස ඉදිකිරීම | ටි.එම්.නිශාන්ත, ජනාවාස 06,තලාෙකාළවැව, ඌව පැල්වත්ත | කුමාරගම | 300000 | [7 empty] | 1
103 | නව නිවාස ඉදිකිරීම | ඩබ් .ටී. ආර් සමන් බණ්ඩාර, ජනාවාස 15,රහතන්ගම, බුත්තල | රහතන්ගම | 300000 | [9 empty] | 1 |  |  |  | 50000
104 | නව නිවාස ඉදිකිරීම | කේ.එච්.සුරේෂ් මධුශංක, මිණුම්සේවා ජනපදය, කුකුරම්පොල.ඌව පැල්වත්ත | කුමාරපුර | 300000 | [9 empty] | 1 |  |  |  | 50000
105 | නව නිවාස ඉදිකිරීම | ආර්.එම්.පියදාස, අංක 59, මුංකොටුව, යටියල්ලාතොට | යටියල්ලාතොට | 300000 | [11 empty] | 1 |  | 220000
106 | නව නිවාස ඉදිකිරීම | ඊබ්‍රහිම් මයිමූනාච්චි, 7 කණුව, ඌව පැල්වත්ත | මහසෙන්පුර | 300000 | [7 empty] | 1
107 | නව නිවාස ඉදිකිරීම | ආර්.එම්.කුසුමාවති, වෙහරගල මාවත, කුඩාඔය, බුත්තල | වෙහෙරගල | 300000 | [9 empty] | 1 |  |  |  | 50000
108 | නව නිවාස ඉදිකිරීම | එස්.ඩි.චන්ද්‍රිකා, අංක 71 /බී, උනාවටුන, බුත්තල | උනාවටුන | 300000 | [9 empty] | 1 |  |  |  | 50000
109 | නව නිවාස ඉදිකිරීම | එම්.ජී.මිහිදුපාල, වඩුමඩුව අසල, පුහුල්කොටුව, බුත්තල | පුහුල්කොටුව | 300000 | [11 empty] | 1 |  | 220000
110 | නව නිවාස ඉදිකිරීම | එස්.ඒ.සජිත් සාලින්ද, පීල්ලෙවෙල, යුදගනාව, බුත්තල | යුදගනාව | 300000 | [9 empty] | 1 |  |  |  | 50000
111 | නව නිවාස ඉදිකිරීම | කේ.එම්.පේමාවති මිය, අන්දම්පහුව, දික්යාය, බුත්තල | දික්යාය | 300000 | [9 empty] | 1 |  |  |  | 50000
112 | නව නිවාස ඉදිකිරීම | එච්.ඒ.සමන් තිලකපාල, පන්සල පාර, උඩගම, බුත්තල | උඩගම | 300000 | [11 empty] | 1 |  | 220000
113 | නව නිවාස ඉදිකිරීම | එස්.ඒ.ධම්මික, 01 කණුව, ඔක්කම්පිටිය පාර, බුත්තල | පෙට්ටගම්වෙල | 300000 | [10 empty] | 1 |  |  | 130000
114 | නව නිවාස ඉදිකිරීම | එම්.ඒ.සමන්ත කුමාර, කරවිලකොටුව,මැදගම,බුත්තල | මැදගම | 300000 | [7 empty] | 1 | [5 empty] | 50000
115 | නව නිවාස ඉදිකිරීම | කේ.ඩබ්.අබේසිංහ, කොලොන්ගස්වත්ත,මැදගම,බුත්තල | වගුරුවෙල | 300000 | [10 empty] | 1 |  |  | 130000
116 | නව නිවාස ඉදිකිරීම | ආර්.එම්.සිරිවර්ධන, 16 කණුව, රජ මාවත, බුත්තල | කෝන්කැටිය | 300000 | [10 empty] | 1 |  |  | 130000
117 | නව නිවාස ඉදිකිරීම | බී.එම්.පුෂ්ප කුමාර, 20 කණුව, රජ මාවත, බුත්තල | ගෝනගංආර | 300000 | [8 empty] | 1
118 | නව නිවාස ඉදිකිරීම | ඩබ්.ඩී.සුජිත් කුමාර මහතා, නව ගම්මානය පාර,මහගොඩයාය, බුත්තල | මහගොඩයාය | 300000 | [8 empty] | 1
119 | නව නිවාස ඉදිකිරීම | ඩී.එම්.සුජීව බණ්ඩාර, ගල්කොටුව, කණ්ඩියාය, ඔක්කම්පිටිය | ඔක්කම්පිටිය | 300000 | [11 empty] | 1 |  | 220000
120 | නව නිවාස ඉදිකිරීම | ආර්.එම්.රත්නායක, බටුකොටුව, ගාමිණිපුර, ඔක්කම්පිටිය | ගාමිණිපුර | 300000 | [7 empty] | 1
121 | නව නිවාස ඉදිකිරීම | ආර්.එම්.සුදුබණ්ඩා, දොඹගහෙවල ගෙදර, වැව පෙදස, ඔක්කම්පිටිය | බුරුතගොල්ල | 300000 | [11 empty] | 1 |  | 220000
122 | නව නිවාස ඉදිකිරීම | ආර්.එම්. අප්පුහාමි, නියදගල,පහලගම | පහලගම | 300000 | [12 empty] | 1 | 300000
123 | නව නිවාස ඉදිකිරීම | ආර්.එම්.ගුණපාල, ගල්ටැම්මණ්ඩිය, ඔක්කම්පිටිය | ගල්ටැම්මණ්ඩිය | 300000 | [11 empty] | 1 |  | 220000
124 | නව නිවාස ඉදිකිරීම | ආර්.එම්.සුනිල් රත්නායක අංක 112, ජනපදය, ඔක්කම්පිටිය | උළුගල | 300000 | [9 empty] | 1 |  |  |  | 50000
125 | නව නිවාස ඉදිකිරීම | ටී.එම්.ජයන්ත ශ්‍රිනාත්, තිස්ස පාර, මිණිපරගම, මාලිගාවිල | මිණිපුරගම | 300000 | [7 empty] | 1
126 | නව නිවාස ඉදිකිරීම | එස්.විජිත කුමාර, ඩී - 91/1, නියදැල්ල පාර, මාලිගාවිල | මාලිගාවිල | 300000 | [9 empty] | 1 |  |  |  | 50000
127 | ග්‍රාමීය මාර්ග | පේරකැටිය බුදුඟල ආරණ්‍ය මාර්ගය සංවර්ධනය කිරිම. | උඩඅරාව | 776000 |  |  |  |  | 1
128 | ග්‍රාමීය මාර්ග | මුරුංගාවත්ත ජනාවාස 02 මාර්ගය සංවර්ධනය කිරිම. | හොරබොක්ක | 776000 |  |  |  |  | 1
129 | ග්‍රාමීය මාර්ග | බුත්තල වැල්ලවාය මාර්ගයේ 7 කණුව පොදු සුසාන භූමිය අසලින් ආරම්භ වන විජය පාර සංවර්ධනය කිරිම. | පැල්වත්ත | 776000 |  |  |  |  | 1
130 | ග්‍රාමීය මාර්ග | උඩවැව පාර දේවාලේ කොටස දක්වා මාර්ගය සංවර්ධනය කිරිම | කුකුරම්පොළ | 776000 |  |  |  |  | 1
131 | ග්‍රාමීය මාර්ග | මිනියානාගල පාර බෝක්කුව ඉඳිකර සංවර්ධනය කිරිම. | කුමාරගම | 776000 |  |  |  |  | 1
132 | ග්‍රාමීය මාර්ග | ආර්.ජී.ජයසේන මයාගේ නිවස අසල සිට 20 ගම්මානයේ බෝධිය අසල දක්වා මාර්ගය සංවර්ධනය කිරිම. | රහතන්ගම | 776000 |  |  |  |  | 1
133 | ග්‍රාමීය මාර්ග | මැණුම් සේවා ජනපදයේ වැව් බැම්ම අසලින් ගම්මානය හරහා වාරිමාර්ග ඇලට යන පාර බෝක්කුව සමඟ පාර පුළුල් කර සංවර්ධනය කිරිම. | කුමාරපුර | 776000 |  |  |  |  | 1
134 | ග්‍රාමීය මාර්ග | බුරුතපාර සිට බුරුතපාර ගම දක්වා මාර්ගය සංවර්ධනය කිරිම. | යටියල්ලාතොට | 776000 |  |  |  |  | 1
135 | ග්‍රාමීය මාර්ග | මුල්ලේ කුඹුර 06 කණුව මාර්ගයේ කැටගල්ආර අතුරු මාර්ගය සංවර්ධනය කිරිම. | මහසෙන්පුර | 776000 |  |  |  |  | 1
136 | ග්‍රාමීය මාර්ග | බුරුත පාරේ සිට වෙහෙරගල ගම්මානයට පිවිසෙන මාර්ගයේ ඉතිරි කොටස කැටගල් අල්ලා සංවර්ධනය කිරිම. | වෙහෙරගල | 776000 |  |  |  |  | 1
137 | ග්‍රාමීය මාර්ග | උනාවටුන අඹකොලවැව මාර්ග‍යේඇල්බට් මයාගේ කඩය අසලින් වම් පසට තිබෙන මාර්ගය සංවර්ධනය කිරිම. | උනාවටුන | 776000 |  |  |  |  | 1
138 | ග්‍රාමීය මාර්ග | පුහුල් කොටුව පහළ කොටස ඩබ්. එම්.විජේසිරිමයාගේ නිවස අසල මාර්ගය සංවර්ධනය කිරිම. | පුහුල්කොටුව | 776000 |  |  |  |  | 1
139 | ග්‍රාමීය මාර්ග | යුදගනාව පන්සල පාර සිට සමිති ශාලාව අසලින් බෝධිය පාර අතුරු මාර්ගය සංවර්ධනය කිරිම. | යුදගනාව | 776000 |  |  |  |  | 1
140 | ග්‍රාමීය මාර්ග | අන්දම්පහුව මාර්ගය ඉතිරි කොටස සංවර්ධනය කිරිම. | දික්යාය | 776000 |  |  |  |  | 1
141 | ග්‍රාමීය මාර්ග | උඩගම පන්සල මාර්ගයේ සිට පාසල් මාවත දක්වා ඇළ මාර්ගය කැටගල් අල්ලා සංවර්ධනය කිරිම. | උඩගම | 776000 |  |  |  |  | 1
142 | ග්‍රාමීය මාර්ග | බුත්තල පෙට්ටගම්වෙල විමලතුංග මාවත කැටගල් අල්ලා සංවර්ධනය කිරිම. | පෙට්ටගම්වෙල | 776000 |  |  |  |  | 1
143 | ග්‍රාමීය මාර්ග | ඔක්කම්පිටිය මාර්ගයේ කරවිල කොටුව වැව දක්වා මාර්ගයේ මැද කොටස කැටගල් අල්ලා සංවර්ධනය කිරිම. | මැදගම | 776000 |  |  |  |  | 1
144 | ග්‍රාමීය මාර්ග | 16 කණුව සාගිනි වට රවුම මාර්ගය සංවර්ධනය කිරිම. | කෝන්කැටිය | 776000 |  |  |  |  | 1
145 | ග්‍රාමීය මාර්ග | කුඹුක්ගස් ආර වැවට යන මාර්ගය සංවර්ධනය කිරිම. | ගෝනගංආර | 776000 |  |  |  |  | 1
146 | ග්‍රාමීය මාර්ග | මොරමණ්ඩිය සිට වැලිආර මාවත සංවර්ධනය කිරිම. | මහගොඩයාය | 776000 |  |  |  |  | 1
147 | ග්‍රාමීය මාර්ග | ඔක්කම්පිටිය කදුරුවැලෑන (කටුගහ නිවස) මාර්ගය සංවර්ධනය කිරිම. | ඔක්කම්පිටිය | 776000 |  |  |  |  | 1
148 | ග්‍රාමීය මාර්ග | කටුවාමඩ අතුරු මාර්ගයේ ඩබ්.එම්.සෝමපාල මයාගේ නිවස අසලින් දිවෙන මාර්ගයේ සපත්තු පාලම ඉදිකර සංවර්ධනය කිරිම. | ගාමිණිපුර | 776000 |  |  |  |  | 1
149 | ග්‍රාමීය මාර්ග | බෝගස් හන්දිය -හැබ්බැස්ස මාර්ගයේ ධර්මසේන මයාගේ කඩය අසලින් ආරම්භවන කුඩා සුසාන භුමිය මාර්ගය ආර්.එම් ගුණවර්ධන මුදලාලිගේ නිවස අසල දක්වා මාර්ගය සංවර්ධනය කිරිම. | බුරුතගොල්ල | 776000 |  |  |  |  | 1
150 | ග්‍රාමීය මාර්ග | බුත්තල ගෙදර සිට ගඩොල් බැම්ම දක්වා මාර්ගය සංවර්ධනය කිරිම. | පහලගම | 776000 |  |  |  |  | 1
151 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය පහළ මැද පාර අපරැක්ක හල් මෝල අසලින් ආරම්භ වන මාර්ගය සංවර්ධනය කිරිම | ගල්ටැම්මණ්ඩිය | 776000 |  |  |  |  | 1
152 | ග්‍රාමීය මාර්ග | 92 කිරිවන්තේ මයාගේ නිවස අසල සිට මාලිගාවිල මැද පාර සංවර්ධනය කිරිම. | උළුගල | 776000 |  |  |  |  | 1
153 | ග්‍රාමීය මාර්ග | මිණිපුරගම කරුවලගස්දෝව ආර පාර 121 සමන්ත මයාගේ නිවස අසල සිට සිරිපාල මයාගේ නිවස අසල දක්වා මාර්ගය සංවර්ධනය කිරිම. | මිණිපුරගම | 776000 |  |  |  |  | 1
154 | ග්‍රාමීය මාර්ග | 71 ජායා මයාගේ ඉඩම අසල සිට පළුකපිටිය වැව දක්වා මාර්ගය සංවර්ධනය කිරිම. | මාලිගාවිල | 776000 |  |  |  |  | 1
155 | නිවාස ඉදිකිරීම | කේ.එම් සුමිත්‍රා කුමාරි මිය. දුව, උඩඅරාව, ඌව පැල්වත්ත | උඩඅරාව | 300000 | [9 empty] | 1 |  |  |  | 50000
156 | නිවාස ඉදිකිරීම | එච්.එම්.සම්පත් කුමාර මයා, මනම්පිටිය, හොර බොක්ක,ඌව පැල්වත්ත. | හොරබොක්ක | 300000 | [7 empty] | 1
157 | නිවාස ඉදිකිරීම | ඩබ්.ජී නිශාන්ත ලක්ෂ්මන් මයා, වැවේවෙල පහල, 6 කණුව, ඌව පැල්වත්ත. | පැල්වත්ත | 300000 | [7 empty] | 1
158 | නිවාස ඉදිකිරීම | බී.වී ජයතිලක මයා, එඩරුගලයාය,කුකුරම්පොළ,ඌව පැල්වත්ත. | කුකුරම්පොළ | 300000 | [9 empty] | 1 |  |  |  | 50000
159 | නිවාස ඉදිකිරීම | ඒ.ඒ දුලිකා ලක්මාලි මිය, ජනාවාස 04 දේවාලේ කොටස, කුමාරගම. | කුමාරගම | 300000 | [7 empty] | 1
160 | නිවාස ඉදිකිරීම | කේ.එච්.ජගත් මයා, ජනාවාස 9,ලං.සී.ස., පැල්වත්ත | රහතන්ගම | 300000 | [9 empty] | 1 |  |  |  | 50000
161 | නිවාස ඉදිකිරීම | එච්.එම්.කරුණාරත්න මයා, වැලිමඩයාය, කුකුරම්පොල, ඌව පැල්වත්ත. | කුමාරපුර | 300000 | [9 empty] | 1 |  |  |  | 50000
162 | නිවාස ඉදිකිරීම | ආර්.එම් නදීකා සදමාලි මිය,බතල කොටුව හන්දිය, බුත්තල. | යටියල්ලාතොට | 300000 | [7 empty] | 1
163 | නිවාස ඉදිකිරීම | එච්,එම් ඥාණවති මිය, මුල්ලේ කුඹුර ,6 කණුව, ඌව පැල්වත්ත. | මහසෙන්පුර | 300000 | [9 empty] | 1 |  |  |  | 50000
164 | නිවාස ඉදිකිරීම | එස්.එම්.ධර්මපාල මයා, බුරුත පාර බුත්තල. | වෙහෙරගල | 300000 | [10 empty] | 1 |  |  | 130000
165 | නිවාස ඉදිකිරීම | ආර්.ඩී. පියල් සමරකෝන් මයා, 94 /බී, පිරිවෙන පාර, පළුගස්මඩ, උණාවටුන, බුත්තල. | උනාවටුන | 300000 | [7 empty] | 1
166 | නිවාස ඉදිකිරීම | එච්.එම් දයානි හේරත් මිය,වෙල්විදාන නිවස, පුහුල්කොටුව,බුත්තල. | පුහුල්කොටුව | 300000 | [7 empty] | 1
167 | නිවාස ඉදිකිරීම | එස්.ඒ චන්ද්‍රලතා මිය, පීල්ලේවෙල, යුදගනාව, බුත්තල | යුදගනාව | 300000 | [7 empty] | 1
168 | නිවාස ඉදිකිරීම | කේ.එම් උපාලි චන්ද්‍රසෝම මයා, බණ්ඩාරනායක මාවත.මල්ගස්යාය, බුත්තල. | දික්යාය | 300000 | [7 empty] | 1
169 | නිවාස ඉදිකිරීම | ආර්.ඩබ්.වී උපුල් ප්‍රියංකර මයා, 11 කණුව, මොණරාගල පාර, බුත්තල. | උඩගම | 300000 | [9 empty] | 1 |  |  |  | 50000
170 | නිවාස ඉදිකිරීම | ජී.ඩබ්. රුවිනිකා මදුශානි මිය,1/7 ,ඔක්කම්පිටිය පාර, බුත්තල, | පෙට්ටගම්වෙල | 300000 | [9 empty] | 1 |  |  |  | 50000
171 | නිවාස ඉදිකිරීම | ආර්.එම් පේමතිලක. සමෘද්ධි හංදිය, රජමාවත, බුත්තල | මැදගම | 300000 | [7 empty] | 1
172 | නිවාස ඉදිකිරීම | ඩි.එම්.ගුණපාල මයා, කන්දේයාය, සමෘද්ධි මාවත, වගුරුවෙල,බුත්තල. | වගුරුවෙල | 300000 | [9 empty] | 1 |  |  |  | 50000
173 | නිවාස ඉදිකිරීම | ඒ.ඩී ධනුෂ්ක සඳරුවන් මයා, 18 කණුව ,රජමාවත, බුත්තල. | කෝන්කැටිය | 300000 | [9 empty] | 1 |  |  |  | 50000
174 | නිවාස ඉදිකිරීම | ඩී.එම්.හීන් මැණිකා මිය, 19 කණුව, රජ මාවත, බුත්තල. | ගෝනගංආර | 300000 | [7 empty] | 1
175 | නිවාස ඉදිකිරීම | ඩී.එම්. කුසුමාවති මිය, ගඟේ යාය පාර ,මහගොඩයාය, කුකුරම්පොල | මහගොඩයාය | 300000 | [7 empty] | 1
176 | නිවාස ඉදිකිරීම | ඩී.එම්.ඩිලාන් ලක්සිරි මයා, කණ්ඩියාය, ඔක්කම්පිටිය. | ඔක්කම්පිටිය | 300000 | [9 empty] | 1 |  |  |  | 50000
177 | නිවාස ඉදිකිරීම | බී.කේ ජනක සේන මයා,ගාමිණිපුර, 3 කණුව, ඔක්කම්පිටිය. | ගාමිණිපුර | 300000 | [9 empty] | 1 |  |  |  | 50000
178 | නිවාස ඉදිකිරීම | එච්.ජීපී උපුල් ලක්මාල්, වැව පෙදෙස . ඔක්කම්පිටිය. | බුරුතගොල්ල | 300000 | [7 empty] | 1
179 | නිවාස ඉදිකිරීම | ඩබ්.එම්. ගුණතිලක මයා, සියඹලාගස්වත්ත, පහළගම, ඔක්කම්පිටිය. | පහලගම | 300000 | [9 empty] | 1 |  |  |  | 50000
180 | නිවාස ඉදිකිරීම | ටී.ආර් අනුර සරත් චන්ද්‍ර මයා, ගල් පීල්ල, සමගිපුර, ගල්ටැම් මණ්ඩිය,ඔක්කම්පිටිය. | ගල්ටැම්මණ්ඩිය | 300000 | [7 empty] | 1
181 | නිවාස ඉදිකිරීම | එච්. බී.එම්. ගුණරත්න මයා, අංක7/3 සිය මාවත, මාලිගාවිල | උළුගල | 300000 | [7 empty] | 1
182 | නිවාස ඉදිකිරීම | ආර්.එම්.කරුණාරත්න මයා, අංක57, මිණිපුරගම, මාලිගාවිල. | මිණිපුරගම | 300000 | [7 empty] | 1
183 | නිවාස ඉදිකිරීම | ඩී.එම් සුරියසේන මයා, රන්සිලි වැව,රාත්‍රිවැව, මාලිගාවිල. | මාලිගාවිල | 300000 | [9 empty] | 1 |  |  |  | 50000
උප එකතුව |  |  |  | 92545000 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 31 | 2 | 40 | 9 | 9 | 64 | 43278450.01 | 46460
පරිපාලන.වි.
මුළු එකතුව
183
සියලු ඉදිකිරීම් ව්‍යාපෘති | [5 empty] | සියලු මිලදී ගැනීම් ව්‍යාපෘති
0% - 10% = ව්‍යාපෘතිය අනුමත කර, ප්‍රතිපාදන ලබා දි තිබීම/ඇස්තමේන්තු සකස් කර තිබිම | [5 empty] | 0% - 10% = ව්‍යාපෘතිය අනුමත කර, ප්‍රතිපාදන ලබා දි තිබීම
11% - 25% = ගිවිසුම්ගත වි ඉදිකිරිම් ආරම්භ කර තිබිම | [5 empty] | 11% - 25% = මිලදී ගන්නා භාණ්ඩ තීරණය කිරිම/මිලගණන් කැඳවීම/ගැණුම්කරු තීරණය කිරිම
26% - 50% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 26% සිට 50%ක වැඩ අවසන් කර තිබිම | [5 empty] | 26% - 50% = භාණ්ඩ ඇනුවුම් කිරිම/මිලදි ගැනීම
51% - 75% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 51% සිට 99%ක වැඩ අවසන් කර තිබිම | [5 empty] | 51% - 75% = මිලදී ගත් භාණ්ඩ ලේඛන ගත කිරිම/ගෙවීම් කිරිම
76% - 100% = ඉදිකිරිම් අවසන් කර ගෙවීම් සිදු කිරීම | [5 empty] | 76% - 100% = අදාල ආයතන/ප්‍රතිලාභීන් වෙත භාණ්ඩ ලබාදීම/ ගබඩාකර තැබීම