## Full Report
Annexure 01
Rural Infrastructure Development Programme (RIDP) - 2020
District wise Physical and Financial Progress as at 28.09.2020
Divisional Secretariat :-Buttala
No. | GN Divition | No. of Eligible GN Divisions | No. of Eligible GN Divisions | Projects * | [9 empty] | Allocation | [9 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  |  | Name of Project | Total categorized by Sectors * | [8 empty] | Approved Allocation (Rs. Mn) | Total Allocation Categorized by Sectors * (Rs. Mn.) | [8 empty] | A | B |  |  |  | C | D | E | F | G
[5 empty] | I | II | III | IV | V | VI | VII | VIII | IX |  | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Pettagamwela |  |  | Concreting Perahara Mawatha from Okkampitiya road | [9 empty] | 990000 | 990000 | [17 empty] | 1 | 990000 | bar: Total categorized by Sectors * I
2 | Gaminipura |  |  | Developping Balakotuwa Elamanayaya road | [9 empty] | 495000 | 495000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
3 | Gonaganara |  |  | Developping Kumbukgas ara road | [9 empty] | 495000 | 495000 | [17 empty] | 1 | 495000 | bar: Total categorized by Sectors * I
4 | Mahasenpura |  |  | Developping Katupothawewa Bathala wadiya road | [9 empty] | 495000 | 495000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
5 | Pettagamwela |  |  | Concreting rest of Okkampitiya road 2nd lane | [9 empty] | 495000 | 495000 | [17 empty] | 1 | 495000 | bar: Total categorized by Sectors * I
6 | Yudaganawa | 405 |  | Concreting Anicut road near S.A Weerasinghas house to ahead | [9 empty] | 495000 | 495000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
Total |  | 405 |  |  | Total categorized by Sectors * I: 6 | 3465000 | 3465000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 5 | 1980000 | 0
* Projects should be categorized for following sectors
| Circular code |  |  | Sector Name | [9 empty] | ** Physical progress
| I |  |  | Village Road, Culverts, Bridges, side Drinage etc | [9 empty] | A - Estimates are being / to be prepared
| II |  |  | Werehouse Facilities for Agricultureal Production | [9 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2 = Quotation / Bid called, B-3 = Quotation / Bid Received, B-4 = Contract Awarded
| III |  |  | Economic Centers including Weekly Faires, Small Shops | [9 empty] | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
| IV |  |  | Construction and renovation of Small Tanks, C anals, Anicuts, ponds and Agricultural Wells | [9 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
| V |  |  | Community Drinking Water Supply Projects | [9 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
| VI |  |  | Development/ Modernization of rural Health Centers and Providing Facilities | [9 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
| VII |  |  | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [9 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
| VIII |  |  | Providing for Prevention of Disasters for Human habitants from wild Animals | [9 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
| IX |  |  | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development

## Sinhala
ග්‍රාමීය යටිතල පහසුකම් සංවර්ධන වැඩසටහන - 2020
අමාත්‍යංශය :- ජාතික ප්‍රතිපත්ති හා ආර්ථික කටයුතු අමාත්‍යාංශය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | ක්ෂේත්‍රය | ග්‍රාම නිලධාරි වසම | ව්‍යාපෘතිය | වෙන්කළ මුදල (රු.ශ) | ගිවිසුම් කාලය | ඇස්තමේන්තු මුදල කර්මාන්ත ව්‍යාපෘති සඳහා (රු.ශ) | මාර්ග මීටර් | කොන්ත්‍රාත් කරු | භෞතික ප්‍රගතිය 2020.10.05 | [9 empty] | වියදම රු.
[9 empty] | A | B | B | B | B | 11%-25% | 26%-50% | 51%-75% | 76%-99% | 100%
[10 empty] | ඇස්තමෙන්තු අනුමත කිරීම/ ලිපිගොනු සකසා ඇත | ටෙන්ඩර්/ මිල ගණන් කැඳවා ඇත. | ටෙන්ඩර්/ මිල ගණන් ලැබී ඇත. | කොන්ත්‍රාත් පිරිනමා ඇත.
1 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | බුත්තල ඔක්කම්පිටිය මාර්ගයේ සිට පෙරහැර මාවතේ අබලන් වු කොටස සංවර්ධනය කර කොන්ක්‍රීට් කිරිම. | 990000 | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [12 empty] | 1 | 990000
2 | ග්‍රාමීය මාර්ග | ගාමිණිපුර | බටුකොටුව ඇලමානයාය මාර්ගය සංවර්ධනය කිරිම | 495000 | තල්විල ඇල ගොවි සංවිධානය | [12 empty] | 1
3 | ග්‍රාමීය මාර්ග | ගෝනගංආර | කුඹුක්ගස්ආර මාර්ගය සංවර්ධනය කිරීම | 495000 | ගොඩ ගොවි සංවිධානය - 20 කණුව | [12 empty] | 1 | 495000
4 | ග්‍රාමීය මාර්ග | මහසෙන්පුර | කටුපොතවැව බතල වාඩිය මාර්ගය සංවර්ධනය කිරීම | 495000 | සමගි ගොවි සංවිධානය - 20 කණුව | [12 empty] | 1
5 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | ඔක්කම්පිටිය පාර දෙවන පටුමග මාර්ගයේ ඉතිරි කොටස කොන්ක්‍රීට් කිරීම | 495000 | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [12 empty] | 1 | 495000
6 | ග්‍රාමීය මාර්ග | යුදගනාව | අමුණපාර එස්.ඒ.වීරසිංහ මහතාගේ නිවස අසල සිට ඉදිරියට ඇති මාර්ගය කොන්ක්‍රීට් කිරීම. | 495000 | යුදගනාව ග්‍රාමසංවර්ධන සමිතිය | [12 empty] | 1
මුළු එකතුව |  |  |  | 3465000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1980000 | 0
සියලු ඉදිකිරීම් ව්‍යාපෘති
0% - 10% = ව්‍යාපෘතිය අනුමත කර, ප්‍රතිපාදන ලබා දි තිබීම/ඇස්තමේන්තු සකස් කර තිබිම
11% - 25% = ගිවිසුම්ගත වි ඉදිකිරිම් ආරම්භ කර තිබිම
26% - 50% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 26% සිට 50%ක වැඩ අවසන් කර තිබිම
51% - 75% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 51% සිට 99%ක වැඩ අවසන් කර තිබිම
76% - 100% = ඉදිකිරිම් අවසන් කර ගෙවීම් සිදු කිරීම

## DS Summary
ග්‍රාමීය යටිතල පහසුකම් සංවර්ධන වැඩසටහන - 2020
අමාත්‍යංශය :- ජාතික ප්‍රතිපත්ති හා ආර්ථික කටයුතු අමාත්‍යාංශය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | භෞතික ප්‍රගතිය 2020.08.31 | ප්‍රමාණය
1 | මුළු ව්‍යාපෘති සංඛ්‍යාව | 6
2 | ඇස්තමෙන්තු සකස්කර ඇති ව්‍යාපෘති සංඛ්‍යාව | 0
3 | කොන්ත්‍රාත් පිරිනමා ඇති ව්‍යාපෘති සංඛ්‍යාව | 0
4 | 11 - 25% ක් වැඩ අවසන් | 0
5 | 26 - 50% ක් වැඩ අවසන් | 1
6 | 51 - 75% ක් වැඩ අවසන් | 0
7 | 76 - 99% ක් වැඩ අවසන් | 0
8 | 100% | 5
9 | සංශෝධනයට යොමුකර ඇති ව්‍යාපෘති සංඛ්‍යාව | 0
10 | වෙන් කළ මුදල | 3465000
11 | මෙතෙක් වියදම | 1980000