## Full Report
Annexure 01
Sapiri Gamak - People's Participatory Rural Development Programme- 2020
District wise Physical and Financial Progress as at 05.10.2020
Division Secretariat :- BUTTALA
No. | GN Divition | No. of Eligible GN Divisions | No. of Eligible GN Divisions | Projects * | [9 empty] | Allocation | [9 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  |  | Name of Project | Total categorized by Sectors * | [8 empty] | Approved Allocation (Rs. Mn) | Total Allocation Categorized by Sectors * (Rs. Mn.) | [8 empty] | A | B |  |  |  | C | D | E | F | G
[5 empty] | I | II | III | IV | V | VI | VII | VIII | IX |  | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Udaarawa | Udaarawa | Udaarawa | Laying interlock Concret blocks in Murungawatta road | [9 empty] | 1000000 | 1000000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
2 | Udaarawa | Udaarawa | Udaarawa | Construction the culvert of Peraketiya Bulgala road | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
3 | Udaarawa | Udaarawa | Udaarawa | Repairing the road with Laying interlock Concret blocks in Blok two road | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
4 | Horabokka | Horabokka | Horabokka | Constructing main gate and fence of Horabokka Heath Center | [9 empty] | 500000 | [5 empty] | 500000 | [7 empty] | 1 | bar: Total categorized by Sectors * VI
5 | Horabokka | Horabokka | Horabokka | Constructing the culvert of Demodarayaya road | [9 empty] | 500000 | 500000 | [9 empty] | 1 | bar: Total categorized by Sectors * I
6 | Horabokka | Horabokka | Horabokka | Graveling Kottagaslanda Road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
7 | Horabokka | Horabokka | Horabokka | Construction Manampitiya Demodarayaya Bridge | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
8 | Pelwatta | Pelwatta | Pelwatta | Graveling wewewelayaya Bogaha ela Road | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
9 | Pelwatta | Pelwatta | Pelwatta | Graveling the Block two Road | [9 empty] | 900000 | 900000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
10 | Pelwatta | Pelwatta | Pelwatta | Graveling the Pimburalanda Manampitiya by Road | [9 empty] | 600000 | 600000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
11 | Kukurampola | Kukurampola | Kukurampola | Concreting Kumarapotha Dewalakotasa road | [9 empty] | 1000000 | 1000000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
12 | Kukurampola | Kukurampola | Kukurampola | Repairing Nagasyaya Pitiya Road from Main road | [9 empty] | 1000000 | 1000000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
13 | Kumaragama | Kumaragama | Kumaragama | Developping Damage culavert in Devala Kotasa | [9 empty] | 2000000 | 2000000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
14 | Rahathangama | Rahathangama | Rahathangama | Developping Block 10 Temple road in | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
15 | Rahathangama |  |  | Fitting roof of Block 16 Pavilian | [9 empty] | 500000 | 500000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
16 | Rahathangama |  |  | Developping Block 14 village Road with Greveling | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
17 | Rahathangama |  |  | Developping Block 09 By Road with Greveling | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
18 | Kumarapura | Kumarapura | Kumarapura | Concreting Minumsewa janapadaya road to Kudaoya rever | [9 empty] | 1000000 | 1000000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
19 | Kumarapura | Kumarapura | Kumarapura | Concreting ahead rever road near Dewalaya | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
20 | Kumarapura | Kumarapura | Kumarapura | Concreting the road near Mr Buddadasas house ahead rever | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
21 | Yatiyallathota | Yatiyallathota | Yatiyallathota | Developing the road from Thangalla house to S. M Senavirathnas houe | [9 empty] | 1000000 | 1000000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
22 | Yatiyallathota | Yatiyallathota | Yatiyallathota | Developing the road from D.M Buddadasas house to Puwakpitiya tank | [9 empty] | 1000000 | 1000000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
23 | Mahasenpura | Mahasenpura | Mahasenpura | Grevelling Pahalawela Kukurampola road | [9 empty] | 500000 | 500000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
24 | Mahasenpura |  |  | Grevelling Bathalawadiya road | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
25 | Mahasenpura | Mahasenpura | Mahasenpura | Grevelling Mullekumbura by road Bandarawela wadiya road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
26 | Mahasenpura | Mahasenpura | Mahasenpura | Developing the Ranthilakas house road with Culvert | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
27 | Weheragala | Weheragala | Weheragala | Developing Weheragala Arannya road with tar | [9 empty] | 500000 | 500000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
28 | Weheragala | Weheragala | Weheragala | Concreting from Salani Pre School to temple road | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
29 | Weheragala | Weheragala | Weheragala | Concreting EDO Office road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
30 | Weheragala | Weheragala | Weheragala | Laying interlock Concret blocks in Ela Bunt road to Gemunugama road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
31 | Unawatuna | Unawatuna | Unawatuna | Grevelling Ambakolawewa bunt road upto yudaganawa road | [9 empty] | 1000000 | 1000000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
32 | Unawatuna | Unawatuna | Unawatuna | Concreting in rest of Sithumina kade road to Gemunugama road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
33 | Unawatuna | Unawatuna | Unawatuna | Laying interlock Concret blocks in rest of Temple middle road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
34 | Puhulkotuwa | Puhulkotuwa | Puhulkotuwa | Establish Water Filter near the Puhulkotuwa School | [9 empty] | 1000000 |  |  |  |  | 1000000 | [5 empty] | 1 | bar: Total categorized by Sectors * V
35 | Puhulkotuwa | Puhulkotuwa | Puhulkotuwa | Concreting from Sumangala Mawatha 48 house to 8th house road | [9 empty] | 1000000 | 1000000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
36 | Yudaganawa | Yudaganawa | Yudaganawa | Grevelling Bodiya road Deepas house to Amuna road | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
37 | Yudaganawa |  |  | Amuna road near Chandrikas house by road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
38 | Yudaganawa | Yudaganawa | Yudaganawa | Extending water suppling Akkara 100 Sunils house road | [9 empty] | 500000 |  |  |  |  | 500000 | [5 empty] | 1 | bar: Total categorized by Sectors * V
39 | Yudaganawa | Yudaganawa | Yudaganawa | Grevelling Walimadayaya Nishshankas house By road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
40 | Dicyaya | Dicyaya | Dicyaya | Developping Rajakandiya main road with culverts and dranage System | [9 empty] | 2000000 | 2000000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
41 | Udagama | Udagama | Udagama | Laying interlock Concret blocks in via rest of cemetory to Buttala Badalkumbura road | [9 empty] | 2000000 | 2000000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
42 | Pettagamwela | Pettagamwela | Pettagamwela | Developping Namandiya Viilage road with culvert | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
43 | Pettagamwela | Pettagamwela | Pettagamwela | Laying interlock Concret blocks in Perahara Mawatha Uda Mawatha | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
44 | Pettagamwela | Pettagamwela | Pettagamwela | Laying interlock Concret blocks in 2nd lane | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
45 | Pettagamwela | Pettagamwela | Pettagamwela | Laying interlock Concret blocks in rest of Pettagamwela watta road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
46 | Madagama | Madagama | Madagama | Developping Pitamulla Road from Rajapaksha Mawatha | [9 empty] | 500000 | 500000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
47 | Madagama | Madagama | Madagama | Developping from Deyyannewela junction to Aluthwela temple | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
48 | Madagama | Madagama | Madagama | Developping Galkoriya road with returning wall | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
49 | Madagama | Madagama | Madagama | Developping from 1st lane junction Galkoriya road with returning wall | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
50 | Waguruwela | Waguruwela | Waguruwela | Graveling the the road from Deyyannewela Boo tree to river | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
51 | Waguruwela | Waguruwela | Waguruwela | Developping the Kandeyaya road with a culvert | [9 empty] | 1000000 | 1000000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
52 | Waguruwela | Waguruwela | Waguruwela | Developping Dambagaskotuwa road | [9 empty] | 500000 | 500000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
53 | Konketiya | Konketiya | Konketiya | Graveling Alimanthala pahala road with culvert | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
54 | Konketiya |  |  | Graveling 17th mile post mr. Somas house road with culvert | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
55 | Konketiya |  |  | Repairing 16th mile post community center and construct a toilet | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
56 | Konketiya |  |  | Graveling Thammannara tank road with cosway | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
57 | Gonaganara | Gonaganara | Gonaganara | Graveling from Gonaganara Water tank up to Mr Anandas house road. | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
58 | Gonaganara | Gonaganara | Gonaganara | Graveling Diyakiritta Mr Jayaweeras house road. | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
59 | Gonaganara |  |  | Graveling near Mr Mahathuns house road. | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
60 | Gonaganara |  |  | Graveling near Mr Maheepalas house road with culvert | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
61 | Mahagodayaya | Mahagodayaya | Mahagodayaya | Graveling road in front of the Gangeyaya transformer and E.A Saraths house and Palathawana road M.M Sunils house road. | [9 empty] | 1000000 | 1000000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
62 | Mahagodayaya | Mahagodayaya | Mahagodayaya | Graveling Devagiri Arannya road | [9 empty] | 1000000 | 1000000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
63 | Okkampitiya | Okkampitiya | Okkampitiya | Laying interlock Concret blocks in Kaduruwelena road with reterning wall | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
64 | Okkampitiya | Okkampitiya | Okkampitiya | Concreting Kandiyaya Cemetary road up to Arannya | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
65 | Okkampitiya | Okkampitiya | Okkampitiya | Developping Kandiyaya road with Culvert | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
66 | Okkampitiya | Okkampitiya | Okkampitiya | Concreting Bandayaya Ilukpitiya road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
67 | Gaminipura | Gaminipura | Gaminipura | Concreting Kanda Village road from 2nd mile post P.G Siriya lathas Kade | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
68 | Gaminipura | Gaminipura | Gaminipura | Concreting Elamanayaya road near B.K Wimalasenas house with drainage system | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
69 | Gaminipura | Gaminipura | Gaminipura | Concreting near Batukotuwa Acmans house Kande village road with drainage system | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
70 | Gaminipura | Gaminipura | Gaminipura | Concreting near Rathwatta Mawatha 1st lane H.M Shanthas road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
71 | Buruthagolla | Buruthagolla | Buruthagolla | Concreting road from Nimals kadaya to Wijayas house (Watawagodakanda road) | [9 empty] | 750000 | 750000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
72 | Buruthagolla | Buruthagolla | Buruthagolla | Laying interlock Concret blocks from M. wimalasenas house to Tikiriralas house | [9 empty] | 750000 | 750000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
73 | Buruthagolla | Buruthagolla | Buruthagolla | Laying interlock Concret blocks from Jhothi Mudalalis Kadaya to Nanda Teachers house | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
74 | Pahalagama | Pahalagama | Pahalagama | Concreting Gadol Bemma road fro Buttala Gedara to river | [9 empty] | 1000000 | 1000000 | [16 empty] | 1 | bar: Total categorized by Sectors * I
75 | Pahalagama | Pahalagama | Pahalagama | Graveling the near the Dambeyaya School road pu to river | [9 empty] | 500000 | 500000 | [17 empty] | 1 | 495000 | bar: Total categorized by Sectors * I
76 | Pahalagama | Pahalagama | Pahalagama | Graveling near R.M Jayasinghas house Aluthgedara road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
77 | Galtammandiya | Galtammandiya | Galtammandiya | Graveling near R.M Jayasinghas house Aluthgedara road | [9 empty] | 500000 | 500000 | [15 empty] | 1 | bar: Total categorized by Sectors * I
78 | Galtammandiya | Galtammandiya | Galtammandiya | Graveling the Badulu Gammana road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
79 | Galtammandiya | Galtammandiya | Galtammandiya | Concreting Sooriyagaswatta road near Health Center | [9 empty] | 500000 | 500000 | [14 empty] | 1 | bar: Total categorized by Sectors * I
80 | Galtammandiya | Galtammandiya | Galtammandiya | Graveling Galketa ara road with near pirith kade Culvert | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
81 | Ulugala | Ulugala | Ulugala | Graveling the road from 6th Cannal to Galtammandiya ara with 6th cannal bridge | [9 empty] | 1000000 | 1000000 | [12 empty] | 1 | bar: Total categorized by Sectors * I
82 | Ulugala | Ulugala | Ulugala | Graveling the road from 1st Cannal to 9th Cannal | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
83 | Ulugala | Ulugala | Ulugala | Graveling Siyamawatha road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | 495000 | bar: Total categorized by Sectors * I
84 | Minipuragama | Minipuragama | Minipuragama | Developping the road from Boo tree to Isurugama Beralimankada | [9 empty] | 1000000 | 1000000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
85 | Minipuragama | Minipuragama | Minipuragama | Laying interlock Concret blocks in Karuwalagasdowa house road | [9 empty] | 500000 | 500000 | [13 empty] | 1 | bar: Total categorized by Sectors * I
86 | Minipuragama | Minipuragama | Minipuragama | Graveling tak road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | 494747.52 | bar: Total categorized by Sectors * I
87 | Maligavila | Maligavila | Maligavila | Repairing Niyadella anicut road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
88 | Maligavila | Maligavila | Maligavila | Repairing Raththriwewa Junction to Boogas junction road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
89 | Maligavila | Maligavila | Maligavila | Repairing near Sama mawatha D.M Jayasekeras house and near Sunils house to Health Center road | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
90 | Maligavila | Maligavila | Maligavila | Repairing near Premasiris house to D63 Malas house road (Jaya Mawatha) | [9 empty] | 500000 | 500000 | [17 empty] | 1 | bar: Total categorized by Sectors * I
Total |  | 0 |  |  | 87 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 58000000 | 56000000 | 0 | 0 | 0 | 1500000 | 500000 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 7 | 21 | 9 | 9 | 10 | 31 | 1484747.52 | 0
* Projects should be categorized for following sectors
| Circular code |  |  | Sector Name | [9 empty] | ** Physical progress
| I |  |  | Village Road, Culverts, Bridges, side Drinage etc | [9 empty] | A - Estimates are being / to be prepared
| II |  |  | Werehouse Facilities for Agricultureal Production | [9 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
| III |  |  | Economic Centers including Weekly Faires, Small Shops | [9 empty] | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
| IV |  |  | Construction and renovation of Small Tanks, C anals, Anicuts, ponds and Agricultural Wells | [9 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
| V |  |  | Community Drinking Water Supply Projects | [9 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
| VI |  |  | Development/ Modernization of rural Health Centers and Providing Facilities | [9 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
| VII |  |  | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [9 empty] | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
| VIII |  |  | Providing for Prevention of Disasters for Human habitants from wild Animals | [9 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
| IX |  |  | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development

## SINHALA
“සපිරි ගමක්“ ප්‍රජා පාදක ග්‍රාමීය සංවර්ධන වැඩසටහන - 2020
අමාත්‍යංශය :- ජාතික ප්‍රතිපත්ති හා ආර්ථික කටයුතු අමාත්‍යාංශය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | ක්ෂේත්‍රය | ග්‍රාම නිලධාරි වසම | ගම්මානය | ව්‍යාපෘතිය | වෙන්කළ මුදල (රු.ශ) | ගිවිසුම් කාලය | ඇස්තමේන්තු මුදල කර්මාන්ත ව්‍යාපෘති සඳහා (රු.ශ) | මාර්ග මීටර් | කොන්ත්‍රාත් කරු | භෞතික ප්‍රගතිය 2020.10.05 | [9 empty] | වියදම රු. | ප්‍රතිලාභින් ගණන
[10 empty] | A | B | B | B | B | 11%-25% | 26%-50% | 51%-75% | 76%-99% | 100%
[11 empty] | ඇස්තමෙන්තු අනුමත කිරීම/ ලිපිගොනු සකසා ඇත | ටෙන්ඩර්/ මිල ගණන් කැඳවා ඇත. | ටෙන්ඩර්/ මිල ගණන් ලැබී ඇත. | කොන්ත්‍රාත් පිරිනමා ඇත.
1 | ග්‍රාමීය මාර්ග | උඩඅරාව | මුරුංගාවත්ත | මුරුංගාවත්ත මාර්ගය කැටගල් අල්ලා මාර්ගය සකස් කිරීම | 1000000 |  |  |  | එක්සත් ගැමුණු ගොවි සංවිධානය | [5 empty] | 1
2 | ග්‍රාමීය මාර්ග | උඩඅරාව | පේරකැටිය | පේරකැටිය බුළුගල මාර්ගයේ බෝක්කුව දැමීම | 500000 |  |  |  | එක්සත් ගැමුණු ගොවි සංවිධානය | [8 empty] | 1
3 | ග්‍රාමීය මාර්ග | උඩඅරාව | උඩඅරාව | ජනාවාස 02 මාර්ගය කැටගල් අල්ලා සකස් කිරීම | 500000 |  |  |  | එක්සත් ගැමුණු ගොවි සංවිධානය | [8 empty] | 1
4 | ග්‍රාමීය මාර්ග | හොරබොක්ක | ගංගොඩකුඹුර | හොරබොක්ක සෞඛ්‍ය මධ්‍යස්ථානයට ආරක්ෂක වැටක් ඉදිකිරිම හා ප්‍රධාන දොරටුව ඉදි කිරීම | 500000 |  |  |  | අම්බලන්පොත අමුණ ගොවි සංවිධානය |  |  |  |  | 1
5 | ග්‍රාමීය මාර්ග | හොරබොක්ක | දෙමෝදරයාය | දෙමෝදරයාය මනම්පිටිය ප්‍රධාන මාර්ගයේ 1 වන බෝක්කුව සැකසීම | 500000 |  |  |  | ප්‍රගති ගොවි සංවිධානය - මනම්පිටිය |  | 1
6 | ග්‍රාමීය මාර්ග | හොරබොක්ක | වැලිආරලන්ද | කොට්ටගස් ලන්ද මාර්ගය 1km කණු සකසා බොරළු දමා පිළිසකර කිරීම | 500000 |  |  |  | අම්බලන්පොත අමුණ ගොවි සංවිධානය | [9 empty] | 1
7 | ග්‍රාමීය මාර්ග | හොරබොක්ක | මනම්පිටිය | මනම්පිටිය දෙමෝදරයාය පාලම ඉදිකිරීම | 500000 | [12 empty] | 1
8 | ග්‍රාමීය මාර්ග | පැල්වත්ත | වැවේවෙල ඉහළ | වැවේවෙලයාය පහල බෝගහ ඇල මාර්ගය ග්‍රැවල් දැමීම | 500000 |  |  |  | පිඹුරාලන්ද ගොවි සංවිධානය | [6 empty] | 1
9 | ග්‍රාමීය මාර්ග | පැල්වත්ත | වැවේවෙල ඉහළ | ජනාවාස 2 මාර්ගයේ කොටසක් ග්‍රැවල් දැමීම | 900000 | 2020.05.29 - 2020.08.31 |  |  | පිඹුරාලන්ද ගොවි සංවිධානය | [9 empty] | 1
10 | ග්‍රාමීය මාර්ග | පැල්වත්ත | පිඹුරාලන්ද | පිඹුරාලන්ද මනම්පිටිය අතුරු මාර්ගය ග්‍රැවල් කිරීම | 600000 |  |  |  | පිඹුරාලන්ද ගොවි සංවිධානය | [7 empty] | 1
11 | ග්‍රාමීය මාර්ග | කුකුරම්පොළ | කුමාරපොත | කුමාරපොත කොන්ක්‍රීට් මාර්ගය අවසානයේ සිට දේවාල කොටස දක්වා මාර්ගය කොන්ක්‍රීට් කිරීම | 1000000 | 2020.05.29 - 2020.08.31 |  |  | එඩරුගලයාය ගොවි සංවිධානය | [9 empty] | 1
12 | ග්‍රාමීය මාර්ග | කුකුරම්පොළ | නාගස්යාය වටිය | ප්‍රධාන මාර්ගයේ සිට නාගස්යාය පිටිය මාර්ගය ප්‍රතිසංස්කරණය කිරීම | 1000000 | 2020.05.29 - 2020.08.32 |  |  | එඩරුගලයාය ගොවි සංවිධානය | [9 empty] | 1
13 | ග්‍රාමීය මාර්ග | කුමාරගම | කුමාරගම වසම | දේවාල කොටස ගම්මානයේ කැඩී ගිය බෝක්කුව සංවර්ධනය කිරිම | 2000000 | [11 empty] | 1
14 | ග්‍රාමීය මාර්ග | රහතන්ගම | ජනාවාස 10 | පන්සල පාර බොරළු දමා සංවර්ධනය කිරිම | 500000 |  |  |  | රහතන්ගම එක්සත් ගොවි සංවිධානය | [9 empty] | 1
15 | ග්‍රාමීය මාර්ග | රහතන්ගම | ජනාවාස 16 | ක්‍රීඩාගාරයේ වහලය සැකසීම | 500000 |  |  |  | රහතන්ගම එක්සත් ගොවි සංවිධානය |  |  |  |  | 1
16 | ග්‍රාමීය මාර්ග | රහතන්ගම | ජනාවාස 14 | ගම්මානය අතුරු මාර්ග බොරලු දමා සංවර්ධණය කිරිම. | 500000 |  |  |  | රහතන්ගම එක්සත් ගොවි සංවිධානය | [7 empty] | 1
17 | ග්‍රාමීය මාර්ග | රහතන්ගම | ජනාවාස 09 | ගම්මාන අතුරු මාර්ගය බොරළු දමා සංවර්ධනය කිරිම. | 500000 |  |  |  | රහතන්ගම එක්සත් ගොවි සංවිධානය | [9 empty] | 1
18 | ග්‍රාමීය මාර්ග | කුමාරපුර | මිණුම්සේවා ජනපදයප | මිණුම්සේවා ජනපදයප ප්‍රජාශාලාව අසල සිට කුඩාඔය ගග දක්වා මාර්ගය කොන්ක්‍රීට් කිරීම | 1000000 |  |  |  | වීරකැටිය ‍ගොවි සංවිධානය මිණුම්සේවා ජනපදයප |  |  |  |  | 1
19 | ග්‍රාමීය මාර්ග | කුමාරපුර | වැලිමඩයාය | දේවාලය අසලින් කුඩාඔය ගග දෙසට යන මාර්ගය කොන්ක්‍රීට් කිරීම | 500000 |  |  |  | වීරකැටිය ‍ගොවි සංවිධානය මිණුම්සේවා ජනපදයප | [5 empty] | 1
20 | ග්‍රාමීය මාර්ග | කුමාරපුර | වැලිමඩයාය | කේ.එම්.බුද්ධදාස මහතාගේ නිවස අසලින් ගග දෙසට යන මාර්ගය කොන්ක්‍රීට් කිරීම | 500000 |  |  |  | වීරකැටිය ‍ගොවි සංවිධානය මිණුම්සේවා ජනපදයප | [9 empty] | 1
21 | ග්‍රාමීය මාර්ග | යටියල්ලාතොට | බුරුතපාරගම | තංගල්ල නිවස සිට එස්.එම්.සෙනෙවිරත්ව මහතාගේ නිවස දක්වා මාර්ගය | 1000000 |  |  |  | යටියල්ලාතොට ගොවි සංවිධානය | [8 empty] | 1
22 | ග්‍රාමීය මාර්ග | යටියල්ලාතොට | පරණ බුරුතපාර | ඩී.එම්.බුද්ධදාස මහතාගේ නිවස අසල සිට පුවක්පිටිය වැව දක්වා යන මාර්ගය | 1000000 |  |  |  | යටියල්ලාතොට ගොවි සංවිධානය | [5 empty] | 1
23 | ග්‍රාමීය මාර්ග | මහසෙන්පුර | කටුපොත වැව පෙරයන්ආර | පහලෙවල මාර්ගය කුකුරම්ෙපාල මාර්ගයට පිවිසුම් ෙකාටස ග්‍රැවල් කිරීම 400m | 500000 |  |  |  | සමගි ගොවි සංවිධානය - කටුපොත වැව |  |  |  |  | 1
24 | ග්‍රාමීය මාර්ග | මහසෙන්පුර | කටුපොත වැව පෙරයන්ආර | බතලවාඩිය මාර්ගය ග්‍රැවල් කිරීම 400m | 500000 | [12 empty] | 1
25 | ග්‍රාමීය මාර්ග | මහසෙන්පුර | මුල්ලේකුඹුරගම | මුල්ලේකුඹුර අතුරු මාර්ගය බණ්ඩාරවෙල වාඩිය පාර ග්‍රැවල් කිරීම 600m | 500000 |  |  |  | සමගි ගොවි සංවිධානය - කටුපොත වැව | [9 empty] | 1
26 | ග්‍රාමීය මාර්ග | මහසෙන්පුර | ගල්ගොඩයායගම | රන්තිලක මහතාගේ නිවස ලග පෙට්ටි බෝක්කුවක් දමා පාර ඉස්සීම | 500000 |  |  |  | සමගි ගොවි සංවිධානය - කටුපොත වැව | [7 empty] | 1
27 | ග්‍රාමීය මාර්ග | වෙහෙරගල | වෙහෙරගල | වෙහෙරගල ආරණ්‍යයට යන වෙහෙරගල ප්‍රධාන මාර්ගය 1km ක් තාර දැමීම (අලුත්වැඩියාව) | 500000 |  |  |  | නිකවැව එක්සත් ගොවි සංවිධානය |  |  |  |  | 1
28 | ග්‍රාමීය මාර්ග | වෙහෙරගල | වෙහෙරගල | සලනි පෙර පාසල ලග සිට පන්සලට පහළින් ඇති පාර කොන්ක්‍රීට් කිරීම | 500000 |  |  |  | නිකවැව එක්සත් ගොවි සංවිධානය | [8 empty] | 1
29 | ග්‍රාමීය මාර්ග | වෙහෙරගල | ගැමුණුගම | ආර්ථික සංවර්ධන නිලධාරියාගේ කාර්යාලය අසලින් යන මාර්ගය (කොන්ක්‍රීට් කිරීම 200m) | 500000 |  |  |  | ගැමුණු වැව ගොවි සංවිධානය | [9 empty] | 1
30 | ග්‍රාමීය මාර්ග | වෙහෙරගල | ගැමුණුගම | ඇල බන්ටෙක පාරේ සිට ගැමුණුගම මාර්ගය දක්වා කැටගල් ඇල්ලීම 200m | 500000 |  |  |  | ගැමුණු වැව ගොවි සංවිධානය | [5 empty] | 1
31 | ග්‍රාමීය මාර්ග | උනාවටුන | හරිගලගම | සිතුමිණ අතුරු මාර්ගය කොන්ක්‍රිට් කිරිම | 500000 |  |  |  | ශ්‍රී සුමංගල ගොවි සංවිධානය | [5 empty] | 1
32 | ග්‍රාමීය මාර්ග | උනාවටුන | උනාවටුන | අඹකොළ වැව බන්ටෙක අසල සිට යුදගනාව කාපට් මාර්ගය දක්වා ග්‍රැවල් කිරිම | 1000000 | 2020.05.29 - 2020.08.31 |  |  | ශ්‍රී සුමංගල ගොවි සංවිධානය | [9 empty] | 1
33 | ග්‍රාමීය මාර්ග | උනාවටුන | උනාවටුන | උනාවටනු පිරිවෙන අතුරු මාර්ගය කොන්ක්‍රිට් ගල් ඇතිරීම | 500000 |  |  |  | ශ්‍රී සුමංගල ගොවි සංවිධානය | [5 empty] | 1
34 | පානීය ජලය | පුහුල්කොටුව | පුහුල්කොටුව | පුහුල්කොටුව ප්‍රාථමික විද්‍යාලය අසල ජල ෆිල්ටරයක් ස්ථාපිත කිරීම | 1000000 | [5 empty] | 1
35 | ග්‍රාමීය මාර්ග | පුහුල්කොටුව | යුදගනා ජනපදය | සුමංගල මාවතේ 48 නිවස අසල සිට අංක 08 නිවස දක්වා මාර්ගය කොන්ක්‍රීට් කිරීම | 1000000 |  |  |  | යුදගනාව සමගිවැව ගොවි සංවිධානය | [9 empty] | 1
36 | ග්‍රාමීය මාර්ග | යුදගනාව | බෝධිය පාර | බෝධිය පාර දීපා මහත්මියගේ නිවස අසල සියඹලා ගස් හන්දියේ සිට අමුණ පාර කෙළවර දක්වා 1km පමණ ග්‍රැවල් කිරීම | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය - යුදගනාව | [7 empty] | 1
37 |  | යුදගනාව |  | අමුණපාර චන්ද්‍රිකා මහත්මියගේනිවස අසලින් යුදගනාව ප්‍රධාන මාර්ගය දක්වා යන යකඩ පාලම පාර | 500000 | [9 empty] | 1
38 | පානීය ජලය | යුදගනාව | අක්කර 100 | අක්කර 100 වයි.ජේ.එම්.සුනිල් මහතාගේ නිවස අසල සිට අක්කර 100 අවසානය දක්වා ජලනල දීර්ඝ කිරීම | 500000 | [5 empty] | 1
39 | ග්‍රාමීය මාර්ග | යුදගනාව | වැලිමඩයාය | වැලිමඩයාය නිශ්ශංක මහතාගේ නිවස අසල සිට අතුරු මාර්ග ග්‍රැවල් දමා පිළිසකර කිරීම | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය - යුදගනාව | [9 empty] | 1
40 | ග්‍රාමීය මාර්ග | දික්යාය | රාජකණ්ඩිය | රාජකණ්ඩිය ප්‍රධාන මාර්ගය ග්‍රැවල් යොදා, බෝක්කු හා කාණු පද්ධතිය සමග සංවර්ධනය කිරීම | 2000000 |  |  |  | රාජකණ්ඩිය ගොවි සංවිධානය | [9 empty] | 1
41 | ග්‍රාමීය මාර්ග | උඩගම | උඩගම | සුසානභුමිය හරහා බඩල්කුඹුර - බුත්තල ප්‍රධාන මාර්ගය දක්වා ඇති මාර්ගයේ ඉතිරි කොටස කැටගල් අල්ලා සංවර්ධනය කිරිම. | 2000000 |  |  |  | ග්‍රාම සංවර්ධන ප්‍රාදේශීය බලමණ්ඩලය | [6 empty] | 1
42 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | නාමණ්ඩිය | නාමණ්ඩියේ ඇතුළු ගම්මානය මාර්ගයේ තිබෙන බෝක්කුව හා මාර්ගය සංවර්ධනය කිරීම | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [9 empty] | 1
43 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | පෙරහැර මාවත | පෙරහැර උඩ මාවතේ මාර්ගයේ සිට ප්‍රධාන මාර්ගය දක්වා කැටගල් ඇල්ලීම (2km) | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [5 empty] | 1
44 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | පෙට්ටගම්වෙල | දෙවන පටුමග මාර්ගයේ ඉතිරි තොටස කැටගල් ඇල්ලීම | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [5 empty] | 1
45 | ග්‍රාමීය මාර්ග | පෙට්ටගම්වෙල | පෙට්ටගම්වෙල | පෙට්ටගම්වෙල වත්ත මාර්ගයේ ඉතිරි කොටස කැටගල් ඇල්ලීම | 500000 |  |  |  | පැරකුම් ගොවි සංවිධානය, පෙට්ටගම්වෙල | [5 empty] | 1
46 | ග්‍රාමීය මාර්ග | මැදගම | ගැරඩිබකිණි | රාජපක්ෂ මාවතේ සිට පිටමුල්ල මාර්ගය සංවර්ධනය කිරීම | 500000 |  |  |  | මැදගම ග්‍රාම සංවර්ධන සමිතිය | [8 empty] | 1
47 | ග්‍රාමීය මාර්ග | මැදගම | අලුත්වෙල | දෙයියන්නේවෙල හන්දියේ සිට අලුත්වෙල තිබිබටුවාව පුරාණ රජමහා විහාරය දක්වා මාර්ගය සැකසීම | 500000 |  |  |  | මැදගම ග්‍රාම සංවර්ධන සමිතිය | [6 empty] | 1
48 | ග්‍රාමීය මාර්ග | මැදගම | කරවිලකොටුව | ගල්කොරිය පාර (පැති බැම්ම සමග පාර සකස් කිරීම) | 500000 |  |  |  | මැදගම ග්‍රාම සංවර්ධන සමිතිය | [6 empty] | 1
49 | ග්‍රාමීය මාර්ග | මැදගම | කරවිලකොටුව | පළමු පටුමග තුන්මං හන්දියේ සිට කරවිල කොටුව වැව දක්වා පාර සංවර්ධනය කිරීම | 500000 |  |  |  | මැදගම ග්‍රාම සංවර්ධන සමිතිය | [9 empty] | 1
50 | ග්‍රාමීය මාර්ග | වගුරුවෙල | දෙයියන්නේවෙල | දෙයියන්නේවෙල බෝ ගහ ලග සිට ගගට යන පාර ග්‍රැවල් කිරීම (800m) | 500000 |  |  |  | වගුරුවෙල ග්‍රාම සංවර්ධන සමිතිය | [9 empty] | 1
51 | ග්‍රාමීය මාර්ග | වගුරුවෙල | කන්දෙයාය | කන්දෙයාය තුන්මං හන්දිය අසල (දඹගහ අසළ) බෝක්කුව සහ 100mක් සංවර්ධනය කිරීම | 1000000 |  |  |  | වගුරුවෙල ග්‍රාම සංවර්ධන සමිතිය | [8 empty] | 1
52 | ග්‍රාමීය මාර්ග | වගුරුවෙල | දඹගස්කොටුව | දඹගස්කොටුව මාර්ගය සංවර්ධනය කිරීම | 500000 |  |  |  | වගුරුවෙල ග්‍රාම සංවර්ධන සමිතිය |  |  |  |  | 1
53 | ග්‍රාමීය මාර්ග | කෝන්කැටිය | කෝන්කැටිය | අලිමංතල පාර පහල කොටස සූරිය මහතාගේ නිවසට යන පාර අසල සිට බෝක්කුව දමා ග්‍රැවල් කිරිම. | 500000 |  |  |  | තිඹිරිගස්ආර මහවැව ගොවි සංවිධානය, | [5 empty] | 1
54 | ග්‍රාමීය මාර්ග | කෝන්කැටිය | කෝන්කැටිය | 17 කණුව සෝම මහතාගේ නිවස දක්වා අතුරු මාර්ගය බෝක්කුවක් සහිතව ග්‍රැවල් කිරිම | 500000 |  |  |  | තිඹිරිගස්ආර මහවැව ගොවි සංවිධානය, | [9 empty] | 1
55 | ග්‍රාමීය මාර්ග | කෝන්කැටිය | කෝන්කැටිය | 16 කණුව ප්‍රජා ශාලාව අලුත්වැඩියාව සහ වැසිකිලියක් ඉදිකිරිම | 500000 |  |  |  | තම්මැන්නාර වැව ගොවි සංවිධානය, | [7 empty] | 1
56 | ග්‍රාමීය මාර්ග | කෝන්කැටිය | කෝන්කැටිය | තම්මැන්නාර වැව පාර ප්‍රධාන මාර්ගයේ සිට කෝසුවක් සහිතව ග්‍රැවල් කිරිම | 500000 |  |  |  | තම්මැන්නාර වැව ගොවි සංවිධානය, | [9 empty] | 1
57 | ග්‍රාමීය මාර්ග | ගෝනගංආර | ගෝනගංආර වසම | ගෝනගංආර වතුර ටැංකිය අසල සිට ආනන්ද මහතාගේ කඩේ දක්වා ග්‍රැවල් කිරීම | 500000 |  |  |  | පෑලැස්ස ගොවි සංවිධානය, | [7 empty] | 1
58 | ග්‍රාමීය මාර්ග | ගෝනගංආර | දියකිරිත්ත | දියකිරිත්ත විජයවීර මහතාගේ නිවස අසල අතුරු මාර්ගය ග්‍රැවල් කිරිම | 500000 |  |  |  | දියකිරිත්ත ග්‍රාම සංවර්ධන සමිතිය | [7 empty] | 1
59 |  | ගෝනගංආර | ගෝනගංආර වසම | මහතුන් මහතාගේ නිවස අසලින්පටන් ගන්නා අතුරු මාර්ගය ග්‍රැවල් කිරිම | 500000 |  |  |  | දියකිරිත්ත ග්‍රාම සංවර්ධන සමිතිය | [5 empty] | 1
60 | ග්‍රාමීය මාර්ග | ගෝනගංආර | ගෝනගංආර වසම | 19 වැව පාර මහීපාල මහතාගේ නිවස අසල සිට බෝක්කුව සහිතව ග්‍රැවල් කිරිම. | 500000 |  |  |  | ගලපිට ආර ගොවි සංවිධානය, | [5 empty] | 1
61 | ග්‍රාමීය මාර්ග | මහගොඩයාය | ගගේයාය | ගගේයාය මාර්ගයේ ට්‍රාන්ස්පෝමරය ඉදිරිපිට ඇති බෝක්කුව ළග සිට ඊ.ඒ.සරත් මහතාගේ නිවස දක්වා මාර්ගය 50m ක් සහ පැළ තවාන මාර්ගයේ එම්.එම්.සුනිල් මහතාගේ නිවස දක්වා මාර්ගය ග්‍රැවල් කිරීම | 1000000 |  |  |  | ජය විජය ගොවි සංවිධානය, මහගොඩයාය | [8 empty] | 1
62 | ග්‍රාමීය මාර්ග | මහගොඩයාය | එගොඩවත්ත | දේවගිරි ආරණ්‍ය මාර්ගය ග්‍රැවල් කිරීම | 1000000 |  |  |  | ජය විජය ගොවි සංවිධානය, මහගොඩයාය | [6 empty] | 1
63 | ග්‍රාමීය මාර්ග | ඔක්කමිපිටිය | කදුරුවැලෑන | වීරගස්හන්දිය කදුරුවැලෑන මාර්ගය කැටගල් අල්ලා පැති බැම්ම සෑදීම (150m) | 500000 |  |  |  | දාගොබ ඇල ගොවි සංවිධානය | [6 empty] | 1
64 | ග්‍රාමීය මාර්ග | ඔක්කමිපිටිය | ගල්කන්ද | කණ්ඩියාය සුසාන භූමිය ආරණ්‍යය දක්වා මාර්ගය කොන්ක්‍රීටි කිරීම | 500000 |  |  |  | දාගොබ ඇල ගොවි සංවිධානය | [6 empty] | 1
65 | ග්‍රාමීය මාර්ග | ඔක්කමිපිටිය | කණ්ඩියාය | කණ්ඩියාය ඇලකණ්ඩිය මාර්ගය බෝක්කු දමා සෑදීම | 500000 |  |  |  | දාගොබ ඇල ගොවි සංවිධානය | [6 empty] | 1
66 | ග්‍රාමීය මාර්ග | ඔක්කමිපිටිය | බඳයාය | බඳයාය ඉලුක්පිටිය යා කරන මාර්ගය කොන්ක්‍රීට් දැමීම | 500000 |  |  |  | දාගොබ ඇල ගොවි සංවිධානය | [5 empty] | 1
67 | ග්‍රාමීය මාර්ග | ගාමිණිපුර | 2 කණුව | 2 කණුව පී.ජී.සිරියලතා මහත්මියගේ කඩේ අසලින් කන්ද ගම්මානයට යන මාර්ගය 300m කාණු පද්ධතිය සහිත කොන්ක්‍රීට් කිරීම | 500000 |  |  |  | එක්සත් ගොවි සංවිධානය | [5 empty] | 1
68 | ග්‍රාමීය මාර්ග | ගාමිණිපුර | 3 කණුව | බී.කේ.විමලසේන මහතාගේ නිවස අසලින් ඇලමානයාය මාර්ගය කොන්ක්‍රීට් කිරීම හා කාණු පද්ධතිය සකස් කිරිම 500m | 500000 |  |  |  | එක්සත් ගොවි සංවිධානය | [5 empty] | 1
69 | ග්‍රාමීය මාර්ග | ගාමිණිපුර | බටුකොටුව | බටුකොටුව ඇක්මන් මහතාගේ නිවස අසලින් කන්දේගම්මානයට යන මාර්ගය 400m කොන්ක්‍රීට් කිරීම හා කාණු පද්ධතිය සකස් කිරීම | 500000 |  |  |  | එක්සත් ගොවි සංවිධානය | [5 empty] | 1
70 | ග්‍රාමීය මාර්ග | ගාමිණිපුර | රත්වත්තමාවත | රත්වත්ත මාවත පළමු පටුමග එච්.එම්.ශාන්ත මහතාගේ නිවස අසල සිට 400m කොන්ක්‍රීට් කිරීම | 500000 |  |  |  | එක්සත් ගොවි සංවිධානය | [5 empty] | 1
71 | ග්‍රාමීය මාර්ග | බුරුතගොල්ල | වැවපෙදෙස | නිමල් මහතාගේ කඩය අසල සිට විජය මහතාගේ නිවස අසල ඇති නළ ලිඳ දක්වා 1/21km (වටවල ගොඩකන්ද පාර) ග්‍රැවල් කිරීම | 750000 | 2020.05.29 - 2020.08.32 |  |  | ජනපුබුදු ග්‍රාම සංවර්ධන සමිතිය | [9 empty] | 1
72 | ග්‍රාමීය මාර්ග | බුරුතගොල්ල | බුරුතගොල්ල | එම්.විමලසේන මහතාගේ නිවස අසල සිට ටිකිරි රාළ මහතාගේ නිවස දක්වා වූ මාර්ගය කොන්ක්‍රීට් කිරිම. | 750000 | 2020.05.29 - 2020.08.32 |  |  | ජනපුබුදු ග්‍රාම සංවර්ධන සමිතිය | [9 empty] | 1
73 | ග්‍රාමීය මාර්ග | බුරුතගොල්ල | වැව පෙදෙස | ජෝති මුදලාලිගේ කඩය අසල සිට නන්ද ටීචර්ගේ නිවස දක්වා 150m කැටගල් ඇල්ලීම | 500000 |  |  |  | ජනපුබුදු ග්‍රාම සංවර්ධන සමිතිය | [5 empty] | 1
74 | ග්‍රාමීය මාර්ග | පහලගම | ගඩොල්බැම්ම | බුත්තල ගෙදර අසල සිට ගග දක්වා ගඩොල් බැම්ම මාර්ගය කොන්ක්‍රීට් කිරීම 500m | 1000000 |  |  |  | නුගමන්ඩිය ගොවි සංවිධානය | [8 empty] | 1
75 | ග්‍රාමීය මාර්ග | පහලගම | දඹේයාය | දඹේයාය කණ්ටු විදුහල අසල මාර්ගය ගග දක්වා ග්‍රැවල් කිරීම (300m) | 500000 | 2020.05.29 - 2020.08.32 |  |  | නුගමන්ඩිය ගොවි සංවිධානය | [9 empty] | 1 | 495000
76 | ග්‍රාමීය මාර්ග | පහලගම | පිංතාලිය හන්දිය | ආර්.එම්.ජයසිංහ මහතාගේ නිවස අසලින් ඇති අළුත් ගෙදර පාර ග්‍රැවල් කිරීම 300m | 500000 | 2020.05.29 - 2020.08.32 |  |  | නුගමන්ඩිය ගොවි සංවිධානය | [9 empty] | 1
77 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය | ගල්ටැම්මණ්ඩිය | ඇපරැක්ක හාල්මෝල අසල ගැමුණුවැව මාවත මැදපාර කුඹුරු යාය කොටස 500m ග්‍රැවල් කිරීම | 500000 |  |  |  | සමගි ගොවි සංවිධානය, ගල්ටැම්මණ්ඩිය | [7 empty] | 1
78 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය | බදුල්ලගම | බදුළු ගම්මානයට යන මාර්ගය ග්‍රැවල් කිරීම (500m) | 500000 |  |  |  | සමගි ගොවි සංවිධානය, ගල්ටැම්මණ්ඩිය | [5 empty] | 1
79 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය | ගල්ටැම්මණ්ඩිය | සෞඛ්‍ය මධ්‍යස්ථානය අසල සූරියගස්වත්ත මාර්ගය 500m කොන්ක්‍රීට් කිරිම | 500000 |  |  |  | සමගි ගොවි සංවිධානය, ගල්ටැම්මණ්ඩිය | [6 empty] | 1
80 | ග්‍රාමීය මාර්ග | ගල්ටැම්මණ්ඩිය | ගල්පීල්ල | ගල්කැට ආර මාර්ගය 500m ග්‍රැවල් කිරිම සහ බොෝක්කුව පිරිත් කඩේ අසල සිට කන්ද දක්වා ප්‍රතිසංස්කරණය | 500000 | 2020.05.29 - 2020.08.32 |  |  | සමගි ගොවි සංවිධානය, ගල්ටැම්මණ්ඩිය | [9 empty] | 1
81 | ග්‍රාමීය මාර්ග | උළුගල | 6 ඇල | 6 ඇල සිට ගල්ටැම්මණ්ඩිය ආර දක්වා මාර්ගය බොරළු දමා ප්‍රතිසංස්කරණය කිරීම හා 06 ඇල පාලම ප්‍රතිසංස්කරණය කිරීම | 1000000 |  |  |  | නැගෙනහිර ගොවි සංවිධානය |  |  |  |  | 1
82 | ග්‍රාමීය මාර්ග | උළුගල | 01 ඇල සිට 09 ඇල දක්වා | 01 ඇල සිට 09 ඇල දක්වා ඇල මාර්ගය බොරළු දමා ප්‍රතිසංස්කරණය කිරීම | 500000 | 2020.05.29 - 2020.08.32 |  |  | නැගෙනහිර ගොවි සංවිධානය | [9 empty] | 1
83 | ග්‍රාමීය මාර්ග | උළුගල | සිය මාවත | සිය මාවත මාර්ගයේ කි.මි.01ක් පමණ බොරළු දමා ප්‍රතිසංස්කරණය කිරීම | 500000 | 2020.05.29 - 2020.08.32 |  |  | නැගෙනහිර ගොවි සංවිධානය | [9 empty] | 1 | 495000
84 | ග්‍රාමීය මාර්ග | මිණිපුරගම | ඉසුරුගම | බෝගස අසල සිට ඉසුරුගම බෙරලිමංකඩ දක්වා මාර්ගය සංවර්ධනය කිරිම | 1000000 |  |  |  | මිණිපුරගම කාන්තා ග්‍රාම සංවර්ධණ සමිතිය | [9 empty] | 1
85 | ග්‍රාමීය මාර්ග | මිණිපුරගම | මිණිපුරගම | කරුවලගස්දෝව නිවාස මාර්ගය 300m කැටගල් ඇල්ලීම | 500000 |  |  |  | මිණිපුරගම කාන්තා ග්‍රාම සංවර්ධණ සමිතිය | [5 empty] | 1
86 | ග්‍රාමීය මාර්ග | මිණිපුරගම | මිණිපුරගම | වැව මාර්ගය 500m (බෝක්කු 03) ග්‍රැවල් දැමීම | 500000 | 2020.05.29 - 2020.08.32 |  |  | මිණිපුරගම කාන්තා ග්‍රාම සංවර්ධණ සමිතිය | [9 empty] | 1 | 494747.52
87 | ග්‍රාමීය මාර්ග | මාලිගාවිල | නියදැල්ල | නියදැල්ල අමුණ මාර්ගය 1km ප්‍රතිසංස්කරණය කිරීම | 500000 | 2020.05.29 - 2020.08.33 |  |  | නියදැල්ල ගොවි සංවිධානය | [9 empty] | 1
88 | ග්‍රාමීය මාර්ග | මාලිගාවිල | රාත්‍රීවැව | රාත්‍රී වැව මං සන්ධිය අසල සිට බෝගස් හන්දිය දක්වා මාර්ගය 3km ප්‍රතිසංස්කරණය කිරීම | 500000 | 2020.05.29 - 2020.08.34 |  |  | නියදැල්ල ගොවි සංවිධානය | [9 empty] | 1
89 | ග්‍රාමීය මාර්ග | මාලිගාවිල | සාම මාවත | සාම මාවත ඩී.එම්.ජයසේකර මහතාගේ නිවස අසල සිට මාර්ගය සහ සුනිල් මහතාගේ නිවස අසල මාර්ගය සෞඛ්‍ය මධ්‍යස්ථානයට ප්‍රවේශ මාර්ගය දක්වා ප්‍රතිසංස්කරණය කිරීම 2km | 500000 | 2020.05.29 - 2020.08.35 |  |  | නියදැල්ල ගොවි සංවිධානය | [9 empty] | 1
90 | ග්‍රාමීය මාර්ග | මාලිගාවිල | පහළ දඹේගොඩ | ප්‍රේමසිරි මහතාගේ නිවස අසල සිට D63 මාලා නිලන්ති මහත්මියගේ නිවස අසල දක්වා මාර්ගය 1km ප්‍රතිසංස්කරණය කිරීම (ජය මාවත) | 500000 | 2020.05.29 - 2020.08.36 |  |  | නියදැල්ල ගොවි සංවිධානය | [9 empty] | 1
මුළු එකතුව |  |  |  |  | 58000000 |  | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 7 | 21 | 9 | 9 | 10 | 31 | 1484747.52
සියලු ඉදිකිරීම් ව්‍යාපෘති | [19 empty] | 90
0% - 10% = ව්‍යාපෘතිය අනුමත කර, ප්‍රතිපාදන ලබා දි තිබීම/ඇස්තමේන්තු සකස් කර තිබිම | 0% - 10% = ව්‍යාපෘතිය අනුමත කර, ප්‍රතිපාදන ලබා දි තිබීම
11% - 25% = ගිවිසුම්ගත වි ඉදිකිරිම් ආරම්භ කර තිබිම
26% - 50% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 26% සිට 50%ක වැඩ අවසන් කර තිබිම
51% - 75% = ඇස්තමේන්තුගත වැඩ කොටස් වලින් 51% සිට 99%ක වැඩ අවසන් කර තිබිම
76% - 100% = ඉදිකිරිම් අවසන් කර ගෙවීම් සිදු කිරීම

## DS Summary
“සපිරි ගමක්“ ප්‍රජා පාදක ග්‍රාමීය සංවර්ධන වැඩසටහන - 2020
අමාත්‍යංශය :- ජාතික ප්‍රතිපත්ති හා ආර්ථික කටයුතු අමාත්‍යාංශය
බුත්තල ප්‍රාදේශීය ලේකම් කොට්ඨාසය
අනු අංකය | භෞතික ප්‍රගතිය 2020.08.31 | ප්‍රමාණය
1 | මුළු ව්‍යාපෘති සංඛ්‍යාව | 90
2 | ඇස්තමෙන්තු සකස්කර ඇති ව්‍යාපෘති සංඛ්‍යාව | 79
3 | කොන්ත්‍රාත් පිරිනමා ඇති ව්‍යාපෘති සංඛ්‍යාව | 18
4 | 11 - 25% ක් වැඩ අවසන් | 29
5 | 26 - 50% ක් වැඩ අවසන් | 8
6 | 51 - 75% ක් වැඩ අවසන් | 3
7 | 76 - 99% ක් වැඩ අවසන් | 3
8 | 100% | 18
9 | සංශෝධනයට යොමුකර ඇති ව්‍යාපෘති සංඛ්‍යාව | 0
10 | වෙන් කළ මුදල | 58000000
11 | මෙතෙක් වියදම | 0